## Proposed Final STIP
PROPOSED FINAL 2024-2033 STATE TRANSPORTATION IMPROVEMENT PROGRAM: SCHEDULES OF PROJECTS SELECTED THROUGH PRIORITIZATION COMPARED TO DRAFT STIP (AUGUST 2022)
NOTES: COSTS AND SCHEDULES ARE AS OF MARCH 31, 2023 AND ARE SUBJECT TO CHANGE. PRIORITIZATION STATUS IS BASED ON THE FIRST YEAR OF RIGHT-OF-WAY, UTILITIES, OR CONSTRUCTION FUNDING. IF THE FIRST YEAR OF RIGHT-OF-WAY, UTILITIES, OR CONSTRUCTION FUNDING IS SCHEDULED ON OR BEFORE FISCAL YEAR 2028, THE PROJECT IS CONSIDERED "SCHEDULED FOR DELIVERY" AND DOES NOT HAVE TO BE REPRIORITIZED.
ESSENTIAL PROJECT INFORMATION | [6 empty] | PRIORITIZATION INFORMATION |  |  |  | SCHEDULE INFORMATION
COUNTY(S) | ROUTE/CITY | DESCRIPTION | MODE | DIVISION(S) | MPOs/RPOs | PROJECT ID | STI FUNDING CATEGORY DRAFT STIP (AUGUST 2022) | STI FUNDING CATEGORY FINAL STIP (MARCH 2023) | PRIORITIZATION STATUS DRAFT 2024-2033 STIP (AUGUST 2022) | PRIORITIZATION STATUS FINAL 2024-2033 STIP (MARCH 2023) | RIGHT-OF-WAY SCHEDULE DRAFT 2024-2033 STIP (AUGUST 2022) | RIGHT-OF-WAY SCHEDULE FINAL 2024-2033 STIP (MARCH 2023) | RIGHT-OF-WAY DRAFT STIP TO FINAL STIP CHANGE | UTILITIES SCHEDULE DRAFT 2024-2033 STIP (AUGUST 2022) | UTILITIES SCHEDULE FINAL 2024-2033 STIP (MARCH 2023) | UTILITIES DRAFT STIP TO FINAL STIP CHANGE | CONSTRUCTION SCHEDULE DRAFT 2024-2033 STIP (AUGUST 2022) | CONSTRUCTION SCHEDULE FINAL 2024-2033 STIP (MARCH 2023) | CONSTRUCTION DRAFT STIP TO FINAL STIP CHANGE | SCHEDULE CHANGE DUE TO DELIVERY (NOT DUE TO FUNDING)? | PROJECT PART OF SWAP?
ALAMANCE | BURLINGTON- ALAMANCE REGIONAL AIRPORT (BUY) | CONSTRUCT 100 FT PAVED OVERRUN AND MAKE SAFETY ENHANCEMENTS. | AVIATION | 7 | BURLINGTON-GRAHAM MPO | AV-5851 | DIVISION 7 | DIVISION 7 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | N/A | N/A | NO CHANGE | N/A | N/A | NO CHANGE | 2024 | 2024 | NO CHANGE
ALAMANCE | LEE AVENUE | WEST LEBANON AVENUE TO SR 1454 (WEST HAGGARD AVENUE) IN ELON. CONSTRUCT SIDEWALK. | BIKE/PED | 7 | BURLINGTON-GRAHAM MPO | EB-5988 | DIVISION 7 | DIVISION 7 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2025 | 2025 | NO CHANGE | N/A | N/A | NO CHANGE | 2026 | 2026 | NO CHANGE
ALAMANCE | I-40 / I-85 | SR 1158 (HUFFMAN MILL ROAD) INTERCHANGE. CONSTRUCT ADDITIONAL LEFT TURN LANE ON I-40 WESTBOUND RAMP AND IMPROVE OPERATIONS AT SR 1308 (GARDEN ROAD) INTERSECTION. | HIGHWAY | 7 | BURLINGTON-GRAHAM MPO | I-6009 | STATEWIDE MOBILITY | STATEWIDE MOBILITY | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE
ALAMANCE | I-40 / I-85 | SR 1981 (TROLLINGWOOD-HAWFIELDS ROAD) IN MEBANE. UPGRADE INTERCHANGE. | HIGHWAY | 7 | BURLINGTON-GRAHAM MPO | I-6059 | DIVISION 7 | DIVISION 7 | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE
ALAMANCE | NC 119 | SR 1981 (TROLLINGWOOD-HAWFIELDS ROAD) / SR 2126 (OLD HILLSBOROUGH ROAD TO LOWES BOULEVARD IN MEBANE. WIDEN TO MULTILANES. | HIGHWAY | 7 | BURLINGTON-GRAHAM MPO | U-6013 | DIVISION 7 | DIVISION 7 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2023 | 2023 | NO CHANGE | 2023 | 2023 | NO CHANGE | 2024 | 2024 | NO CHANGE
ALAMANCE | NC 49 (ROXBORO ROAD) | SR 1928 (WILKINS ROAD) AND SR 1927 (BASON ROAD). UPGRADE K-TYPE INTERSECTION. | HIGHWAY | 7 | BURLINGTON-GRAHAM MPO | U-6183 | DIVISION 7 | DIVISION 7 | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE
ALAMANCE | NC 54 (CHAPEL HILL ROAD) | SR 1445 (SOUTH O'NEAL STREET) IN BURLINGTON. RECONFIGURE INTERSECTION TO MAKE O'NEAL STREET THE THROUGH MOVEMENT WITH NC 54 EAST OF THE INTERSECTION. | HIGHWAY | 7 | BURLINGTON-GRAHAM MPO | U-6184 | DIVISION 7 | DIVISION 7 | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE
ALAMANCE | NC 54 (EAST HARDEN STREET) | SR 1945 (RIVERBEND ROAD) / SR 2431 (JOHNSON STREET) INTERSECTIONIN GRAHAM. INTERSECTION IMPROVEMENTS. | HIGHWAY | 7 | BURLINGTON-GRAHAM MPO | U-6115A | DIVISION 7 | DIVISION 7 | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE
ALAMANCE | NC 54 (EAST HARDEN STREET) | I-40 / I-85 INTERCHANGE IN GRAHAM. UPGRADE RAMP INTERSECTIONS. | HIGHWAY | 7 | BURLINGTON-GRAHAM MPO | U-6115B | REGION D | REGION D | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE
ALAMANCE | NC 54 (EAST HARDEN STREET) | SR 2106 (WOODY DRIVE) IN GRAHAM. INTERSECTION IMPROVEMENTS. | HIGHWAY | 7 | BURLINGTON-GRAHAM MPO | U-6115C | REGION D | REGION D | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE
ALAMANCE | NC 54 (EAST HARDEN STREET) | SR 2106 (WOODY DRIVE) AND SR 2107 (WHITTEMORE ROAD) INTERSECTIONS IN GRAHAM. UPGRADE PIPE CULVERTS 000271 AND 000297. | HIGHWAY | 7 | BURLINGTON-GRAHAM MPO | U-6115D | REGION D | REGION D | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE
ALAMANCE | NC 54 (WEST HARDEN STREET) | NC 49 (MAPLE AVENUE) IN BURLINGTON. INSTALL DUAL LEFT TURN LANES IN WESTBOUND DIRECTION. | HIGHWAY | 7 | BURLINGTON-GRAHAM MPO | U-6131 | REGION D | REGION D | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2025 | 2025 | NO CHANGE | 2025 | 2025 | NO CHANGE | 2026 | 2026 | NO CHANGE
ALAMANCE | NC 62 | SR 1430 (RAMADA ROAD) TO US 70 (CHURCH STREET) IN BURLINGTON. WIDEN TO MULTILANES. | HIGHWAY | 7 | BURLINGTON-GRAHAM MPO | U-5844 | DIVISION 7 | DIVISION 7 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2024 | 2024 | NO CHANGE | 2024 | 2024 | NO CHANGE | 2025 | 2025 | NO CHANGE
ALAMANCE | NC 62 (ALAMANCE ROAD) | SR 1155 (HATCHERY ROAD) / BONNIE LANE INTERSECTION IN BURLINGTON. INSTALL TRAFFIC SIGNAL AND ADD TURN LANES. | HIGHWAY | 7 | BURLINGTON-GRAHAM MPO | U-6114 | REGION D | REGION D | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE
ALAMANCE | NC 87 (WEBB AVENUE) | SR 1515 (FLORA AVENUE). INSTALL TRAFFIC SIGNAL AND ADD TURN LANES. | HIGHWAY | 7 | BURLINGTON-GRAHAM MPO | U-6182 | DIVISION 7 | DIVISION 7 | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE
ALAMANCE | SR 1455 (EAST HAGGARD AVENUE) | NC 87 (WEST WEBB AVENUE) / NC 100 (UNIVERSITY DRIVE) IN ELON. IMPROVE INTERSECTION. | HIGHWAY | 7 | BURLINGTON-GRAHAM MPO | U-6214 | DIVISION 7 | DIVISION 7 | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE
ALAMANCE | SR 1716 (GRAHAM- HOPEDALE ROAD) | SR 1720 (WEST HANOVER ROAD) TO MORNINGSIDE DRIVE IN BURLINGTON. WIDEN TO MULTILANES WITH BICYCLE / PEDESTRIAN ACCOMMODATIONS. | HIGHWAY | 7 | BURLINGTON-GRAHAM MPO | U-6014 | DIVISION 7 | DIVISION 7 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2023 | 2023 | NO CHANGE | 2023 | 2023 | NO CHANGE | 2025 | 2025 | NO CHANGE
ALAMANCE | SR 1716 (NORTH MAIN STREET) | SR 2396 (WEST PARKER STREET) IN GRAHAM. IMPROVE INTERSECTION. | HIGHWAY | 7 | BURLINGTON-GRAHAM MPO | U-6132 | DIVISION 7 | DIVISION 7 | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE
ALAMANCE | US 70 (SOUTH CHURCH STREET) | TARLETON AVENUE TO FIFTH STREET IN BURLINGTON. WIDEN AND CONSTRUCT CENTER TURN LANE. | HIGHWAY | 7 | BURLINGTON-GRAHAM MPO | U-6009 | REGION D | REGION D | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2028 | 2028 | NO CHANGE | 2028 | 2028 | NO CHANGE | 2030 | 2030 | NO CHANGE
ALAMANCE | US 70 (SOUTH CHURCH STREET) | SR 1158 (HUFFMAN MILL ROAD) IN BURLINGTON. INTERSECTION IMPROVEMENTS. | HIGHWAY | 7 | BURLINGTON-GRAHAM MPO | U-6011 | REGION D | REGION D | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2022 | 2022 | NO CHANGE | 2022 | 2022 | NO CHANGE | 2025 | 2025 | NO CHANGE
ALEXANDER | NC 16 | CATAWBA RIVER TO US 64 IN TAYLORSVILLE. UPGRADE AND MODERNIZE TWO-LANE ROADWAY. | HIGHWAY | 12 | GREATER HICKORY MPO | U-6151 | NOT FUNDED | NOT FUNDED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE
ALEXANDER | US 64 | US 64 AND SR 1124. ADD LEFT TURN LANE ON WESTBOUND US 64/NC 90 | HIGHWAY | 12 | GREATER HICKORY MPO | U-6041 | DIVISION 12 | DIVISION 12 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2024 | 2024 | NO CHANGE | 2024 | 2024 | NO CHANGE | 2025 | 2025 | NO CHANGE
ALEXANDER, CATAWBA | NC 127 | SR 1400 (CLONINGER MILL ROAD) TO SR 1156 (RICHEY ROAD). | HIGHWAY | 12 | GREATER HICKORY MPO | R-3603A | DIVISION 12 | DIVISION 12 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2024 | 2024 | NO CHANGE | 2024 | 2024 | NO CHANGE | 2026 | 2026 | NO CHANGE
ANSON | NEW ROUTE - WADESBORO BYPASS | US 52 NORTH OF WADESBORO TO US 74 EAST OF WADESBORO. CONSTRUCT FREEWAY ON NEW LOCATION. | HIGHWAY | 10 | ROCKY RIVER RPO | R-5878B | REGION E | REGION E | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2027 | 2028 | 1 YEAR DELAY | 2027 | 2028 | 1 YEAR DELAY | 2029 | 2030 | 1 YEAR DELAY | YES
ANSON | US 74 | NC 742 (GRAHAM STREET) TO ANSON HIGH SCHOOL ROAD. CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | HIGHWAY | 10 | ROCKY RIVER RPO | R-5871 | STATEWIDE MOBILITY | STATEWIDE MOBILITY | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE
ANSON | US 74 (ANDREW JACKSON HIGHWAY) | GRAHAM STREET TO SR 1749. CONSTRUCT MEDIAN. | HIGHWAY | 10 | ROCKY RIVER RPO | R-5798 | STATEWIDE MOBILITY | STATEWIDE MOBILITY | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2024 | 2025 | 1 YEAR DELAY | 2024 | 2025 | 1 YEAR DELAY | 2026 | 2029 | 3 YEAR DELAY | YES
ANSON | CSX SF LINE | CONSTRUCT SIDING EXTENSION IN POLKTON. | RAIL | 10 | ROCKY RIVER RPO | P-5750A | REGION E | REGION E | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2024 | 2024 | NO CHANGE | N/A | N/A | NO CHANGE | 2024 | 2024 | NO CHANGE
ANSON | CSX SF LINE | SR 1469 (FREEDOM ROAD) INTERSECTION. CONSTRUCT GRADE SEPARATION. | RAIL | 10 | ROCKY RIVER RPO | P-5750B | REGION E | REGION E | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | N/A | N/A | NO CHANGE | N/A | N/A | NO CHANGE | 2026 | 2026 | NO CHANGE
ASHE | NC 88 | NC 88 TO NC 194. UPGRADE ROADWAY. | HIGHWAY | 11 | HIGH COUNTRY RPO | R-5832 | DIVISION 11 | DIVISION 11 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2023 | 2024 | 1 YEAR DELAY | 2023 | 2024 | 1 YEAR DELAY | 2025 | 2025 | NO CHANGE
ASHE | US 221 BUSINESS | NC 194 AND SR 1248 (BEAVER CREEK SCHOOL ROAD) INTERSECTION. CONSTRUCT SUPERSTREET INTERSECTION. | HIGHWAY | 11 | HIGH COUNTRY RPO | R-5833 | NOT FUNDED | NOT FUNDED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE
AVERY | NC 184 | NC 105 TO SR 1342 (HICKORY NUT GAP ROAD) IN BANNER ELK. WIDEN TO MULTI-LANES. | HIGHWAY | 11 | HIGH COUNTRY RPO | R-5902 | NOT FUNDED | NOT FUNDED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE
AVERY, MITCHELL | US 19E | MULTI-LANES EAST OF SPRUCE PINE TO SR 1106. WIDEN TO MULTI-LANES. | HIGHWAY | 11, 13 | HIGH COUNTRY RPO | R-2520A | DIVISION 11, 13 | DIVISION 11, 13 | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE
BEAUFORT | WARREN FIELD (OCW) | ACQUIRE LAND FOR AND CONSTRUCT RUNWAY 5-23 EXTENSION AND TAXIWAY. | AVIATION | 2 | MID-EAST RPO | AV-5743 | DIVISION 2 | DIVISION 2 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2028 | 2028 | NO CHANGE | N/A | N/A | NO CHANGE | 2029 | 2029 | NO CHANGE
BEAUFORT | NC 32 | BRICK KILN ROAD. IMPROVE INTERSECTION. | HIGHWAY | 2 | MID-EAST RPO | R-5897 | NOT FUNDED | NOT FUNDED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE
BEAUFORT | SR 1306 (15TH STREET) | US 17 BUSINESS (CAROLINA AVENUE) TO BROWN STREET. WIDEN TO MULTI-LANES. | HIGHWAY | 2 | MID-EAST RPO | U-5860 | DIVISION 2 | DIVISION 2 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2026 | 2026 | NO CHANGE | 2026 | 2026 | NO CHANGE | 2028 | 2028 | NO CHANGE
BERTIE | NC 45 | US 17 AT MIDWAY TO SOUTHERN CITY LIMITS OF COLERAIN. | HIGHWAY | 1 | PEANUT BELT RPO | R-5809B | DIVISION 1 | DIVISION 1 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2024 | 2025 | 1 YEAR DELAY | 2024 | 2025 | 1 YEAR DELAY | 2026 | 2027 | 1 YEAR DELAY
BLADEN | FIELD (EYF) CURTIS L BROWN JR | EXTEND RUNWAY TO 5500 FEET AND PARALLEL TAXIWAY. | AVIATION | 6 | MID-CAROLINA RPO | AV-5826 | DIVISION 6 | DIVISION 6 | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | N/A | N/A | NO CHANGE | N/A | N/A | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE
BRUNSWICK | NC 211 (NORTH HOWE STREET) | EAST OWEN STREET TO DOSHER HOSPITAL IN SOUTHPORT. CONSTRUCT SIDEWALK. | BIKE/PED | 3 | CAPE FEAR RPO | EB-5982 | DIVISION 3 | DIVISION 3 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2024 | 2024 | NO CHANGE | N/A | N/A | NO CHANGE | 2025 | 2025 | NO CHANGE
BRUNSWICK | NC 211 | SR 1112 (SUNSET HARBOR ROAD) TO NC 906 (MIDWAY ROAD). WIDEN ROADWAY. | HIGHWAY | 3 | CAPE FEAR RPO | R-5947 | NOT FUNDED | NOT FUNDED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE
BRUNSWICK | US 17 | NC 904. CONVERT INTERSECTION TO SUPERSTREET. | HIGHWAY | 3 | GRAND STRAND AREA TRANSPORTATION STUDY | R-5851 | NOT FUNDED | NOT FUNDED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE
BRUNSWICK | US 17 | US 17 BUSINESS SOUTH OF SHALLOTTE AND US 17 BUSINESS NORTH OF SHALLOTTE. CONVERT INTERSECTIONS TO SUPERSTREETS. | HIGHWAY | 3 | GRAND STRAND AREA TRANSPORTATION STUDY | R-5857 | STATEWIDE MOBILITY | STATEWIDE MOBILITY | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2023 | 2023 | NO CHANGE | 2023 | 2023 | NO CHANGE | 2025 | 2026 | 1 YEAR DELAY
BRUNSWICK | US 17 | NC 211. CONVERT INTERSECTION TO INTERCHANGE. | HIGHWAY | 3 | CAPE FEAR RPO, GRAND STRAND AREA TRANSPORTATION STUDY | U-5932 | STATEWIDE MOBILITY | STATEWIDE MOBILITY | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE
BRUNSWICK | US 17 (SHALLOTTE BYPASS) | SR 1357 (SMITH AVENUE). UPGRADE INTERSECTION TO INTERCHANGE. | HIGHWAY | 3 | GRAND STRAND AREA TRANSPORTATION STUDY | U-5862 | REGION B | REGION B | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2028 | 2028 | NO CHANGE | 2028 | 2028 | NO CHANGE | 2030 | 2030 | NO CHANGE
BRUNSWICK | US 17 (SHALLOTTE BYPASS) | US 17 BUSINESS SOUTH (MAIN STREET). UPGRADE EXISTING AT GRADE INTERSECTION TO INTERCHANGE. | HIGHWAY | 3 | GRAND STRAND AREA TRANSPORTATION STUDY | U-6104 | NOT FUNDED | NOT FUNDED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE
BRUNSWICK, NEW HANOVER | SOUTHPORT - FORT FISHER | CONSTRUCT MOORING FACILITIES. | FERRY | 3 | CAPE FEAR RPO, WILMINGTON URBAN AREA MPO | F-5707 | REGION B | REGION B | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | N/A | N/A | NO CHANGE | N/A | N/A | NO CHANGE | 2025 | 2025 | NO CHANGE
BRUNSWICK, NEW HANOVER | SOUTHPORT-FORT FISHER | SOUTHPORT-FORT FISHER FERRY. CONSTRUCT RIVER CLASS FERRY. | FERRY | 3 | CAPE FEAR RPO, WILMINGTON URBAN AREA MPO | F-5705 | NOT FUNDED | NOT FUNDED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | N/A | N/A | NO CHANGE | N/A | N/A | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE
BUNCOMBE | DEAVERVIEW ROAD | US 19/23/74A (PATTON AVENUE) TO WESTMORE DRIVE IN ASHEVILLE. CONSTRUCT SIDEWALK. | BIKE/PED | 13 | FRENCH BROAD RIVER MPO | EB-5965 | DIVISION 13 | DIVISION 13 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2026 | 2026 | NO CHANGE | N/A | N/A | NO CHANGE | 2027 | 2027 | NO CHANGE
BUNCOMBE | MCDOWELL STREET CHOCTAW STREET | SOUTHSIDE AVENUE TO CHOCTAW STREET AT BILTMORE AVENUE. CONSTRUCT PEDESTRIAN IMPROVEMENTS. | BIKE/PED | 13 | FRENCH BROAD RIVER MPO | EB-5919 | DIVISION 13 | DIVISION 13 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2022 | 2022 | NO CHANGE | 2022 | 2022 | NO CHANGE | 2024 | 2024 | NO CHANGE
BUNCOMBE | NORTH RAD GREENWAY | CONSTRUCT MULTI-USE PATH ALONG RIVERSIDE DRIVE FROM HILL STREET TO US 19/23/70 AT BROADWAY | BIKE/PED | 13 | FRENCH BROAD RIVER MPO | EB-5822 | DIVISION 13 | DIVISION 13 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2023 | 2023 | NO CHANGE | N/A | N/A | NO CHANGE | 2025 | 2025 | NO CHANGE
BUNCOMBE | ASHEVILLE | US 19 (PATTON AVENUE) AND NC 63 (NEW LEICESTER HIGHWAY). CONSTRUCT FINAL INTERSECTION IMPROVEMENTS. | HIGHWAY | 13 | FRENCH BROAD RIVER MPO | U-5971B | NOT FUNDED | NOT FUNDED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE
BUNCOMBE | ASHEVILLE | NC 63 (NEW LEICESTER HIGHWAY), US 19/23 (PATTON AVENUE) TO NEWFOUND ROAD. CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | HIGHWAY | 13 | FRENCH BROAD RIVER MPO | U-5972 | NOT FUNDED | NOT FUNDED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE
BUNCOMBE | I-26 (US 19/US 23) | SR 1781 (BROADWAY STREET) TO US 25/70 | HIGHWAY | 13 | FRENCH BROAD RIVER MPO | A-0010AA | REGION G | REGION G | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2028 | 2028 | NO CHANGE | 2028 | 2028 | NO CHANGE | 2031 | 2031 | NO CHANGE
BUNCOMBE | I-26/I-240 | NORTH OF I-40 TO SR 3548 (HAYWOOD ROAD). WIDEN TO SIX LANE FREEWAY. | HIGHWAY | 13 | FRENCH BROAD RIVER MPO | I-2513AC | REGION G | REGION G | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2023 | 2023 | NO CHANGE | 2023 | 2023 | NO CHANGE | 2024 | 2024 | NO CHANGE
BUNCOMBE | I-26/I-240 | I-26/I-40/I-240 FINAL INTERCHANGE IMPROVEMENTS | HIGHWAY | 13 | FRENCH BROAD RIVER MPO | I-2513C | STATEWIDE MOBILITY | STATEWIDE MOBILITY | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE
BUNCOMBE | I-40 | I-40/SR 1228 (LIBERTY ROAD). CONVERT GRADE SEPARATION TO AN INTERCHANGE AND CONSTRUCT TWO LANE ROADWAY NORTH OF I-40 TO SR 1224 AND FOUR LANE ROADWAY SOUTH OF I-40 TO US 19/US 23/NC 151 WITH PARTS ON NEW LOCATION. | HIGHWAY | 13 | FRENCH BROAD RIVER MPO | I-4759 | STATEWIDE MOBILITY | STATEWIDE MOBILITY | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | UNDERWAY | UNDERWAY | NO CHANGE | UNDERWAY | UNDERWAY | NO CHANGE | 2025 | 2026 | 1 YEAR DELAY
BUNCOMBE | I-40 | I-240 / US 74 ALTERNATE INTERCHANGE. IMPROVE INTERCHANGE. | HIGHWAY | 13 | FRENCH BROAD RIVER MPO | I-6018 | NOT FUNDED | NOT FUNDED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE
BUNCOMBE | I-40 | SR 2838 (PORTERS COVE ROAD) INTERCHANGE. IMPROVE INTERCHANGE. | HIGHWAY | 13 | FRENCH BROAD RIVER MPO | I-6021 | NOT FUNDED | NOT FUNDED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE
BUNCOMBE | I-40 | SR 1200 (WIGGINS ROAD) TO SR 1224 (MONTE VISTA ROAD). ADD ADDITIONAL LANES. | HIGHWAY | 13 | FRENCH BROAD RIVER MPO | I-6054C | NOT FUNDED | NOT FUNDED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE
BUNCOMBE | I-40, I-26 | SR 3548 (HAYWOOD ROAD) TO US 19/23 AT SR 1781 (BROADWAY) | HIGHWAY | 13 | FRENCH BROAD RIVER MPO | I-2513B | STATEWIDE MOBILITY | STATEWIDE MOBILITY | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2024 | 2024 | NO CHANGE | 2024 | 2024 | NO CHANGE | 2024 | 2024 | NO CHANGE
BUNCOMBE | NC 112 (SARDIS ROAD/ SANDHILL ROAD) | NC 191 (BREVARD ROAD) TO US 19/23 (SMOKEY PARK HIGHWAY). WIDEN ROADWAY. | HIGHWAY | 13 | FRENCH BROAD RIVER MPO | U-6047 | DIVISION 13 | DIVISION 13 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2025 | 2028 | 3 YEAR DELAY | 2025 | 2028 | 3 YEAR DELAY | 2028 | 2031 | 3 YEAR DELAY
BUNCOMBE | NC 191 (BREVARD ROAD - OLD HAYWOOD ROAD) | SR 3498 (LEDBETTER ROAD) TO NORTH OF BLUE RIDGE PARKWAY. | HIGHWAY | 13 | FRENCH BROAD RIVER MPO | U-3403B | NOT FUNDED | NOT FUNDED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE
BUNCOMBE | NC 81 (SWANNANOA RIVER ROAD) | SR 3214 (BILTMORE AVENUE) TO US 74A (SOUTH TUNNEL ROAD). WIDEN EXISTING ROADWAY. | HIGHWAY | 13 | FRENCH BROAD RIVER MPO | U-5832 | DIVISION 13 | DIVISION 13 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2028 | 2028 | NO CHANGE | 2028 | 2028 | NO CHANGE | 2030 | 2030 | NO CHANGE
BUNCOMBE | NC 81 (SWANNANOA RIVER ROAD) | US 70 (TUNNEL ROAD) TO US 74 (SOUTH TUNNEL ROAD). UPGRADE ROADWAY. | HIGHWAY | 13 | FRENCH BROAD RIVER MPO | U-6046 | DIVISION 13 | DIVISION 13 | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE
BUNCOMBE | RIVERWAY MULTI-MODAL NETWORK | CRAVEN STREET BRIDGE IMPROVEMENTS OVER THE FRENCH BROAD RIVER | HIGHWAY | 13 | FRENCH BROAD RIVER MPO | U-5019E | DIVISION 13 | DIVISION 13 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | N/A | N/A | NO CHANGE | N/A | N/A | NO CHANGE | 2024 | 2024 | NO CHANGE
BUNCOMBE | SR 1332 (NORTH LOUISIANA AVENUE) | US 19/23 (PATTON AVENUE) TO SR 1338 (EMMA ROAD). MODERNIZE ROADWAY. | HIGHWAY | 13 | FRENCH BROAD RIVER MPO | U-6162 | DIVISION 13 | DIVISION 13 | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE
BUNCOMBE | SR 1477 (RIVERSIDE DRIVE) | SR 1517 (HILL STREET) TO SR 1781 (BROADWAY STREET) | HIGHWAY | 13 | FRENCH BROAD RIVER MPO | I-2513D | DIVISION 13 | DIVISION 13 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2024 | 2024 | NO CHANGE | 2024 | 2024 | NO CHANGE | 2024 | 2024 | NO CHANGE
BUNCOMBE | SR 2002 (RICEVILLE ROAD) | US 70 (TUNNEL ROAD) TO SR 2285 (CLEAR VISTA LANE). UPGRADE ROADWAY. | HIGHWAY | 13 | FRENCH BROAD RIVER MPO | U-5837 | DIVISION 13 | DIVISION 13 | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE
BUNCOMBE | SR 2500 (BLUE RIDGE ROAD) | CONVERT I-40/SR 2500 (BLUE RIDGE ROAD) GRADE SEPARATION TO INTERCHANGE. WIDEN SR 2500 (BLUE RIDGE ROAD) TO THREE LANES FROM US 70 TO SOUTH OF I-40 AND UPGRADE ROADWAY SOUTH OF I-40 TO SR 2713. | HIGHWAY | 13 | FRENCH BROAD RIVER MPO | I-4409 | DIVISION 13 | DIVISION 13 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2023 | 2023 | NO CHANGE | 2023 | 2023 | NO CHANGE | 2025 | 2025 | NO CHANGE
BUNCOMBE | SR 3116 (MILLS GAP ROAD) | US 25 (HENDERSONVILLE ROAD) TO SR 3157 (WESTON ROAD). UPGRADE EXISTING ROADWAY. | HIGHWAY | 13 | FRENCH BROAD RIVER MPO | U-5834 | DIVISION 13 | DIVISION 13 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | UNDERWAY | UNDERWAY | NO CHANGE | UNDERWAY | UNDERWAY | NO CHANGE | 2024 | 2024 | NO CHANGE
BUNCOMBE | SR 3116 (MILLS GAP ROAD) | SR 3136 (CANE CREEK ROAD) INTERSECTION. CONSTRUCT ROUNDABOUT. | HIGHWAY | 13 | FRENCH BROAD RIVER MPO | U-6163 | DIVISION 13 | DIVISION 13 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2024 | 2024 | NO CHANGE | 2024 | 2024 | NO CHANGE | 2024 | 2024 | NO CHANGE
BUNCOMBE | SR 3556 (AMBOYROAD/ MEADOW ROAD) | I-240 TO NC 81/SR 3214 (BILTMORE AVENUE). WIDEN TO MULTI-LANES WITH NEW BRIDGE OVER THE FRENCH BROAD RIVER. | HIGHWAY | 13 | FRENCH BROAD RIVER MPO | U-4739 | DIVISION 13 | DIVISION 13 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2025 | 2025 | NO CHANGE | 2025 | 2025 | NO CHANGE | 2028 | 2028 | NO CHANGE
BUNCOMBE | US 25A (SWEETEN CREEK ROAD) | US 25 (HENDERSONVILLE ROAD) TO SR 3116 (MILLS GAP ROAD) | HIGHWAY | 13 | FRENCH BROAD RIVER MPO | U-2801AA | REGION G | REGION G | SCHEDULED FOR DELIVERY | WILL BE REPRIORITIZED | 2028 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | PROJECT UNCOMMITTED | 2028 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | PROJECT UNCOMMITTED | 2031 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | PROJECT UNCOMMITTED
BUNCOMBE | US 25A (SWEETEN CREEK ROAD) | SR 3116 (MILLS GAP ROAD) TO SR 3081 (ROCK HILL ROAD) | HIGHWAY | 13 | FRENCH BROAD RIVER MPO | U-2801AB | REGION G | REGION G | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2028 | 2028 | NO CHANGE | 2028 | 2028 | NO CHANGE | 2031 | 2031 | NO CHANGE
BUNCOMBE | WEAVERVILLE | US 19 BUSINESS (WEAVERVILLE HIGHWAY) AND SR 1740 (NEW STOCK ROAD). CONSTRUCT INTERSECTION IMPROVEMENTS. | HIGHWAY | 13 | FRENCH BROAD RIVER MPO | U-5973 | NOT FUNDED | NOT FUNDED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE
BUNCOMBE, MADISON | US 25/70 | NORTH OF SR 1584 (TILLERY BRANCH ROAD) TO SR 1727 (MONTICELLO ROAD). UPGRADE ROADWAY TO SUPERSTREET. | HIGHWAY | 13 | FRENCH BROAD RIVER MPO, LAND-OF-SKY RPO | U-6173 | NOT FUNDED | NOT FUNDED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE
BURKE | COLLEGE STREET MULTIMODAL CONNECTOR | NORTH GREEN STREET TO US 70 IN MORGANTON. CONSTRUCT MULTI-USE PATH. | BIKE/PED | 13 | GREATER HICKORY MPO | EB-5978 | DIVISION 13 | DIVISION 13 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2022 | 2022 | NO CHANGE | N/A | N/A | NO CHANGE | 2024 | 2024 | NO CHANGE
BURKE | I-40 | SR 1734 (CAROLINA STREET SE)/SR 1826 - EXIT 111. REVISE INTERCHANGE. | HIGHWAY | 13 | GREATER HICKORY MPO | I-5008 | REGION G | REGION G | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE
BURKE | I-40 | US 64 (BURKEMONT ROAD). IMPROVE INTERCHANGE. | HIGHWAY | 13 | GREATER HICKORY MPO | I-5009 | REGION G | REGION G | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE
BURKE | I-40 | SR 1142 (JAMESTOWN ROAD) - EXIT 100. UPGRADE INTERCHANGE. | HIGHWAY | 13 | GREATER HICKORY MPO | I-5874 | REGION G | REGION G | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE
BURKE | I-40 | SR 1712 (DREXEL ROAD). UPGRADE INTERCHANGE. | HIGHWAY | 13 | GREATER HICKORY MPO | I-5875 | REGION G | REGION G | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE
BURKE | I-40 | SR 1761 (OLD HIGHWAY NC 10) - EXIT 116. UPGRADE INTERCHANGE AND REMOVE TWO-WAY TRAFFIC. | HIGHWAY | 13 | GREATER HICKORY MPO | I-5971 | STATEWIDE MOBILITY | STATEWIDE MOBILITY | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE
BURKE | I-40 | SR 1744 (MINERAL SPRINGS MOUNTAIN ROAD)/SR 1744 (ELDRED STREET SE) - EXIT 112. CONSTRUCT INTERCHANGE IMPROVEMENTS. | HIGHWAY | 13 | GREATER HICKORY MPO | I-5975 | NOT FUNDED | NOT FUNDED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE
BURKE | I-40 | EXIT 118 - SR 1761 (OLD NC 10). CONTRUCT INTERCHANGE IMPROVEMENTS. | HIGHWAY | 13 | GREATER HICKORY MPO | I-5990 | DIVISION 13 | DIVISION 13 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2023 | 2023 | NO CHANGE | 2023 | 2023 | NO CHANGE | 2024 | 2024 | NO CHANGE
BURKE | I-40 | SR 1147 (CAUSBY ROAD). REDESIGN INTERCHANGE AND REMOVE TWO-WAY ON RAMP. | HIGHWAY | 13 | GREATER HICKORY MPO | I-6058 | NOT FUNDED | NOT FUNDED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE
BURKE | NC 126 | SR 1250 (WATERMILL ROAD) TO SR 1254 (FISH HATCHERY ROAD). MODERNIZE ROADWAY. | HIGHWAY | 13 | GREATER HICKORY MPO | U-6164 | NOT FUNDED | NOT FUNDED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE
BURKE | NC 181 | SR 1414 (ST MARY'S CHURCH ROAD) TO MORGANTON ETJ. WIDEN EXISTING ROADWAY. | HIGHWAY | 13 | GREATER HICKORY MPO | U-5836 | REGION G | REGION G | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2027 | 2027 | NO CHANGE | N/A | N/A | NO CHANGE | 2029 | 2029 | NO CHANGE
BURKE | NC 181 | SR 1440 TO SR 1419. WIDEN TO 3-LANES. | HIGHWAY | 13 | GREATER HICKORY MPO | U-5978 | NOT FUNDED | NOT FUNDED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE
BURKE | US 64 (BURKEMONT AVENUE) | US 70 (W. FLEMING DRIVE) INTERSECTION. IMPROVE INTERSECTION. | HIGHWAY | 13 | GREATER HICKORY MPO | U-6123 | NOT FUNDED | NOT FUNDED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE
CABARRUS | CONCORD REGIONAL AIRPORT (JQF) | SOUTH DEVELOPMENT AREA APRON EXPANSION - PHASE II: APRON EXPANSION (DESIGN & CONSTRUCTION) | AVIATION | 10 | CABARRUS-ROWAN MPO | AV-5731 | REGION E | REGION E | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | N/A | N/A | NO CHANGE | N/A | N/A | NO CHANGE | 2025 | 2025 | NO CHANGE
CABARRUS | CONCORD REGIONAL AIRPORT (JQF) | EXTEND RUNWAY SAFETY AREA. | AVIATION | 10 | CABARRUS-ROWAN MPO | AV-5889 | NOT FUNDED | NOT FUNDED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | N/A | N/A | NO CHANGE | N/A | N/A | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE
CABARRUS | CONCORD REGIONAL AIRPORT (JQF) | CONSTRUCT NORTH APRON EXPANSION. | AVIATION | 10 | CABARRUS-ROWAN MPO | AV-5892 | REGION E | REGION E | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | N/A | N/A | NO CHANGE | N/A | N/A | NO CHANGE | 2023 | 2023 | NO CHANGE
CABARRUS | BRUTON SMITH BLVD/ CONCORD MILLS BLVD/ PORTION OF | US 29 TO WEDDINGTON ROAD. CONSTRUCT SIDEWALK ON BOTH SIDES OF THE ROAD, INCLUDING A PORTION OF WEDDINGTON ROAD. | BIKE/PED | 10 | CABARRUS-ROWAN MPO | EB-5732 | DIVISION 10 | DIVISION 10 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2023 | 2023 | NO CHANGE | N/A | N/A | NO CHANGE | 2024 | 2024 | NO CHANGE
CABARRUS | KANNAPOLIS | LITTLE TEXAS ROAD, LANE STREET TO DALE EARNHARDT BOULEVARD. CONSTRUCT SIDEWALK AND CURB AND GUTTER. | BIKE/PED | 10 | CABARRUS-ROWAN MPO | EB-5844 | DIVISION 10 | DIVISION 10 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2023 | 2023 | NO CHANGE | N/A | N/A | NO CHANGE | 2024 | 2024 | NO CHANGE
CABARRUS | GEORGE LILES PARKWAY | NC 49 TO SR 1304 (ROBERTA ROAD) | HIGHWAY | 10 | CABARRUS-ROWAN MPO | R-2246A | DIVISION 10 | DIVISION 10 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2028 | 2028 | NO CHANGE | 2028 | 2028 | NO CHANGE | 2030 | 2030 | NO CHANGE
CABARRUS | NC 3 (DALE EARNHARDT BOULEVARD) | INTERSECTION OF NC 3 (DALE EARNHARDT BOULEVARD) AND US 29/601 (CANNON BOULEVARD). CONSTRUCT INTERSECTION IMPROVEMENTS. | HIGHWAY | 10 | CABARRUS-ROWAN MPO | U-5761 | REGION E | REGION E | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | UNDERWAY | UNDERWAY | NO CHANGE | UNDERWAY | UNDERWAY | NO CHANGE | 2024 | 2024 | NO CHANGE
CABARRUS | NC 73 (DAVIDSON HIGHWAY) | EAST OF SR 1394 (POPLAR TENT ROAD) TO US 29. | HIGHWAY | 10 | CABARRUS-ROWAN MPO | R-5706B | REGION E | REGION E | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE
CABARRUS | SR 1394 (POPLAR TENT ROAD) | EAST OF I-85 TO GEORGE LILES PARKWAY | HIGHWAY | 10 | CABARRUS-ROWAN MPO | U-3415A | DIVISION 10 | DIVISION 10 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2024 | 2025 | 1 YEAR DELAY | 2024 | 2025 | 1 YEAR DELAY | 2027 | 2028 | 1 YEAR DELAY | YES
CABARRUS | US 29 | REALIGN UNION CEMETERY ROAD TO INTERSECT US 29 AT ROCK HILL CHURCH ROAD AND CONSTRUCT IMPROVEMENTS ALONG US 29 FROM 0.6 MILE WEST OF ROCK HILL CHURCH ROAD TO JUST EAST OF ROCK HILL CHURCH ROAD. | HIGHWAY | 10 | CABARRUS-ROWAN MPO | U-5956 | REGION E | REGION E | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2022 | 2022 | NO CHANGE | 2022 | 2022 | NO CHANGE | 2025 | 2025 | NO CHANGE
CABARRUS, MECKLENBURG | POPLAR TENT ROAD | DERITA ROAD TO NC 73. WIDEN TO FOUR-LANES. | HIGHWAY | 10 | CABARRUS-ROWAN MPO, CHARLOTTE REGIONAL TPO | U-6029 | NOT FUNDED | NOT FUNDED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE
CALDWELL | SR 1001 (CONNELLY SPRINGS ROAD) | CATAWBA RIVER TO SR 1933 (SOUTH-WEST BOULEVARD) | HIGHWAY | 11 | GREATER HICKORY MPO | R-3430C | DIVISION 11 | DIVISION 11 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2026 | 2028 | 2 YEAR DELAY | 2026 | 2028 | 2 YEAR DELAY | 2029 | 2031 | 2 YEAR DELAY
CALDWELL | SR 1130 (CAJAH MOUNTAIN ROAD) | SR 1001 (CONNELLY SPRINGS ROAD) TO US 321A. MODERNIZE ROADWAY. | HIGHWAY | 11 | GREATER HICKORY MPO | U-6157 | DIVISION 11 | DIVISION 11 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2023 | 2023 | NO CHANGE | 2023 | 2023 | NO CHANGE | 2025 | 2025 | NO CHANGE
CALDWELL | US 321 | SR 1002 (DUDLEY SHOALS ROAD) GRADE SEPARATION. CONSTRUCT RAMP ONTO US 321 SOUTHBOUND. | HIGHWAY | 11 | GREATER HICKORY MPO | U-6161 | DIVISION 11 | DIVISION 11 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2026 | 2025 | 1 YEAR ACCELERATION | 2026 | 2025 | 1 YEAR ACCELERATION | 2028 | 2027 | 1 YEAR ACCELERATION
CALDWELL | US 321 ALT | SR 1109 (PINEWOOD ROAD) TO SR 1106 (DUKE STREET). UPGRADE ROADWAY. | HIGHWAY | 11 | GREATER HICKORY MPO | U-6034 | DIVISION 11 | DIVISION 11 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2024 | 2024 | NO CHANGE | 2024 | 2024 | NO CHANGE | 2026 | 2026 | NO CHANGE
CAMDEN | NC 343 | US 158 IN CAMDEN TO SR 1119 (SOUTH TROTMAN ROAD) IN SHILOH. MODERNIZE ROADWAY AND REPLACE BRIDGES 140017 AND 140018 IN CAMDEN COUNTY. | HIGHWAY | 1 | ALBEMARLE RPO | R-5807 | DIVISION 1 | DIVISION 1 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2024 | 2024 | NO CHANGE | 2024 | 2024 | NO CHANGE | 2026 | 2027 | 1 YEAR DELAY
CAMDEN, CURRITUCK | SR 1227/SR 1208 (SOUTH MILLS ROAD) SR 1224/SR 1223 | NC 343 IN CAMDEN COUNTY TO NC 168 IN CURRITUCK COUNTY. WIDEN AND INTERSECTION IMPROVEMENTS. | HIGHWAY | 1 | ALBEMARLE RPO | R-5717 | DIVISION 1 | DIVISION 1 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | UNDERWAY | UNDERWAY | NO CHANGE | UNDERWAY | UNDERWAY | NO CHANGE | 2024 | 2024 | NO CHANGE
CARTERET | NC 24 | NC 58. INTERSECTION IMPROVEMENTS. | HIGHWAY | 2 | DOWN EAST RPO | R-5858 | STATEWIDE MOBILITY | STATEWIDE MOBILITY | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | UNDERWAY | UNDERWAY | NO CHANGE | UNDERWAY | UNDERWAY | NO CHANGE | 2025 | 2026 | 1 YEAR DELAY
CARTERET | NC 58 (EMERALD DRIVE) | LOON STREET. INSTALL ROUNDABOUT. | HIGHWAY | 2 | DOWN EAST RPO | R-5884 | NOT FUNDED | NOT FUNDED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE
CARTERET | NC 58 (EMERALD DRIVE) | SR 1000 (COAST GUARD ROAD). INSTALL ROUNDABOUT. | HIGHWAY | 2 | DOWN EAST RPO | R-5886 | NOT FUNDED | NOT FUNDED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE
CARTERET | NC 58 (EMERALD DRIVE) | MANGROVE DRIVE. UPGRADE INTERSECTION. | HIGHWAY | 2 | DOWN EAST RPO | R-5944 | DIVISION 2 | DIVISION 2 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2027 | 2027 | NO CHANGE | 2027 | 2027 | NO CHANGE | 2029 | 2029 | NO CHANGE
CARTERET | SR 1175 (BRIDGES STREET) | SR 1243 (BARBOUR ROAD). REALIGN INTERSECTIONS. | HIGHWAY | 2 | DOWN EAST RPO | R-5941 | DIVISION 2 | DIVISION 2 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2027 | 2027 | NO CHANGE | 2027 | 2027 | NO CHANGE | 2029 | 2029 | NO CHANGE
CARTERET | SR 1176 (BRIDGES STREET EXTENSION) | SR 1738 (BRIDGES STREET) TO SR 1147 (MCCABE ROAD). WIDEN EXISTING ROADWAY AND CONSTRUCT PART ON NEW LOCATION. | HIGHWAY | 2 | DOWN EAST RPO | R-5727 | DIVISION 2 | DIVISION 2 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2027 | 2027 | NO CHANGE | 2027 | 2027 | NO CHANGE | 2029 | 2029 | NO CHANGE
CARTERET | US 70 (ARENDELL STREET) | 4TH STREET TO SR 1175 (RADIO ISLAND ROAD). WIDEN TO MULTI-LANES. | HIGHWAY | 2 | DOWN EAST RPO | U-5876 | STATEWIDE MOBILITY | STATEWIDE MOBILITY | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE
CARTERET | US 70 (CEDAR STREET) | US 70 (LIVE OAK STREET). CONSTRUCT ROUNDABOUT. | HIGHWAY | 2 | DOWN EAST RPO | R-5962 | NOT FUNDED | NOT FUNDED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE
CARTERET | US 70 (LIVE OAK STREET) | NC 101 TO SR 1429 (OLGA ROAD). ACCESS MANAGEMENT. | HIGHWAY | 2 | DOWN EAST RPO | R-5945 | DIVISION 2 | DIVISION 2 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2027 | 2027 | NO CHANGE | 2027 | 2027 | NO CHANGE | 2029 | 2029 | NO CHANGE
CARTERET | US 70 (LIVE OAK STREET) | SR 1310 (LENNOXVILLE ROAD). UPGRADE INTERSECTION. | HIGHWAY | 2 | DOWN EAST RPO | R-5946 | DIVISION 2 | DIVISION 2 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2027 | 2027 | NO CHANGE | 2027 | 2027 | NO CHANGE | 2029 | 2029 | NO CHANGE
CARTERET | US 70 (LIVE OAK STREET) | NC 101. CONSTRUCT ONE LANE ROUNDABOUT. | HIGHWAY | 2 | DOWN EAST RPO | U-6058 | REGION B | REGION B | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2023 | 2023 | NO CHANGE | 2023 | 2023 | NO CHANGE | 2025 | 2025 | NO CHANGE
CARTERET | US 70/NC 12 | SR 1429 (OLGA ROAD) TO SR 1350 (WHITEHURST ROAD). UPGRADE ROADWAY. | HIGHWAY | 2 | DOWN EAST RPO | R-4746 | NOT FUNDED | NOT FUNDED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE
CARTERET | NS/NCRR EC LINE | CONSTRUCT GRADE SEPARATION AT US 70 EASTBOUND AND WESTBOUND. CLOSE EXISTING AT-GRADE CROSSING NEAR NEWPORT. | RAIL | 2 | DOWN EAST RPO | P-5742 | NOT FUNDED | NOT FUNDED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE
CARTERET, HYDE | NC 12 | CEDAR ISLAND - OCRACOKE FERRY. REPLACE M/V SILVER LAKE SOUND CLASS FERRY | FERRY | 1, 2 | ALBEMARLE RPO, DOWN EAST RPO | F-5704 | DIVISION 1, 2 | DIVISION 1, 2 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | N/A | N/A | NO CHANGE | N/A | N/A | NO CHANGE | 2025 | 2025 | NO CHANGE
CASWELL | NC 86 | US 158 TO VIRGINIA STATE LINE. CONSTRUCT PASSING LANES AND SHOULDER IMPROVEMENTS AT VARIOUS LOCATIONS, AND CONSTRUCT TURN LANES FROM SR 1300 (PARK SPRINGS ROAD) TO SOLID WASTE CONVENIENCE CENTER. | HIGHWAY | 7 | PIEDMONT TRIAD RPO | R-5822 | REGION D | REGION D | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE
CASWELL | US 158 / NC 86 | SR 1572 (COUNTY HOME ROAD) TO SR 1734 (RP FUQUAY ROAD). CONSTRUCT PASSING LANES. | HIGHWAY | 7 | PIEDMONT TRIAD RPO | R-5926 | DIVISION 7 | DIVISION 7 | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE
CATAWBA | HICKORY REGIONAL AIRPORT (HKY) | 600 FEET EXTENSION OF RUNWAY 6 - PHASE I AND II. | AVIATION | 12 | GREATER HICKORY MPO | AV-5741 | DIVISION 12 | DIVISION 12 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | N/A | N/A | NO CHANGE | N/A | N/A | NO CHANGE | 2024 | 2024 | NO CHANGE
CATAWBA | HICKORY REGIONAL AIRPORT (HKY) | LAND ACQUISITION AND OBSTRUCTION REMOVAL. | AVIATION | 12 | GREATER HICKORY MPO | AV-5752 | DIVISION 12 | DIVISION 12 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2026 | 2026 | NO CHANGE | N/A | N/A | NO CHANGE | N/A | N/A | NO CHANGE
CATAWBA | HICKORY | SR 1453 (SPRINGS ROAD) TO NC 127 | HIGHWAY | 12 | GREATER HICKORY MPO | U-2307B | DIVISION 12 | DIVISION 12 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2025 | 2025 | NO CHANGE | 2025 | 2025 | NO CHANGE | 2028 | 2028 | NO CHANGE
CATAWBA | I-40 | SR 1007 (LENOIR RHYNE BOULEVARD) INTERCHANGE. CONSTRUCT INTERCHANGE IMPROVEMENTS. | HIGHWAY | 12 | GREATER HICKORY MPO | I-5716 | STATEWIDE MOBILITY | STATEWIDE MOBILITY | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | UNDERWAY | UNDERWAY | NO CHANGE | UNDERWAY | UNDERWAY | NO CHANGE | 2025 | 2026 | 1 YEAR DELAY
CATAWBA | I-40 | US 321 TO SR 1476 (FAIRGROVE CHURCH ROAD). WIDEN TO SIX LANES. | HIGHWAY | 12 | GREATER HICKORY MPO | I-5991A | STATEWIDE MOBILITY | STATEWIDE MOBILITY | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | N/A | N/A | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE
CATAWBA | NC 127 | SR 1132 (HUFFMAN FARM ROAD) TO SR 1008 (ZION CHURCH ROAD). | HIGHWAY | 12 | GREATER HICKORY MPO | U-2530A | DIVISION 12 | DIVISION 12 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2025 | 2025 | NO CHANGE | 2025 | 2025 | NO CHANGE | 2027 | 2027 | NO CHANGE
CATAWBA | NC 127 (2ND STREET NORTHEAST, NORTH CENTER STREET) | 8TH AVENUE NORTHEAST TO SR 1327 (30TH AVENUE NORTHWEST). CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | HIGHWAY | 12 | GREATER HICKORY MPO | U-6135 | NOT FUNDED | NOT FUNDED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE
CATAWBA | SR 1005 (STARTOWN ROAD) | US 70 TO NC 10. WIDEN TO MULTI-LANES. | HIGHWAY | 12 | GREATER HICKORY MPO | R-5113 | DIVISION 12 | DIVISION 12 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2028 | 2028 | NO CHANGE | 2028 | 2028 | NO CHANGE | 2031 | 2031 | NO CHANGE
CATAWBA | SR 1124 (33RD STREET SW) | SR 1124 (33RD STREET SW) AND (34TH STREET NW). REALIGN INTERSECTION. | HIGHWAY | 12 | GREATER HICKORY MPO | U-6042 | DIVISION 12 | DIVISION 12 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2027 | 2027 | NO CHANGE | 2027 | 2027 | NO CHANGE | 2029 | 2029 | NO CHANGE
CATAWBA | SR 1453 (16TH STREET NE, 12TH AVE NE, SPRINGS ROAD | 9TH AVENUE NE TO SR 1504 (CHARLOTTE STREET). CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | HIGHWAY | 12 | GREATER HICKORY MPO | U-6176 | DIVISION 12 | DIVISION 12 | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE
CATAWBA, CALDWELL, BURKE | US 321 | NORTH OF US 70 IN HICKORY TO US 321A | HIGHWAY | 11, 12, 13 | GREATER HICKORY MPO | U-4700A | STATEWIDE MOBILITY | STATEWIDE MOBILITY | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | UNDERWAY | UNDERWAY | NO CHANGE | UNDERWAY | UNDERWAY | NO CHANGE | 2025 | 2026 | 1 YEAR DELAY
CATAWBA, LINCOLN | NC 150 | RELOCATED NC 16 (STIP PROJECT R-2206) TO EAST OF SR 1840 (GREENWOOD ROAD). WIDEN TO 4-LANES WITH A BYPASS OF THE TERRELL HISTORIC DISTRICT. | HIGHWAY | 12 | GREATER HICKORY MPO, GASTON-CLEVELAND-LINCOLN MPO | R-2307A | REGION F | REGION F | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2027 | 2027 | NO CHANGE | 2027 | 2027 | NO CHANGE | 2030 | 2030 | NO CHANGE
CHATHAM | SILER CITY MUNICIPAL AIRPORT (SCR) | EXTEND RUNWAY 22 AND PARALLEL TAXIWAY BY 500 FT, INCLUDING RELOCATION OF AIRPORT ROAD | AVIATION | 8 | TRIANGLE AREA RPO | AV-5816 | DIVISION 8 | DIVISION 8 | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE
CHATHAM | SR 1107 (WEST 3RD STREET) | NORTH GARDEN AVENUE TO SR 1108 (NORTH CHATHAM AVENUE) IN SILER CITY. CONSTRUCT SIDEWALK. | BIKE/PED | 8 | TRIANGLE AREA RPO | EB-6006 | DIVISION 8 | DIVISION 8 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2024 | 2024 | NO CHANGE | N/A | N/A | NO CHANGE | 2026 | 2026 | NO CHANGE
CHATHAM | SR 2106 (EAST CARDINAL STREET); SOUTH 10TH AVENUE | SR 2016 (EAST CARDINAL STREET) FROM SR 2223 (MATTHEWS STREET) TO SOUTH 10TH AVENUE, AND SOUTH 10TH AVENUE FROM EAST CARDINAL STREET TO SR 2103 (EAST RALEIGH STREET) IN SILER CITY. CONSTRUCT SIDEWALK. | BIKE/PED | 8 | TRIANGLE AREA RPO | EB-6007 | NOT FUNDED | NOT FUNDED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE
CHATHAM | NC 87 | NC 902 IN PITTSBORO TO US 64 BYPASS. WIDEN TO 12-FT LANES AND 4-FT PAVED SHOULDERS. | HIGHWAY | 8 | TRIANGLE AREA RPO | R-5961 | NOT FUNDED | NOT FUNDED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE
CHATHAM | NEW ROUTE | US 64 BYPASS IN PITTSBORO TO US 15 / US 501. CONSTRUCT ROADWAY ON NEW LOCATION. | HIGHWAY | 8 | TRIANGLE AREA RPO | R-5930 | DIVISION 8 | DIVISION 8 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2023 | 2023 | NO CHANGE | 2023 | 2023 | NO CHANGE | 2024 | N/A | NO CHANGE
CHATHAM | NEW ROUTE | NORTHERN TERMINUS OF EXISTING CHATHAM PARK WAY JUST NORTH OF US 64 TO NORTH OF PROPOSED GRANT DRIVE. CONSTRUCT ROADWAY ON NEW LOCATION. | HIGHWAY | 8 | TRIANGLE AREA RPO | R-5930A | DIVISION 8 | DIVISION 8 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2023 | 2023 | NO CHANGE | 2023 | 2023 | NO CHANGE | 2024 | 2024 | NO CHANGE
CHATHAM | NEW ROUTE | NORTH OF PROPOSED GRANT DRIVE TO US 15/ US 501. CONSTRUCT ROADWAY ON NEW LOCATION. | HIGHWAY | 8 | TRIANGLE AREA RPO | R-5930B | DIVISION 8 | DIVISION 8 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2023 | 2023 | NO CHANGE | 2023 | 2023 | NO CHANGE | 2024 | 2024 | NO CHANGE
CHATHAM | NEW ROUTE | US 15 / US 501 SOUTH OF PITTSBORO TO SR 1012 (MONCURE-PITTSBORO ROAD). CONSTRUCT 2-LANE ROADWAY ON NEW LOCATION. TOWN OF PITTSBORO DELIVERING PROJECT (ROW 2023, CON 2023). FUNDS REPRESENT NCDOT PAYBACK TO TOWN. | HIGHWAY | 8 | TRIANGLE AREA RPO | R-5963A | DIVISION 8 | DIVISION 8 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2024 | 2024 | NO CHANGE | 2024 | 2024 | NO CHANGE | 2027 | 2027 | NO CHANGE
CHATHAM | NEW ROUTE | SR 1012 (MONCURE-PITTSBORO ROAD) TO US 64 BUSINESS. CONSTRUCT 2-LANE ROADWAY ON NEW LOCATION. TOWN OF PITTSBORO DELIVERING PROJECT (ROW 2024, CON 2024). FUNDS REPRESENT NCDOT PAYBACK TO TOWN. | HIGHWAY | 8 | TRIANGLE AREA RPO | R-5963B | DIVISION 8 | DIVISION 8 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2024 | 2024 | NO CHANGE | 2024 | 2024 | NO CHANGE | 2027 | 2027 | NO CHANGE
CHATHAM | NEW ROUTE | US 64 BUSINESS TO JUST NORTH OF US 64. WIDEN EXISTING 2-LANE ROADWAY TO 4-LANES. | HIGHWAY | 8 | TRIANGLE AREA RPO | R-5963C | DIVISION 8 | DIVISION 8 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | N/A | N/A | NO CHANGE | 2024 | 2024 | NO CHANGE | 2027 | 2027 | NO CHANGE
CHATHAM | NEW ROUTE | CONSTRUCTION OF NEW WESTBOUND ON-RAMP FROM CHATHAM PARK WAY TO US 64 AND REALIGNMENT OF SUTTLES ROAD TO NEW INTERSECTION WITH CHATHAM PARK WAY. TOWN OF PITTSBORO DELIVERING PROJECT (ROW 2023, CON 2023). FUNDS REPRESENT NCDOT PAYBACK TO TOWN. | HIGHWAY | 8 | TRIANGLE AREA RPO | R-5963D | DIVISION 8 | DIVISION 8 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2024 | 2025 | 1 YEAR DELAY | 2024 | 2025 | 1 YEAR DELAY | 2027 | 2027 | NO CHANGE
CHATHAM | US 15 / US 501 | US 15 / US 501, NORTH OF US 64 BUSINESS TO POWELL PLACE LANE. MILL AND RESURFACE FROM NORTH OF US 64 BUSINESS TO LAUNIS STREET AND WIDEN FROM LAUNIS STREET TO POWELL PLACE LANE. | HIGHWAY | 8 | TRIANGLE AREA RPO | R-5724B | DIVISION 8 | DIVISION 8 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2023 | 2023 | NO CHANGE | 2023 | 2023 | NO CHANGE | 2025 | 2026 | 1 YEAR DELAY | YES
CHATHAM | US 64 (EAST 11TH STREET) | NORTH GLENN AVENUE TO EAST OF US 421 IN SILER CITY. UPGRADE ROADWAY TO INCLUDE MEDIAN FOR ACCESS CONTROL, SIDEWALKS, CROSSWALKS, BICYCLE LANES AND / OR MULTIUSE SIDEPATH. | HIGHWAY | 8 | TRIANGLE AREA RPO | U-5737 | REGION E | REGION E | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2023 | 2024 | 1 YEAR DELAY | 2023 | 2024 | 1 YEAR DELAY | 2026 | 2028 | 2 YEAR DELAY | YES
CHATHAM, ORANGE | US 15 / US 501 | US 64 BYPASS TO SR 1919 (SMITH LEVEL ROAD). CONVERT REMAINING NON-SYNCHRONIZED SECTIONS OF FACILITY TO SYNCHRONIZED STREET. | HIGHWAY | 8, 7 | TRIANGLE AREA RPO, DURHAM-CHAPEL HILL-CARRBORO MPO | U-6192 | DIVISION 8, 7 | DIVISION 8, 7 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2027 | 2028 | 1 YEAR DELAY | 2027 | 2028 | 1 YEAR DELAY | 2030 | 2031 | 1 YEAR DELAY
CHATHAM, WAKE | US 64 | NC 751. CONVERT AT-GRADE INTERSECTION TO INTERCHANGE. | HIGHWAY | 5, 8 | TRIANGLE AREA RPO, CAPITAL AREA MPO | R-5887 | REGION C, E | REGION C, E | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2027 | 2027 | NO CHANGE | 2027 | 2027 | NO CHANGE | 2029 | 2029 | NO CHANGE
CHEROKEE | US 19/129 | GEORGIA STATE LINE TO US 64. WIDEN ROADWAY. | HIGHWAY | 14 | SOUTHWESTERN RPO | R-5861 | DIVISION 14 | DIVISION 14 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2022 | 2022 | NO CHANGE | 2022 | 2022 | NO CHANGE | 2024 | 2024 | NO CHANGE
CHEROKEE | US 19/US 74/ US 129 | US 64 TO SR 1689 (CASINO PARKWAY). MODERNIZE ROADWAY. | HIGHWAY | 14 | SOUTHWESTERN RPO | R-5908 | DIVISION 14 | DIVISION 14 | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE
CHEROKEE, MACON | US 74 | SR 1393 (WAKEFIELD ROAD) TO SR 1310 (WAYAH ROAD). WIDEN TO MULTI-LANES. | HIGHWAY | 14 | SOUTHWESTERN RPO | R-5920 | NOT FUNDED | NOT FUNDED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE
CLAY | US 64 | NC 175 TO SR 1349 (OLD HWY 64 EAST). WIDEN TO MULTI-LANE. | HIGHWAY | 14 | SOUTHWESTERN RPO | R-5922 | NOT FUNDED | NOT FUNDED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE
CLAY, CHEROKEE | US 64 | US 64 BUSINESS WEST OF HAYESVILLE TO EAST OF NC 141. WIDEN TO FOUR-LANES DIVIDED. | HIGHWAY | 14 | SOUTHWESTERN RPO | R-5847 | NOT FUNDED | NOT FUNDED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE
CLEVELAND | US 74 | US 74 BUSINESS TO NC 226. CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | HIGHWAY | 12 | GASTON-CLEVELAND-LINCOLN MPO | R-5713 | REGION F | REGION F | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | N/A | N/A | NO CHANGE | N/A | N/A | NO CHANGE | 2024 | 2024 | NO CHANGE
CLEVELAND | US 74 (DIXON BOULEVARD) | NC 150 (DEKALB STREET) INTERSECTION. CONSTRUCT INTERCHANGE. | HIGHWAY | 12 | GASTON-CLEVELAND-LINCOLN MPO | U-2567 | STATEWIDE MOBILITY | STATEWIDE MOBILITY | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE
CLEVELAND | US 74 (DIXON BOULEVARD) | INTERSECTION OF US 74 (DIXON BOULEVARD) AND NC 226 (EARL ROAD). CONSTRUCT IMPROVEMENTS. | HIGHWAY | 12 | GASTON-CLEVELAND-LINCOLN MPO | U-5929 | STATEWIDE MOBILITY | STATEWIDE MOBILITY | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE
CLEVELAND | US 74 SHELBY BYPASS | EAST OF NC 150 TO EXISTING US 74 WEST OF SR 2238 (LONG BRANCH ROAD). GRADING, STRUCTURE, PAVING. | HIGHWAY | 12 | GASTON-CLEVELAND-LINCOLN MPO | R-2707D | REGION F | REGION F | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | UNDERWAY | UNDERWAY | NO CHANGE | UNDERWAY | UNDERWAY | NO CHANGE | 2024 | 2024 | NO CHANGE
CLEVELAND | US 74 SHELBY BYPASS | US 74 WEST OF SR 2238 TO WEST OF SR 1001 (STONEY POINT ROAD). GRADING, STRUCTURES, PAVING. | HIGHWAY | 12 | GASTON-CLEVELAND-LINCOLN MPO | R-2707E | REGION F | REGION F | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | UNDERWAY | UNDERWAY | NO CHANGE | UNDERWAY | UNDERWAY | NO CHANGE | 2024 | 2024 | NO CHANGE
CLEVELAND, GASTON | I-85 | SOUTH CAROLINA STATE LINE TO US 74 | HIGHWAY | 12 | GASTON-CLEVELAND-LINCOLN MPO | I-5985A | STATEWIDE MOBILITY | STATEWIDE MOBILITY | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE
COLUMBUS | NC 87 | NC 11 TO US 74/US 76 IN COLUMBUS COUNTY. | HIGHWAY | 6 | CAPE FEAR RPO | R-2561C | DIVISION 6 | DIVISION 6 | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE
COLUMBUS | US 701 BYPASS | SR 1166 (PLEASANT PLAINS CHURCH ROAD) TO SR 1437 (VIRGIL AVENUE). | HIGHWAY | 6 | CAPE FEAR RPO | R-5020A | REGION C | REGION C | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | UNDERWAY | UNDERWAY | NO CHANGE | UNDERWAY | UNDERWAY | NO CHANGE | 2026 | 2029 | 3 YEAR DELAY
COLUMBUS | US 701 BYPASS | SR 1305 (COMPLEX STREET). UPGRADE INTERSECTION. | HIGHWAY | 6 | CAPE FEAR RPO | R-5952 | DIVISION 6 | DELETED | SCHEDULED FOR DELIVERY | DELETED | 2025 | DELETED | PROJECT DELETED | 2025 | DELETED | PROJECT DELETED | 2027 | DELETED | PROJECT DELETED | YES
COLUMBUS, ROBESON | US 74 | NC 41 NEAR LUMBERTON TO US 76 NEAR CHADBOURN. UPGRADE US 74 TO INTERSTATE STANDARDS. | HIGHWAY | 6 | CAPE FEAR RPO, LUMBER RIVER RPO | I-6011 | NOT FUNDED | NOT FUNDED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE
CRAVEN | COASTAL CAROLINA REGIONAL AIRPORT (EWN) | RUNWAY EXTENSION. | AVIATION | 2 | NEW BERN AREA MPO | AV-5891 | NOT FUNDED | NOT FUNDED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | N/A | N/A | NO CHANGE | N/A | N/A | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE
CRAVEN | NC 43 CONNECTOR | US 17 BUSINESS TO SOUTH OF US17/US 70. | HIGHWAY | 2 | NEW BERN AREA MPO | R-4463A | REGION B | REGION B | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2020 | 2020 | NO CHANGE | 2019 | 2020 | 1 YEAR DELAY | 2025 | 2025 | NO CHANGE
CRAVEN | NC 55 (NEUSE BOULEVARD) | US 17 BUSINESS (MLK BOULEVARD). CONSTRUCT ROUNDABOUT. | HIGHWAY | 2 | NEW BERN AREA MPO | U-5993 | REGION B | REGION B | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2026 | 2026 | NO CHANGE | N/A | N/A | NO CHANGE | 2028 | 2028 | NO CHANGE
CRAVEN | SR 1763 (MILLER BOULEVARD) | SR 1756 (LAKE ROAD) TO OUTER BANKS DRIVE. WIDEN TO MULTI-LANES. | HIGHWAY | 2 | DOWN EAST RPO | U-3431 | DIVISION 2 | DIVISION 2 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2026 | 2026 | NO CHANGE | 2026 | 2026 | NO CHANGE | 2028 | 2028 | NO CHANGE
CRAVEN | US 17 | NORTH OF NC 43 TO SR 1438 (SPRUILL TOWN ROAD). | HIGHWAY | 2 | DOWN EAST RPO | R-2513A | DIVISION 2 | DIVISION 2 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2026 | 2026 | NO CHANGE | 2026 | 2026 | NO CHANGE | 2028 | 2028 | NO CHANGE
CRAVEN | US 17 | SR 1433 (ANTIOCH ROAD) TO NORTH OF NC 43. | HIGHWAY | 2 | DOWN EAST RPO, NEW BERN AREA MPO | R-3403B | REGION B | REGION B | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2027 | 2027 | NO CHANGE | 2027 | 2027 | NO CHANGE | 2029 | 2029 | NO CHANGE
CRAVEN | US 17 ALTERNATE (MARTIN LUTHER KING JR. BOULEVARD) | US 70 TO SR 1278 (TRENT ROAD). UGRADE TO SUPERSTREET. | HIGHWAY | 2 | NEW BERN AREA MPO | U-6198 | NOT FUNDED | NOT FUNDED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE
CRAVEN | US 70 | SR 1309 (GLENBURNIE ROAD). IMPROVE INTERCHANGE. | HIGHWAY | 2 | NEW BERN AREA MPO | U-6102 | NOT FUNDED | NOT FUNDED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE
CUMBERLAND | FAYETTEVILLE | CROSS CREEK PARKS CONNECTOR TRAIL, NC 24 (BRAGG BOULEVARD) TO RAY AVENUE IN FAYETTEVILLE. CONSTRUCT GREENWAY. | BIKE/PED | 6 | FAYETTEVILLE AREA MPO | EB-5907 | DIVISION 6 | DIVISION 6 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2024 | 2024 | NO CHANGE | N/A | N/A | NO CHANGE | 2026 | 2026 | NO CHANGE
CUMBERLAND | NC 210 (MURCHISON ROAD) | LANGDON STREET TO US 401 BYPASS. MODERNIZE ROADWAY. | HIGHWAY | 6 | FAYETTEVILLE AREA MPO | U-5015 | NOT FUNDED | NOT FUNDED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE
CUMBERLAND | NC 24 (NORTH BRAGG BOULEVARD) | SR 1451 (MANCHESTER ROAD). CONSTRUCT INTERCHANGE. | HIGHWAY | 6 | FAYETTEVILLE AREA MPO | U-5930 | STATEWIDE MOBILITY | STATEWIDE MOBILITY | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE
CUMBERLAND | NC 24 / NC 87 | SR 1451 (MANCHESTER ROAD) TO NC 210 (LILLINGTON HIGHWAY). IMPROVE EXISTING MULTI-LANE FACILITY BY ADDING ACCESS MANAGEMENT AND OTHER IMPROVEMENTS. | HIGHWAY | 6 | FAYETTEVILLE AREA MPO | U-5802 | DIVISION 6 | DIVISION 6 | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE
CUMBERLAND | NC 59 (SOUTH MAIN STREET) | SR 1243 (SHIPMAN ROAD) TO SR 1118 (PARKTON ROAD). WIDEN TO THREE LANES. | HIGHWAY | 6 | FAYETTEVILLE AREA MPO | U-6001 | REGION C | REGION C | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE
CUMBERLAND | SR 1003 (CAMDEN ROAD) | PROPOSED FAYETTEVILLE OUTER LOOP (U-2519) TO NC 59 (HOPE MILLS ROAD) IN FAYETTEVILLE. WIDEN TO MULTI-LANES. | HIGHWAY | 6 | FAYETTEVILLE AREA MPO | U-3422 | DIVISION 6 | DIVISION 6 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2021 | 2021 | NO CHANGE | 2021 | 2021 | NO CHANGE | 2024 | 2024 | NO CHANGE
CUMBERLAND | SR 1007 (ALL AMERICAN FREEWAY) | SR 1151 (OWEN DRIVE) TO NORTH OF SR 1437 (SANTA FE DRIVE). ADD ADDITIONAL LANES. | HIGHWAY | 6 | FAYETTEVILLE AREA MPO | U-4414 | REGION C | REGION C | SCHEDULED FOR DELIVERY | WILL BE REPRIORITIZED | 2028 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | PROJECT UNCOMMITTED | 2028 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | PROJECT UNCOMMITTED | 2030 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | PROJECT UNCOMMITTED
CUMBERLAND | SR 1104 (STRICKLAND BRIDGE ROAD) | US 401 TO FISHER ROAD. WIDEN ROADWAY. | HIGHWAY | 6 | FAYETTEVILLE AREA MPO | U-6210 | NOT FUNDED | NOT FUNDED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE
CUMBERLAND | SR 1112 (ROCKFISH ROAD) | SR 1102 (GILLIS HILL ROAD) TO CAMDEN ROAD. | HIGHWAY | 6 | FAYETTEVILLE AREA MPO | U-6072A | NOT FUNDED | NOT FUNDED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE
CUMBERLAND | SR 1219 (IRELAND DRIVE) | SR 1141 (CUMBERLAND ROAD) TO US 401 (RAEFORD ROAD). WIDEN ROADWAY. | HIGHWAY | 6 | FAYETTEVILLE AREA MPO | U-6213 | NOT FUNDED | NOT FUNDED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE
CUMBERLAND | SR 1400 (CLIFFDALE ROAD) | MCPHERSON CHURCH ROAD TO SR 1404 (MORGANTON ROAD). WIDEN TO MULTI-LANES. | HIGHWAY | 6 | FAYETTEVILLE AREA MPO | U-4404 | DIVISION 6 | DIVISION 6 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2028 | 2028 | NO CHANGE | 2028 | 2028 | NO CHANGE | 2030 | 2030 | NO CHANGE
CUMBERLAND | SR 1400 (CLIFFDALE ROAD) | SR 1411 (BUNCE ROAD) TO MCPHERSON CHURCH ROAD. ACCESS MANAGEMENT. | HIGHWAY | 6 | FAYETTEVILLE AREA MPO | U-6209 | DIVISION 6 | DIVISION 6 | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE
CUMBERLAND | SR 1437 (SHAW RD) | NC 24/87 (BRAGG BLVD) TO NC 210 (MURCHISON ROAD). INTERCONNECT AND WIDEN TO MULTI-LANES. | HIGHWAY | 6 | FAYETTEVILLE AREA MPO | U-5101A | DIVISION 6 | DIVISION 6 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2026 | 2026 | NO CHANGE | 2026 | 2026 | NO CHANGE | 2028 | 2028 | NO CHANGE
CUMBERLAND | US 401 | US 401 BYPASS TO NORTH OF SLOCUMB ROAD. | HIGHWAY | 6 | FAYETTEVILLE AREA MPO | U-4403C | DIVISION 6 | DIVISION 6 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2026 | 2026 | NO CHANGE | 2026 | 2026 | NO CHANGE | 2029 | 2029 | NO CHANGE
CUMBERLAND | US 401 (RAEFORD ROAD) | EAST OF GLENSFORD DRIVE TO EAST OF ROBESON STREET. | HIGHWAY | 6 | FAYETTEVILLE AREA MPO | U-4405C | DIVISION 6 | DIVISION 6 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | N/A | N/A | NO CHANGE | N/A | N/A | NO CHANGE | 2024 | 2025 | 1 YEAR DELAY | YES
CUMBERLAND | US 401 (ROBESON STREET) | US 401 (RAEFORD ROAD) TO WALTER STREET. ACCESS MANAGEMENT. | HIGHWAY | 6 | FAYETTEVILLE AREA MPO | U-6152 | NOT FUNDED | NOT FUNDED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE
CUMBERLAND | US 401 BUSINESS | US 401 BUSINESS (MARTIN LUTHER KING, JR. FREEWAY) TO US 401 BYPASS. | HIGHWAY | 6 | FAYETTEVILLE AREA MPO | U-4403B | REGION C | REGION C | SCHEDULED FOR DELIVERY | WILL BE REPRIORITIZED | 2027 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | PROJECT UNCOMMITTED | 2027 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | PROJECT UNCOMMITTED | 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | PROJECT UNCOMMITTED
CUMBERLAND | US 401 BUSINESS (SKIBO ROAD) | SR 1400 (CLIFFDALE ROAD). IMPROVE INTERSECTION | HIGHWAY | 6 | FAYETTEVILLE AREA MPO | U-6133 | REGION C | REGION C | SCHEDULED FOR DELIVERY | WILL BE REPRIORITIZED | 2028 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | PROJECT UNCOMMITTED | 2028 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | PROJECT UNCOMMITTED | 2030 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | PROJECT UNCOMMITTED
CUMBERLAND | FAYETTEVILLE AREA SYSTEM TRANSIT | EXPANSION BUS. | PUBLIC TRANSIT | 6 | FAYETTEVILLE AREA MPO | TA-6685 | DIVISION 6 | DIVISION 6 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | N/A | N/A | NO CHANGE | N/A | N/A | NO CHANGE | 2026 | 2026 | NO CHANGE
CUMBERLAND, HOKE | SR 1102 (GILLIS HILL ROAD) | FROM SR 1418 (LINDSAY ROAD) TO NORTH OF SR 1112 (STONEY POINT ROAD). WIDEN TO MULTI-LANES. | HIGHWAY | 6, 8 | FAYETTEVILLE AREA MPO | U-5798B | DIVISION 6, 8 | DIVISION 6, 8 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2023 | 2023 | NO CHANGE | 2023 | 2023 | NO CHANGE | 2025 | 2025 | NO CHANGE
CURRITUCK | NEW ROUTE | MID-CURRITUCK BRIDGE, COINJOCK TO COROLLA. NEW STRUCTURE OVER CURRITUCK SOUND AND UPGRADE APPROACHES. | HIGHWAY | 1 | ALBEMARLE RPO | R-2576 | DIVISION 1 | DIVISION 1 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2024 | 2024 | NO CHANGE | 2024 | 2024 | NO CHANGE | 2024 | 2024 | NO CHANGE
CURRITUCK, CAMDEN | US 158 (SHORTCUT ROAD) | EAST OF NC 34 (SHAWBORO ROAD) AT BELCROSS IN CAMDEN COUNTY TO US 158/NC 168 (CARATOKE HIGHWAY) IN CURRITUCK COUNTY. WIDEN TO MULTI-LANES. | HIGHWAY | 1 | ALBEMARLE RPO | R-2574 | REGION A | REGION A | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE
DARE | US 158 | CYPRESS KNEE LANE TO JEJAC STREET IN KITTY HAWK. CONSTRUCT SIDEWALK ON WEST SIDE. | BIKE/PED | 1 | ALBEMARLE RPO | EB-5848 | DIVISION 1 | DIVISION 1 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | N/A | N/A | NO CHANGE | N/A | N/A | NO CHANGE | 2025 | 2025 | NO CHANGE
DARE | US 158 | US 64-NC 12 TO EASTERN END OF CURRITUCK SOUND BRIDGE. ACCESS MANAGEMENT IMPROVEMENTS. | HIGHWAY | 1 | ALBEMARLE RPO | R-3419 | STATEWIDE MOBILITY | STATEWIDE MOBILITY | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE
DARE | US 158 | NC 12. IMPROVE INTERSECTION. | HIGHWAY | 1 | ALBEMARLE RPO | R-4457 | NOT FUNDED | NOT FUNDED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE
DARE, HYDE | HATTERAS - SOUTH DOCK | CONSTRUCT PASSENGER FERRY. | FERRY | 1 | ALBEMARLE RPO | F-5706 | NOT FUNDED | NOT FUNDED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | N/A | N/A | NO CHANGE | N/A | N/A | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE
DAVIDSON | NC 109 | NC 109 IN DENTON TO I-85 IN THOMASVILLE. WIDEN TO MULTILANES. | HIGHWAY | 9 | HIGH POINT URBAN AREA MPO | R-4734 | DIVISION 9 | DIVISION 9 | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE
DAVIDSON | NC 8 (WINSTON ROAD) | 9TH STREET TO SR 1408 (BIESECKER ROAD) IN LEXINGTON. WIDEN TO MULTILANES. | HIGHWAY | 9 | HIGH POINT URBAN AREA MPO | U-5757 | REGION D | REGION D | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2019 | 2019 | NO CHANGE | 2019 | 2019 | NO CHANGE | 2024 | 2024 | NO CHANGE
DAVIDSON | SR 1508 (HICKORY TREE ROAD) | US 52 / NC 8 / FUTURE I-285 TO NC 150. WIDEN TO MULTILANES. | HIGHWAY | 9 | WINSTON-SALEM URBAN AREA MPO | U-5786 | DIVISION 9 | DIVISION 9 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2026 | 2026 | NO CHANGE | 2026 | 2026 | NO CHANGE | 2028 | 2028 | NO CHANGE
DAVIDSON | NCRR / NORFOLK SOUTHERN MAIN LINE | SR 2165 (TURNER STREET) IN THOMASVILLE. CONSTRUCT GRADE SEPARATION AND CLOSE CROSSING 722327S. | RAIL | 9 | HIGH POINT URBAN AREA MPO | P-5751 | DIVISION 9 | DIVISION 9 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2028 | 2028 | NO CHANGE | N/A | N/A | NO CHANGE | 2031 | 2031 | NO CHANGE
DAVIDSON | NORFOLK SOUTHERN | KIMBERLY CLARK IN LEXINGTON. CONSTRUCT LEAD. | RAIL | 9 | HIGH POINT URBAN AREA MPO | P-5722 | REGION D | REGION D | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | N/A | N/A | NO CHANGE | N/A | N/A | NO CHANGE | 2024 | 2025 | 1 YEAR DELAY | YES
DAVIDSON | NORFOLK SOUTHERN | CROSSING 722306Y (EAST 7TH AVENUE) IN LEXINGTON. CONSTRUCT GRADE SEPARATION IN VICINITY OF 5TH STREET AND CLOSE CROSSING 722306Y. | RAIL | 9 | HIGH POINT URBAN AREA MPO | P-5731 | DIVISION 9 | DIVISION 9 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2022 | 2024 | 2 YEAR DELAY | N/A | N/A | NO CHANGE | 2022 | 2025 | 3 YEAR DELAY | YES
DAVIE | NEW ROUTE | SR 1630 (BALTIMORE ROAD) TO I-40. CONSTRUCT 2-LANE EXTENSION OF BALTIMORE ROAD AND INTERCHANGE AT I-40. | HIGHWAY | 9 | WINSTON-SALEM URBAN AREA MPO | U-6187 | DIVISION 9 | DIVISION 9 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2024 | 2024 | NO CHANGE | 2024 | 2024 | NO CHANGE | 2025 | 2025 | NO CHANGE
DAVIE | SR 1410 (FARMINGTON ROAD) | I-40 EASTBOUND RAMP AND US 158 INTERSECTION. CONSTRUCT ROUNDABOUTS. | HIGHWAY | 9 | NORTHWEST PIEDMONT RPO | R-5854 | DIVISION 9 | DIVISION 9 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2023 | 2023 | NO CHANGE | 2023 | 2023 | NO CHANGE | 2025 | 2025 | NO CHANGE
DAVIE | US 601 | SR 1345 (BLAISE CHURCH ROAD) TO SR 1408 (CANA ROAD). WIDEN TO MULTILANES. | HIGHWAY | 9 | NORTHWEST PIEDMONT RPO | R-5736 | DIVISION 9 | DIVISION 9 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2026 | 2026 | NO CHANGE | 2026 | 2026 | NO CHANGE | 2028 | 2028 | NO CHANGE
DURHAM | NC 157 / SR 1322 (GUESS ROAD) | HILLCREST DRIVE TO SR 1407 (WEST CARVER STREET) IN DURHAM. CONSTRUCT SIDEWALKS ON BOTH SIDES. | BIKE/PED | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | EB-5834 | DIVISION 5 | DIVISION 5 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2025 | 2025 | NO CHANGE | N/A | N/A | NO CHANGE | 2026 | 2026 | NO CHANGE
DURHAM | NC 55 (ALSTON AVENUE) | SR 1171 (RIDDLE ROAD) TO CECIL STREET IN DURHAM. CONSTRUCT SIDEWALK ON EAST SIDE TO FILL IN MISSING GAPS. | BIKE/PED | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | EB-5835 | DIVISION 5 | DIVISION 5 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2027 | 2027 | NO CHANGE | N/A | N/A | NO CHANGE | 2028 | 2028 | NO CHANGE
DURHAM | I-40 | NC 55 (ALSTON AVENUE) TO NC 147 (DURHAM FREEWAY / TRIANGLE EXPRESSWAY) IN DURHAM. CONSTRUCT WESTBOUND AUXILIARY LANE. | HIGHWAY | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | I-5707 | STATEWIDE MOBILITY | STATEWIDE MOBILITY | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2024 | 2025 | 1 YEAR DELAY | 2024 | 2025 | 1 YEAR DELAY | 2026 | 2027 | 1 YEAR DELAY
DURHAM | I-40, NC 54 | EAST OF LITTLE CREEK TO EAST OF I-40. UPGRADE ROADWAY CORRIDOR AND CONSTRUCT INTERCHANGE IMPROVEMENTS AT I-40. | HIGHWAY | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | U-5774F | STATEWIDE MOBILITY | STATEWIDE MOBILITY | WILL BE REPRIORITIZED | SCHEDULED FOR DELIVERY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2028 | PROJECT BECOMES COMMITTED | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2028 | PROJECT BECOMES COMMITTED | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2031 | PROJECT BECOMES COMMITTED |  | YES
DURHAM | I-85 / US 15 | EAST OF SR 1827 (MIDLAND TERRACE) TO SR 1632 (RED MILL ROAD) IN DURHAM. ADD LANES. | HIGHWAY | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | I-6010 | NOT FUNDED | NOT FUNDED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE
DURHAM | I-885 | I-40 TO NC 147 IN DURHAM. ADD LANES AND REHABILITATE PAVEMENT. | HIGHWAY | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | U-5934 | STATEWIDE MOBILITY | STATEWIDE MOBILITY | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2028 | 2028 | NO CHANGE | 2028 | 2028 | NO CHANGE | 2029 | 2029 | NO CHANGE
DURHAM | NC 147 (DURHAM FREEWAY) | SR 1127 (WEST CHAPEL HILL STREET) TO BRIGGS AVENUE IN DURHAM. CONSTRUCT AUXILIARY LANES AND OPERATIONAL IMPROVEMENTS. | HIGHWAY | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | U-5937 | STATEWIDE MOBILITY | STATEWIDE MOBILITY | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE
DURHAM | NC 54 | EAST OF SR1110 (BARBEE CHAPEL ROAD) TO EAST OF LITTLE CREEK. UPGRADE ROADWAY CORRIDOR. | HIGHWAY | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | U-5774C | REGION C | REGION C | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE
DURHAM | NC 55 | MERIDIAN PARKWAY TO I-40 INTERCHANGE IN DURHAM. ADD THIRD SOUTHBOUND LANE AND UPGRADE RAMP TERMINALS. | HIGHWAY | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | U-6118 | NOT FUNDED | DIVISION 5 | WILL BE REPRIORITIZED | SCHEDULED FOR DELIVERY | NOT FUNDED | 2028 | PROJECT BECOMES COMMITTED | NOT FUNDED | 2028 | PROJECT BECOMES COMMITTED | NOT FUNDED | 2029 | PROJECT BECOMES COMMITTED |  | YES
DURHAM | NC 98 (HOLLOWAY STREET) | SR 1938 (JUNCTION ROAD) TO SR 1919 (LYNN ROAD) IN DURHAM. CONSTRUCT SAFETY IMPROVEMENTS AND WIDEN TO ADD MEDIAN, BICYCLE LANES, SIDEWALKS, TRANSIT STOP IMPROVEMENTS, AND TRAFFIC SIGNALS WHERE NEEDED. | HIGHWAY | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | U-6120 | DIVISION 5 | DIVISION 5 | WILL BE REPRIORITIZED | SCHEDULED FOR DELIVERY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2028 | PROJECT BECOMES COMMITTED | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2028 | PROJECT BECOMES COMMITTED | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2030 | PROJECT BECOMES COMMITTED |  | YES
DURHAM | SR 1118 (FAYETTEVILLE ROAD) | WOODCROFT PARKWAY TO BARBEE ROAD IN DURHAM. WIDEN TO 4-LANE DIVIDED FACILITY WITH BICYCLE / PEDESTRIAN ACCOMMODATIONS. | HIGHWAY | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | U-6021 | DIVISION 5 | DIVISION 5 | SCHEDULED FOR DELIVERY | WILL BE REPRIORITIZED | 2028 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | PROJECT UNCOMMITTED | 2028 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | PROJECT UNCOMMITTED | 2031 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | PROJECT UNCOMMITTED |  | YES
DURHAM | US 15 / US 501 | SR 1116 (GARRETT ROAD) IN DURHAM. CONVERT AT-GRADE INTERSECTION TO INTERCHANGE. | HIGHWAY | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | U-5717 | STATEWIDE MOBILITY | STATEWIDE MOBILITY | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | UNDERWAY | UNDERWAY | NO CHANGE | UNDERWAY | UNDERWAY | NO CHANGE | 2026 | 2027 | 1 YEAR DELAY
DURHAM | US 15 / US 501 | I-40, SR (MOUNT MORIAH ROAD), AND SOUTHWEST DURHAM PARKWAY IN DURHAM. IMPROVE INTERCHANGE / INTERSECTION AREA. | HIGHWAY | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | U-6067 | STATEWIDE MOBILITY | STATEWIDE MOBILITY | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE
DURHAM | US 501 (ROXBORO ROAD) | SR 1448 (LATTA ROAD) / SR 1639 (INFINITY ROAD) INTERSECTION IN DURHAM. INTERSECTION IMPROVEMENTS. | HIGHWAY | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | U-5516 | REGION C | REGION C | SCHEDULED FOR DELIVERY | WILL BE REPRIORITIZED | 2026 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | PROJECT UNCOMMITTED | 2026 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | PROJECT UNCOMMITTED | 2028 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | PROJECT UNCOMMITTED
DURHAM | US 70 (MIAMI BOULEVARD) | LYNN ROAD TO SR 1959 (SOUTH MIAMI BOULEVARD) / SR 1811 (SHERRON ROAD). | HIGHWAY | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | U-5720A | STATEWIDE MOBILITY | STATEWIDE MOBILITY | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE
DURHAM | US 70 (MIAMI BOULEVARD) | SR 1959 (SOUTH MIAMI BOULEVARD) / SR 1811 (SHERRON ROAD) TO EAST OF SR 2095 (PAGE ROAD EXTENSION). | HIGHWAY | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | U-5720B | STATEWIDE MOBILITY | STATEWIDE MOBILITY | SCHEDULED FOR DELIVERY | WILL BE REPRIORITIZED | 2027 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | PROJECT UNCOMMITTED | 2027 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | PROJECT UNCOMMITTED | 2030 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | PROJECT UNCOMMITTED |  | YES
DURHAM | WOODCROFT PARKWAY EXTENSION | SR 1116 (GARRETT ROAD) TO NC 751 (HOPE VALLEY ROAD) IN DURHAM. CONSTRUCT ROADWAY ON NEW ALIGNMENT. | HIGHWAY | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | U-5823 | DIVISION 5 | DIVISION 5 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2024 | 2024 | NO CHANGE | 2024 | 2024 | NO CHANGE | 2025 | 2025 | NO CHANGE
DURHAM | NORFOLK SOUTHERN H LINE | EAST DURHAM RAILROAD SAFETY PROJECT. PROJECT WILL STRAIGHTEN EXISTING RAILROAD CURVATURE BETWEEN CP NELSON AND CP EAST DURHAM AND INCLUDES A COMBINATION OF GRADE SEPARATIONS AND CLOSURES AT ELLIS ROAD SOUTH END (734737A), GLOVER ROAD (734735L), AND WRENN | RAIL | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | P-5706 | STATEWIDE MOBILITY | STATEWIDE MOBILITY | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | UNDERWAY | UNDERWAY | NO CHANGE | 2023 | 2023 | NO CHANGE | 2027 | 2028 | 1 YEAR DELAY
DURHAM | NORFOLK SOUTHERN H LINE | CROSSING 734742W AT SR 1121 (CORNWALLIS ROAD) IN DURHAM. CONSTRUCT GRADE SEPARATION. | RAIL | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | P-5717 | REGION C | REGION C | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2022 | 2022 | NO CHANGE | 2022 | 2022 | NO CHANGE | 2024 | 2024 | NO CHANGE
DURHAM, WAKE | I-40 SR 1728 (WADE AVENUE) | NC 54 (EXIT 273) TO SR 1728 (WADE AVENUE), I-40 TO SR 1664 (BLUE RIDGE ROAD) CONVERT FACILITY TO A MANAGED FREEWAY WITH RAMP METERING AND OTHER ATM / ITS COMPONENTS. | HIGHWAY | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO, CAPITAL AREA MPO | I-6006 | STATEWIDE MOBILITY | STATEWIDE MOBILITY | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE
EDGECOMBE | TARBORO EDGECOMBE AIRPORT (ETC) | RUNWAY EXTENSION. | AVIATION | 4 | UPPER COASTAL PLAIN RPO | AV-5897 | DIVISION 4 | DIVISION 4 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | N/A | N/A | NO CHANGE | N/A | N/A | NO CHANGE | 2028 | 2028 | NO CHANGE
EDGECOMBE | EAST RALEIGH BOULEVARD | US 64 TO ARLINGTON STREET IN ROCKY MOUNT. PEDESTRIAN IMPROVEMENTS. | BIKE/PED | 4 | ROCKY MOUNT URBAN AREA MPO | EB-5984 | DIVISION 4 | DIVISION 4 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | N/A | N/A | NO CHANGE | N/A | N/A | NO CHANGE | 2028 | 2028 | NO CHANGE
EDGECOMBE | NC 97 (ATLANTIC AVENUE) | US 64 TO EAST RALEIGH BOULEVARD IN ROCKY MOUNT. PEDESTRIAN IMPROVEMENTS. | BIKE/PED | 4 | ROCKY MOUNT URBAN AREA MPO | EB-5729 | DIVISION 4 | DIVISION 4 | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | N/A | N/A | NO CHANGE | N/A | N/A | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE
EDGECOMBE | US 258 | SR 1601 (COLONIAL ROAD) TO US 64. WIDEN ROADWAY. | HIGHWAY | 4 | UPPER COASTAL PLAIN RPO | R-5949 | DIVISION 4 | DIVISION 4 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2027 | 2027 | NO CHANGE | 2027 | 2027 | NO CHANGE | 2029 | 2029 | NO CHANGE
EDGECOMBE, NASH | ROCKY MOUNT | US 301 BUSINESS, RIVER DRIVE TO MONK STREET IN ROCKY MOUNT. CONVERT ABANDONED RAILROAD TO MULTI-USE PATH. | BIKE/PED | 4 | ROCKY MOUNT URBAN AREA MPO | EB-5763 | DIVISION 4 | DIVISION 4 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2024 | 2024 | NO CHANGE | N/A | N/A | NO CHANGE | 2025 | 2025 | NO CHANGE
FORSYTH | SALEM CREEK GREENWAY | FORSYTH TECHNICAL COMMUNITY COLLEGE TO EXISTING GREENWAY AT MARKETPLACE MALL IN WINSTON-SALEM. CONSTRUCT GREENWAY. | BIKE/PED | 9 | WINSTON-SALEM URBAN AREA MPO | EB-5812 | DIVISION 9 | DIVISION 9 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | N/A | N/A | NO CHANGE | N/A | N/A | NO CHANGE | 2026 | 2026 | NO CHANGE
FORSYTH | SR 1122 (JONESTOWN ROAD) | EAST OF US 421 TO SR 1001 (COUNTRY CLUB ROAD) IN WINSTON-SALEM. CONSTRUCT SIDEWALK ON EAST SIDE AND WEST SIDE OF JONESTOWN RD. | BIKE/PED | 9 | WINSTON-SALEM URBAN AREA MPO | EB-5920 | DIVISION 9 | DIVISION 9 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2024 | 2024 | NO CHANGE | 2024 | 2024 | NO CHANGE | 2025 | 2025 | NO CHANGE
FORSYTH | I-40 | I-74 / US 311 TO SR 2643 (UNION CROSS ROAD). | HIGHWAY | 9 | WINSTON-SALEM URBAN AREA MPO | I-5981A | STATEWIDE MOBILITY | STATEWIDE MOBILITY | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE
FORSYTH | I-40 | SR 2643 (UNION CROSS ROAD) TO NC 66. | HIGHWAY | 9 | WINSTON-SALEM URBAN AREA MPO | I-5981B | STATEWIDE MOBILITY | STATEWIDE MOBILITY | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE
FORSYTH | I-40 / US 311 | NC 109 (THOMASVILLE ROAD) / CLEMMONSVILLE ROAD SPLIT-DIAMOND INTERCHANGE IN WINSTON-SALEM. CONVERT HALF DIAMOND INTERCHANGE AT NC 109 TO FULL DIAMOND, AND REMOVE CONNECTOR ROADS AND HALF DIAMOND INTERCHANGE AT CLEMMONSVILLE ROAD | HIGHWAY | 9 | WINSTON-SALEM URBAN AREA MPO | I-5880 | REGION D | REGION D | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2023 | 2023 | NO CHANGE | 2023 | 2023 | NO CHANGE | 2025 | 2025 | NO CHANGE
FORSYTH | KERNERSVILLE SOUTHERN LOOP (PHASE I) | US 421 / BUSINESS 40 TO NC 66 (WEST MOUNTAIN STREET) IN KERNERSVILLE. WIDEN BIG MILL FARM ROAD AND SR 2649 (HOPKINS ROAD) AND CONSTRUCT INTERCHANGE AT US 421 / NC 150 / BUSINESS 40. | HIGHWAY | 9 | WINSTON-SALEM URBAN AREA MPO | U-5760 | DIVISION 9 | DIVISION 9 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2022 | 2022 | NO CHANGE | 2022 | 2022 | NO CHANGE | 2025 | 2025 | NO CHANGE
FORSYTH | NC 65 (BETHANIA-RURAL HALL ROAD) | US 52 TO SR 3983 (NORTHRIDGE DRIVE) IN RURAL HALL. WIDEN TO MULTILANES. | HIGHWAY | 9 | WINSTON-SALEM URBAN AREA MPO | U-6005 | DIVISION 9 | DIVISION 9 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2023 | 2023 | NO CHANGE | 2023 | 2023 | NO CHANGE | 2025 | 2025 | NO CHANGE
FORSYTH | NC 65 (BETHANIA-RURAL HALL ROAD) | SR 1647 (GLADE STREET) TO NC 66 IN RURAL HALL. WIDEN TO 3 LANES. | HIGHWAY | 9 | WINSTON-SALEM URBAN AREA MPO | U-6190 | DIVISION 9 | DIVISION 9 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2027 | 2027 | NO CHANGE | 2027 | 2027 | NO CHANGE | 2029 | 2029 | NO CHANGE
FORSYTH | NC 66 (OLD HOLLOW ROAD) | HARLEY DRIVE TO US 158 IN WALKERTOWN. WIDEN TO MULTILANES. | HIGHWAY | 9 | WINSTON-SALEM URBAN AREA MPO | U-5824 | DIVISION 9 | DIVISION 9 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2021 | 2021 | NO CHANGE | N/A | N/A | NO CHANGE | 2024 | 2024 | NO CHANGE
FORSYTH | NEW ROUTE | PROPOSED GREAT WAGON ROAD FROM SHALLOWFORD ROAD (SR 1001) TO LEWISVILLE-VIENNA ROAD (SR 1308) IN LEWISVILLE. MULTILANE FACILITY ON NEW LOCATION WITH BICYCLE AND PEDESTRIAN ACCOMMODATIONS. | HIGHWAY | 9 | WINSTON-SALEM URBAN AREA MPO | U-5536 | DIVISION 9 | DIVISION 9 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2022 | 2022 | NO CHANGE | 2022 | 2022 | NO CHANGE | 2024 | 2024 | NO CHANGE
FORSYTH | NEW ROUTE | FORUM PARKWAY CONNECTOR, SR 3955 (FORUM PARKWAY) TO NC 66 (UNIVERSITY PARKWAY) IN RURAL HALL. CONSTRUCT 2-LANE ROADWAY ON NEW LOCATION. | HIGHWAY | 9 | WINSTON-SALEM URBAN AREA MPO | U-5899 | DIVISION 9 | DIVISION 9 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2022 | 2022 | NO CHANGE | 2022 | 2022 | NO CHANGE | 2024 | 2024 | NO CHANGE
FORSYTH | NEW ROUTE | SR 1969 (PINEY GROVE ROAD) TO NC 150 (NORTH MAIN STREET) IN KERNERSVILLE. CONSTRUCT TWO-LANE DIVIDED FACILITY WITH BICYCLE / PEDESTRIAN ACCOMMODATIONS. | HIGHWAY | 9 | WINSTON-SALEM URBAN AREA MPO | U-6003 | DIVISION 9 | DIVISION 9 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | UNDERWAY | UNDERWAY | NO CHANGE | UNDERWAY | UNDERWAY | NO CHANGE | 2024 | 2024 | NO CHANGE
FORSYTH | NEW ROUTE (FUTURE NC 452) | WINSTON-SALEM NORTHERN BELTWAY, WESTERN SECTION, US 158 TO SOUTH OF I-40 | HIGHWAY | 9 | WINSTON-SALEM URBAN AREA MPO | R-2247A | NOT FUNDED | NOT FUNDED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE
FORSYTH | NEW ROUTE (FUTURE NC 452) | WINSTON-SALEM NORTHERN BELTWAY, WESTERN SECTION, SOUTH OF I-40 TO SOUTH OF US 421 INTERCHANGE | HIGHWAY | 9 | WINSTON-SALEM URBAN AREA MPO | R-2247B | NOT FUNDED | NOT FUNDED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE
FORSYTH | NEW ROUTE (FUTURE NC 452) | WINSTON-SALEM NORTHERN BELTWAY, WESTERN SECTION, INTERCHANGE WITH US 421 AND INTERCHANGE WITH SR 1140 (PEACE HAVEN ROAD) | HIGHWAY | 9 | WINSTON-SALEM URBAN AREA MPO | R-2247CA | REGION D | REGION D | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE
FORSYTH | NEW ROUTE (FUTURE NC 452) | WINSTON-SALEM NORTHERN BELTWAY, WESTERN SECTION, NORTH OF US 421 INTERCHANGE TO SR 1348 (ROBINHOOD ROAD) | HIGHWAY | 9 | WINSTON-SALEM URBAN AREA MPO | R-2247CB | REGION D | REGION D | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE
FORSYTH | NEW ROUTE (FUTURE NC 452) | WINSTON-SALEM NORTHERN BELTWAY, WESTERN SECTION, NORTH OF SR 1348 (MEADOWLARK DRIVE-ROBINHOOD ROAD) TO NC 67 | HIGHWAY | 9 | WINSTON-SALEM URBAN AREA MPO | R-2247D | REGION D | REGION D | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE
FORSYTH | NEW ROUTE (FUTURE NC 452) | WINSTON-SALEM NORTHERN BELTWAY, WESTERN SECTION, NC 67 TO SOUTH OF US 52 | HIGHWAY | 9 | WINSTON-SALEM URBAN AREA MPO | R-2247EA | REGION D | REGION D | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2028 | 2028 | NO CHANGE | 2028 | 2028 | NO CHANGE | 2030 | 2030 | NO CHANGE
FORSYTH | SR 1103 (LEWISVILLE- CLEMMONS ROAD) | US 158 TO SR 1891 (PEACE HAVEN ROAD) IN CLEMMONS. ACCESS MANAGEMENT AND OPERATIONAL IMPROVEMENTS. | HIGHWAY | 9 | WINSTON-SALEM URBAN AREA MPO | U-6004 | DIVISION 9 | DIVISION 9 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2024 | 2024 | NO CHANGE | 2024 | 2024 | NO CHANGE | 2026 | 2026 | NO CHANGE
FORSYTH | SR 1156 (LEWISVILLE- CLEMMONS ROAD) | SR 1103 (STYERS FERRY ROAD) TO SR 1101 (SHALLOWFORD ROAD) IN LEWISVILLE. WIDEN TO 3 LANES WITH BICYCLE AND PEDESTRIAN ACCOMMODATIONS. | HIGHWAY | 9 | WINSTON-SALEM URBAN AREA MPO | U-6189 | DIVISION 9 | DIVISION 9 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2027 | 2027 | NO CHANGE | 2027 | 2027 | NO CHANGE | 2029 | 2029 | NO CHANGE
FORSYTH | SR 1969 (PINEY GROVE ROAD) | NORTH OF NELSON STREET TO SR 2031 (BROWN ROAD) IN KERNERSVILLE. WIDEN TO 3 LANES WITH BICYCLE / PEDESTRIAN ACCOMMODATIONS. | HIGHWAY | 9 | WINSTON-SALEM URBAN AREA MPO | U-6188 | DIVISION 9 | DIVISION 9 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2027 | 2027 | NO CHANGE | 2027 | 2027 | NO CHANGE | 2029 | 2029 | NO CHANGE
FORSYTH | US 158 | MULTI-LANES NORTH OF US 421 / I-40 BUSINESS TO SR 1965 (BELEWS CREEK ROAD) | HIGHWAY | 9 | WINSTON-SALEM URBAN AREA MPO | R-2577A | REGION D | REGION D | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2021 | 2021 | NO CHANGE | 2021 | 2021 | NO CHANGE | 2024 | 2024 | NO CHANGE
FORSYTH, GUILFORD | US 158 | SR 1965 (BELEWS CREEK ROAD) IN FORSYTH COUNTY TO SR 2034 (ANTHONY ROAD) IN GUILFORD COUNTY | HIGHWAY | 7, 9 | WINSTON-SALEM URBAN AREA MPO, GREENSBORO URBAN AREA MPO | R-2577B | REGION D | REGION D | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE
FORSYTH, GUILFORD | US 421 (SALEM PARKWAY) | FUTURE I-74 IN KERNERSVILLE TO I-40 IN GUILFORD COUNTY. WIDEN TO 6 LANES. | HIGHWAY | 7, 9 | WINSTON-SALEM URBAN AREA MPO, GREENSBORO URBAN AREA MPO | U-6068 | NOT FUNDED | NOT FUNDED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE
FRANKLIN | TRIANGLE NORTH EXECUTIVE AIRPORT (LHZ) | CONSTRUCT RUNWAY EXTENSION, TO INCLUDE RELOCATION OF UTILITIES, NAVAID AND ROADWAYS. | AVIATION | 5 | CAPITAL AREA MPO | AV-5819 | DIVISION 5 | DIVISION 5 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2026 | 2026 | NO CHANGE | N/A | N/A | NO CHANGE | 2028 | 2028 | NO CHANGE
FRANKLIN | NC 56 | SR 1114 (PEACH ORCHARD ROAD) TO US 401 IN LOUISBURG. WIDEN TO 4 LANES. | HIGHWAY | 5 | KERR-TAR RPO | R-5893 | NOT FUNDED | NOT FUNDED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE
FRANKLIN | US 401 | SR 1103 (FLAT ROCK CHURCH ROAD / CLIFTON POND ROAD) TO SR 1700 (FOX PARK ROAD) SOUTH OF LOUISBURG | HIGHWAY | 5 | CAPITAL AREA MPO, KERR-TAR RPO | R-2814D | DIVISION 5 | DIVISION 5 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2028 | 2028 | NO CHANGE | 2028 | 2028 | NO CHANGE | 2031 | 2031 | NO CHANGE
FRANKLIN | US 401 / NC 39 | NC 56 / NC 581 (NASH STREET) TO SR 1229 (MAIN STREET). WIDEN TO MULTILANES. | HIGHWAY | 5 | KERR-TAR RPO | R-3608 | REGION C | REGION C | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE
FRANKLIN | US 401 / NC 39 (BICKETT BOULEVARD) | BURKE BOULEVARD TO NC 56 / NC 581 (NASH STREET) IN LOUISBURG. CONVERT 5-LANE SECTION TO 4-LANE DIVIDED FACILITY WITH BICYCLE / PEDESTRIAN ACCOMMODATIONS. | HIGHWAY | 5 | KERR-TAR RPO | U-6024 | DIVISION 5 | DIVISION 5 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2028 | 2028 | NO CHANGE | 2028 | 2028 | NO CHANGE | 2031 | 2031 | NO CHANGE
GASTON | CRAMERTON | SR 2014 (LAKEWOOD ROAD), SR 2565 (EAGLE ROAD) TO LAKE DRIVE. CONSTRUCT SIDEWALK AND PEDESTRIAN BRIDGE OVER SOUTH FORK RIVER INLET. | BIKE/PED | 12 | GASTON-CLEVELAND-LINCOLN MPO | EB-5913 | DIVISION 12 | DIVISION 12 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | N/A | N/A | NO CHANGE | N/A | N/A | NO CHANGE | 2025 | 2025 | NO CHANGE
GASTON | NC 279 (NEW HOPE ROAD) | US 29/74 (FRANKLIN BOULEVARD) TO HUNT AVENUE. CONSTRUCT SIDEWALK ON EAST SIDE OF NC 279 (NEW HOPE ROAD) FROM US 29/74 (FRANKLIN BOULEVARD) TO COURT DRIVE AND WEST SIDE OF NC 279 FROM COURT DRIVE TO HUNT AVENUE. | BIKE/PED | 12 | GASTON-CLEVELAND-LINCOLN MPO | EB-5975 | DIVISION 12 | DIVISION 12 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | N/A | N/A | NO CHANGE | N/A | N/A | NO CHANGE | 2024 | 2024 | NO CHANGE
GASTON | NC 279 (SOUTH NEW HOPE ROAD) | SR 2200 (ARMSTRONG PARK ROAD) TO SR 1255 (HUDSON BOULEVARD). CONSTRUCT MISSING SIDEWALK ON SOUTH SIDE OF NC 279. | BIKE/PED | 12 | GASTON-CLEVELAND-LINCOLN MPO | EB-5743 | DIVISION 12 | DIVISION 12 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | N/A | N/A | NO CHANGE | N/A | N/A | NO CHANGE | 2024 | 2024 | NO CHANGE
GASTON | SOUTH MARIETTA STREET/ HILLTOP DRIVE | HUDSON BOULEVARD TO CLYDE STREET. CONSTRUCT SIDEWALK ON ONE SIDE OF ROAD. | BIKE/PED | 12 | GASTON-CLEVELAND-LINCOLN MPO | EB-5768 | DIVISION 12 | DIVISION 12 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2023 | 2023 | NO CHANGE | N/A | N/A | NO CHANGE | 2024 | 2024 | NO CHANGE
GASTON | SR 1255 (HUDSON BLVD) SR 2466 (REDBUD DR) | SR 1255 (HUDSON BOULEVARD) FROM SR 2200 (GASTON DAY SCHOOL ROAD) TO SR 2466 (REDBUD DRIVE). SR 2466 (REDBUD DRIVE) FROM SR 1255 (HUDSON BOULEVARD) TO NC 279 (SOUTH NEW HOPE ROAD). CONSTRUCT SIDEWALK ON ONE SIDE. | BIKE/PED | 12 | GASTON-CLEVELAND-LINCOLN MPO | EB-5745 | DIVISION 12 | DIVISION 12 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2023 | 2023 | NO CHANGE | N/A | N/A | NO CHANGE | 2024 | 2024 | NO CHANGE
GASTON | SR 2044 (TUCKASEEGEE ROAD) MOUNT HOLLY | NC 273 TO MARINA VILLAGE DRIVE. CONSTRUCT SIDEWALK ON SOUTH SIDE. MARINA VILLAGE DRIVE NORTH TO BROOME STREET. CONSTRUCT SIDEWALK ON WEST SIDE. | BIKE/PED | 12 | GASTON-CLEVELAND-LINCOLN MPO | EB-5912 | DIVISION 12 | DIVISION 12 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2025 | 2025 | NO CHANGE | N/A | N/A | NO CHANGE | 2027 | 2027 | NO CHANGE
GASTON | SR 2200 (COX ROAD) | I-85 TO COURT DRIVE. CONSTRUCT SIDEWALK ON BOTH SIDES OF SR 2200 (COX ROAD). | BIKE/PED | 12 | GASTON-CLEVELAND-LINCOLN MPO | EB-5976 | DIVISION 12 | DIVISION 12 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | N/A | N/A | NO CHANGE | N/A | N/A | NO CHANGE | 2024 | 2024 | NO CHANGE
GASTON | I-85 | US 321 TO NC 273. WIDEN TO EIGHT LANES. | HIGHWAY | 12 | GASTON-CLEVELAND-LINCOLN MPO | I-5719 | STATEWIDE MOBILITY | STATEWIDE MOBILITY | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2024 | 2024 | NO CHANGE | 2024 | 2024 | NO CHANGE | 2024 | 2024 | NO CHANGE
GASTON | I-85 | US 74 TO US 321 | HIGHWAY | 12 | GASTON-CLEVELAND-LINCOLN MPO | I-5985B | STATEWIDE MOBILITY | STATEWIDE MOBILITY | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE
GASTON | NC 27 (WEST CHARLOTTE AVENUE) | INTERSECTION OF NC 27 (WEST CHARLOTTE AVENUE) AND SR 2534 (HAWTHORNE STREET). CONSTRUCT INTERSECTION IMPROVEMENTS. | HIGHWAY | 12 | GASTON-CLEVELAND-LINCOLN MPO | U-5819 | DIVISION 12 | DIVISION 12 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2028 | 2028 | NO CHANGE | 2028 | 2028 | NO CHANGE | 2030 | 2030 | NO CHANGE
GASTON | NC 273 | SR 2525 (SOUTH POINT ROAD) INTERSECTION. CONSTRUCT ROUNDABOUT. | HIGHWAY | 12 | GASTON-CLEVELAND-LINCOLN MPO | U-6150 | NOT FUNDED | NOT FUNDED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE
GASTON | NC 274 (UNION ROAD) | OSCEOLA STREET TO NIBLICK DRIVE. UPGRADE ROADWAY. | HIGHWAY | 12 | GASTON-CLEVELAND-LINCOLN MPO | U-5961 | REGION F | REGION F | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2024 | 2024 | NO CHANGE | 2024 | 2024 | NO CHANGE | 2027 | 2027 | NO CHANGE
GASTON | NC 275 | INTERSECTION OF NC 275 AND NC 274, INTERSECTION OF NC 275 AND SR 1327 (FAIRVIEW ROAD), AND INTERSECTION OF SR 1456 (WHITE JENKINS ROAD) AND SR 1327 (FAIRVIEW ROAD). IMPROVE INTERSECTIONS AND CLOSE INTERSECTION OF NC 275 AND SR 1456 (WHITE JENKINS ROAD) | HIGHWAY | 12 | GASTON-CLEVELAND-LINCOLN MPO | U-6078 | DIVISION 12 | DIVISION 12 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2025 | 2025 | NO CHANGE | 2025 | 2025 | NO CHANGE | 2027 | 2027 | NO CHANGE
GASTON | NC 279 | NORTH OF SR 2275 (ROBINSON-CLEMMER ROAD) TO WEST OF NC 275 IN DALLAS. | HIGHWAY | 12 | GASTON-CLEVELAND-LINCOLN MPO | U-2523B | REGION F | REGION F | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2026 | 2026 | NO CHANGE | 2026 | 2026 | NO CHANGE | 2028 | 2028 | NO CHANGE
GASTON | NC 279 (NEW HOPE ROAD) | SR 2478 (TITMAN ROAD) TO SR 2435 (UNION-NEW HOPE ROAD). WIDEN TO 4-LANES. | HIGHWAY | 12 | GASTON-CLEVELAND-LINCOLN MPO | U-5821 | DIVISION 12 | DIVISION 12 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2023 | 2023 | NO CHANGE | 2023 | 2023 | NO CHANGE | 2026 | 2026 | NO CHANGE
GASTON | NC 279 (NORTH NEW HOPE ROAD) | US 29/74 (FRANKLIN BOULEVARD) INTERSECTION. ADD RIGHT TURN LANE FROM NC 279 (NORTH NEW HOPE ROAD) TO US 29/74 (FRANKLIN BOULEVARD). | HIGHWAY | 12 | GASTON-CLEVELAND-LINCOLN MPO | U-6138 | REGION F | REGION F | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2025 | 2025 | NO CHANGE | 2025 | 2025 | NO CHANGE | 2026 | 2026 | NO CHANGE
GASTON | NC 7 | INTERSECTION OF NC 7/US 74 AND NC 7/US 29. CONSTRUCT NORTHBOUND THROUGH LANE AND INTERSECTION IMPROVEMENTS. | HIGHWAY | 12 | GASTON-CLEVELAND-LINCOLN MPO | U-5800 | REGION F | REGION F | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2024 | 2024 | NO CHANGE | 2024 | 2024 | NO CHANGE | 2024 | 2024 | NO CHANGE
GASTON | SR 2200 (COX ROAD) | I-85 TO US 29/74. SELECTIVE WIDENING AND OPERATIONAL IMPROVEMENTS. | HIGHWAY | 12 | GASTON-CLEVELAND-LINCOLN MPO | U-6044 | DIVISION 12 | DIVISION 12 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2025 | 2025 | NO CHANGE | 2025 | 2025 | NO CHANGE | 2028 | 2028 | NO CHANGE
GASTON | US 29 (FRANKLIN BOULEVARD) | US 29 (FRANKLIN BOULEVARD) AND NC 274. CONSTRUCT INTERSECTION IMPROVEMENTS. | HIGHWAY | 12 | GASTON-CLEVELAND-LINCOLN MPO | U-5965 | REGION F | REGION F | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2023 | 2023 | NO CHANGE | 2023 | 2023 | NO CHANGE | 2025 | 2025 | NO CHANGE
GASTON | US 29/74 (FRANKLIN BOULEVARD) | SR 2329 (REDBUD DRIVE) INTERSECTION. IMPROVE INTERSECTION AREA INCLUDING NEW GRADE-SEPARATED CROSSING OF US 29/74. | HIGHWAY | 12 | GASTON-CLEVELAND-LINCOLN MPO | U-6141 | NOT FUNDED | NOT FUNDED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE
GASTON | US 29/74 (WILKINSON BOULEVARD) | MARKET STREET TO SR 2015 (ALBERTA AVENUE. WIDEN TO SIX LANES (INCLUDES REPLACEMENT OF BRDIGE 350082 OVER SOUTH FORK OF CATAWBA RIVER). | HIGHWAY | 12 | GASTON-CLEVELAND-LINCOLN MPO | U-6146 | REGION F | REGION F | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2022 | 2022 | NO CHANGE | 2022 | 2022 | NO CHANGE | 2024 | 2024 | NO CHANGE
GASTON | US 29/US 74 (FRANKLIN BOULEVARD) | SR 2200 (COX ROAD) TO 400 FEET EAST OF LINEBERGER ROAD. ADD LANE IN THE EASTBOUND DIRECTION. | HIGHWAY | 12 | GASTON-CLEVELAND-LINCOLN MPO | U-6043 | DIVISION 12 | DIVISION 12 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2023 | 2023 | NO CHANGE | 2023 | 2023 | NO CHANGE | 2025 | 2025 | NO CHANGE
GASTON | US 321 (SOUTH YORK ROAD) | 19TH AVENUE TO CLYDE. CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | HIGHWAY | 12 | GASTON-CLEVELAND-LINCOLN MPO | U-5970 | REGION F | REGION F | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE
GASTON | US 74 (WILKINSON BOULEVARD) | US 74 (WILKINSON BOULEVARD) AT NC 273 (PARK STREET). CONSTRUCT INTERSECTION IMPROVEMENTS. | HIGHWAY | 12 | GASTON-CLEVELAND-LINCOLN MPO | U-5959 | REGION F | REGION F | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE
GATES, CHOWAN | NC 32 | NC 37 (GLIDEN ROAD) TO VIRGINIA STATE LINE. MODERNIZE ROADWAY. | HIGHWAY | 1 | ALBEMARLE RPO | R-5938 | DIVISION 1 | DIVISION 1 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2028 | 2028 | NO CHANGE | 2028 | 2028 | NO CHANGE | 2030 | 2031 | 1 YEAR DELAY
GRAHAM | NC 143 | WEST BUFFALO CREEK TO NC 143 BUSINESS. UPGRADE CORRIDOR. | HIGHWAY | 14 | SOUTHWESTERN RPO | R-2822B | REGION G | REGION G | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2023 | 2023 | NO CHANGE | 2023 | 2023 | NO CHANGE | 2025 | 2025 | NO CHANGE | YES
GRAHAM | NC 28 | SWAIN/GRAHAM COUNTY LINE AT LITTLE TENNESSEE RIVER TO WOODS ROAD AT FONTANA DAM VILLAGE. UPGRADE ROADWAY. | HIGHWAY | 14 | SOUTHWESTERN RPO | R-5839BA | DIVISION 14 | DIVISION 14 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2027 | 2027 | NO CHANGE | 2027 | 2027 | NO CHANGE | 2029 | 2029 | NO CHANGE
GRANVILLE | NC 56 (EAST C STREET) | SR 1215 (WEST LYON STATION ROAD) IN BUTNER. REALIGN INTERSECTION. | HIGHWAY | 5 | KERR-TAR RPO | U-6020 | DIVISION 5 | DIVISION 5 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | UNDERWAY | UNDERWAY | NO CHANGE | UNDERWAY | UNDERWAY | NO CHANGE | 2025 | 2025 | NO CHANGE
GREENE | NC 58 (KINGOLD BOULEVARD) | SR 1105 (GREENRIDGE ROAD) TO CAROLINA DRIVE. UPGRADE ROADWAY. | HIGHWAY | 2 | EASTERN CAROLINA RPO | R-5898 | NOT FUNDED | NOT FUNDED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE
GREENE | US 13 | SR 1104 (HULL ROAD). UPGRADE INTERSECTION. | HIGHWAY | 2 | EASTERN CAROLINA RPO | R-5943 | DIVISION 2 | DIVISION 2 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2026 | 2025 | 1 YEAR ACCELERATION | 2026 | 2025 | 1 YEAR ACCELERATION | 2028 | 2028 | NO CHANGE
GREENE | US 13/US 258 | NC 91 TO US 258 SPLIT. UPGRADE TO FREEWAY. | HIGHWAY | 2 | EASTERN CAROLINA RPO | R-5942 | NOT FUNDED | NOT FUNDED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE
GUILFORD | PIEDMONT TRIAD INTERNATIONAL AIRPORT (GSO) | SURFACE MOVEMENT GUIDANCE AND CONTROL SYSTEM (SMGCS) UPDATE. | AVIATION | 7 | GREENSBORO URBAN AREA MPO | AV-5711 | STATEWIDE MOBILITY | STATEWIDE MOBILITY | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | N/A | N/A | NO CHANGE | N/A | N/A | NO CHANGE | 2025 | 2026 | 1 YEAR DELAY
GUILFORD | PIEDMONT TRIAD INTERNATIONAL AIRPORT (GSO) | RUNWAY 5R-23L GROUP VI UPGRADE. | AVIATION | 7 | GREENSBORO URBAN AREA MPO | AV-5715 | STATEWIDE MOBILITY | STATEWIDE MOBILITY | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | N/A | N/A | NO CHANGE | N/A | N/A | NO CHANGE | 2024 | 2024 | NO CHANGE
GUILFORD | PIEDMONT TRIAD INTERNATIONAL AIRPORT (GSO) | TAXIWAY F. CONSTRUCT TAXIWAY INCLUDING BRIDGE OVER TED JOHNSON PARKWAY. | AVIATION | 7 | GREENSBORO URBAN AREA MPO | AV-5803 | STATEWIDE MOBILITY | STATEWIDE MOBILITY | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | N/A | N/A | NO CHANGE | N/A | N/A | NO CHANGE | 2024 | 2024 | NO CHANGE
GUILFORD | BENJAMIN PARKWAY; WESTOVER TERRACE | BENJAMIN PARKWAY FROM ELAM AVENUE TO BATTLEGROUND AVENUE, AND WESTOVER TERRACE FROM BENJAMIN PARKWAY TO SEMINOLE DRIVE IN GREENSBORO. CONSTRUCT SIDEWALK ON BENJAMIN PARKWAY FROM ELAM AVENUE TO AYCOCK STREET, CONSTRUCT SIDEPATH ON BENJAMIN PARKWAY FROM AYC | BIKE/PED | 7 | GREENSBORO URBAN AREA MPO | EB-5986 | DIVISION 7 | DIVISION 7 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2022 | 2023 | 1 YEAR DELAY | N/A | N/A | NO CHANGE | 2024 | 2024 | NO CHANGE
GUILFORD | CEDROW DRIVE | WEST OF I-74 TO EAST OF I-74 IN HIGH POINT. CONSTRUCT MULTIUSE FACILITY ACROSS I-74. | BIKE/PED | 7 | HIGH POINT URBAN AREA MPO | EB-5989 | DIVISION 7 | DIVISION 7 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2025 | 2025 | NO CHANGE | N/A | N/A | NO CHANGE | 2026 | 2026 | NO CHANGE
GUILFORD | GREEN VALLEY ROAD | FRIENDLY AVENUE TO WESTOVER TERRACE IN GREENSBORO. CONSTRUCT SIDEWALKS. | BIKE/PED | 7 | GREENSBORO URBAN AREA MPO | EB-5997 | DIVISION 7 | DIVISION 7 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2023 | 2024 | 1 YEAR DELAY | N/A | N/A | NO CHANGE | 2025 | 2025 | NO CHANGE
GUILFORD | HIGH POINT RAILROAD ESPLANADE | LIINDSAY STREET TO CENTENNIAL STREET IN HIGH POINT. CONSTRUCT GREENWAY. | BIKE/PED | 7 | HIGH POINT URBAN AREA MPO | EB-5990 | DIVISION 7 | DIVISION 7 | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | N/A | N/A | NO CHANGE | N/A | N/A | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE
GUILFORD | JOHNSON STREET | PARRIS AVENUE TO SR 1896 (EAST HARTLEY DRIVE) IN HIGH POINT. CONSTRUCT SIDEWALK. | BIKE/PED | 7 | HIGH POINT URBAN AREA MPO | EB-5999 | DIVISION 7 | DIVISION 7 | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | N/A | N/A | NO CHANGE | N/A | N/A | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE
GUILFORD | LAWNDALE DRIVE | PISGAH CHURCH ROAD TO LAKE BRANDT ROAD IN GREENSBORO. CONSTRUCT SIDEWALK. | BIKE/PED | 7 | GREENSBORO URBAN AREA MPO | EB-5995 | DIVISION 7 | DIVISION 7 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2023 | 2023 | NO CHANGE | N/A | N/A | NO CHANGE | 2025 | 2025 | NO CHANGE
GUILFORD | NC 68 (EASTCHESTER DRIVE) | CENTENNIAL STREET TO LASSITER DRIVE IN HIGH POINT. CONSTRUCT SIDEWALK. | BIKE/PED | 7 | HIGH POINT URBAN AREA MPO | EB-5922 | DIVISION 7 | DIVISION 7 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | N/A | N/A | NO CHANGE | N/A | N/A | NO CHANGE | 2025 | 2025 | NO CHANGE
GUILFORD | OLD BATTLEGROUND ROAD | LAKE BRANDT ROAD TO BICENTENNIAL GREENWAY IN GREENSBORO. CONSTRUCT MULTIUSE PATH. | BIKE/PED | 7 | GREENSBORO URBAN AREA MPO | EB-5987 | DIVISION 7 | DIVISION 7 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2024 | 2024 | NO CHANGE | N/A | N/A | NO CHANGE | 2025 | 2025 | NO CHANGE
GUILFORD | SPRING GARDEN STREET | SR 1008 (WEST MARKET STREET) TO POMONA DRIVE AND MERRITT DRIVE TO HOLDEN ROAD IN GREENSBORO. CONSTRUCT SIDEWALK. | BIKE/PED | 7 | GREENSBORO URBAN AREA MPO | EB-5992 | DIVISION 7 | DIVISION 7 | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | N/A | N/A | NO CHANGE | N/A | N/A | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE
GUILFORD | SR 1001 (NORTH CHURCH STREET) | HENRY STREET / ELECTRA DRIVE TO LEES CHAPEL ROAD IN GREENSBORO. CONSTRUCT SIDEWALK. | BIKE/PED | 7 | GREENSBORO URBAN AREA MPO | EB-5996 | DIVISION 7 | DIVISION 7 | WILL BE REPRIORITIZED | SCHEDULED FOR DELIVERY | N/A | 2024 | PHASE ADDED | N/A | N/A | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2025 | PROJECT BECOMES COMMITTED |  | YES
GUILFORD | SR 1536 (PENNY ROAD) | CITY LAKE PARK TO PIEDMONT ENVIRONMENTAL CENTER IN HIGH POINT. CONSTRUCT MULTIUSE PATH. | BIKE/PED | 7 | HIGH POINT URBAN AREA MPO | EB-6000 | DIVISION 7 | DIVISION 7 | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | N/A | N/A | NO CHANGE | N/A | N/A | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE
GUILFORD | SR 2526 (SUMMIT AVENUE) | SULLIVAN STREET TO FOURTH STREET IN GREENSBORO. CONSTRUCT BICYCLE, PEDESTRIAN AND SAFETY IMPROVEMENTS. | BIKE/PED | 7 | GREENSBORO URBAN AREA MPO | EB-6009 | DIVISION 7 | DIVISION 7 | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | N/A | N/A | NO CHANGE | N/A | N/A | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE
GUILFORD | SUMMERFIELD SOUTH GREENWAY | US 220 TO CENTERFIELD ROAD IN SUMMERFIELD. CONSTRUCT MULTIUSE PATH. | BIKE/PED | 7 | GREENSBORO URBAN AREA MPO | EB-5900 | DIVISION 7 | DIVISION 7 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2022 | 2022 | NO CHANGE | N/A | N/A | NO CHANGE | 2024 | 2024 | NO CHANGE
GUILFORD | US 70 (WEST WENDOVER AVENUE) | NC 68 (EASTCHESTER DRIVE) TO GIBSON PARK ENTRANCE IN HIGH POINT. CONSTRUCT SIDEWALK. | BIKE/PED | 7 | HIGH POINT URBAN AREA MPO | EB-6010 | DIVISION 7 | DIVISION 7 | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | N/A | N/A | NO CHANGE | N/A | N/A | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE
GUILFORD | I-40 | SR 1860 (MACY GROVE ROAD). CONVERT GRADE SEPARATION TO INTERCHANGE. | HIGHWAY | 7 | HIGH POINT URBAN AREA MPO | I-5980 | REGION D | REGION D | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE
GUILFORD | I-40 / BUSINESS 85 / US 29 / US 70 / US 220 | US 220 / SR 1398 (FREEMAN MILL ROAD) TO US 29 / US 70 / US 220 IN GREENSBORO. ADD LANES, IMPROVE SR 1007 (RANDLEMAN ROAD) AND ELM-EUGENE STREET INTERCHANGES, AND REPLACE NORFOLK-SOUTHERN RAILROAD BRIDGE OVERPASS EAST OF ELM-EUGENE STREET. | HIGHWAY | 7 | GREENSBORO URBAN AREA MPO | I-5965 | STATEWIDE MOBILITY | STATEWIDE MOBILITY | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE
GUILFORD | I-40 / I-85 | SR 3056 (ROCK CREEK DAIRY ROAD) INTERCHANGE. UPGRADE INTERCHANGE AREA. | HIGHWAY | 7 | GREENSBORO URBAN AREA MPO | I-6004 | STATEWIDE MOBILITY | DIVISION 7 | WILL BE REPRIORITIZED | SCHEDULED FOR DELIVERY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2026 | PROJECT BECOMES COMMITTED | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2026 | PROJECT BECOMES COMMITTED | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2027 | PROJECT BECOMES COMMITTED |  | YES
GUILFORD | I-40 / US 421 | SR 1850 (SANDY RIDGE ROAD) IN GREENSBORO. INTERCHANGE IMPROVEMENTS. | HIGHWAY | 7 | GREENSBORO URBAN AREA MPO | I-5712 | STATEWIDE MOBILITY | STATEWIDE MOBILITY | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2025 | 2026 | 1 YEAR DELAY | 2025 | 2026 | 1 YEAR DELAY | 2027 | 2028 | 1 YEAR DELAY
GUILFORD | MCCONNELL ROAD | GORRELL STREET AND WILLOW HOPE STREET IN GREENSBORO. CONSTRUCT ROUNDABOUT. | HIGHWAY | 7 | GREENSBORO URBAN AREA MPO | U-6185 | DIVISION 7 | DIVISION 7 | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE
GUILFORD | NC 62 | SR 1007 (RANDLEMAN ROAD). CONSTRUCT TURN LANES. | HIGHWAY | 7 | GREENSBORO URBAN AREA MPO | U-6212 | DIVISION 7 | DIVISION 7 | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE
GUILFORD | NC 68 | SR 1523 (HICKSWOOD ROAD) TO SR 1556 (GALLIMORE DAIRY ROAD) IN HIGH POINT. UPGRADE TO SUPERSTREET. | HIGHWAY | 7 | HIGH POINT URBAN AREA MPO | U-5974 | REGION D | REGION D | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2027 | 2027 | NO CHANGE | 2027 | 2027 | NO CHANGE | 2029 | 2029 | NO CHANGE
GUILFORD | NC 68 | SR 1556 (GALLIMORE DAIRY ROAD) TO TRIAD CENTER DRIVE IN GREENSBORO. UPGRADE CORRIDOR TO SUPERSTREET. | HIGHWAY | 7 | GREENSBORO URBAN AREA MPO, HIGH POINT URBAN AREA MPO | U-6122 | REGION D | REGION D | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE
GUILFORD | NC 68 | SR 2129 (FOGLEMAN ROAD) TO SR 2017 / SR 2269 (ALCORN ROAD) IN OAK RIDGE. ACCESS MANAGEMENT IMPROVEMENTS. | HIGHWAY | 7 | GREENSBORO URBAN AREA MPO | U-6127 | REGION D | REGION D | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE
GUILFORD | PISGAH CHURCH ROAD | NORTH ELM STREET IN GREENSBORO. INTERSECTION IMPROVEMENTS. | HIGHWAY | 7 | GREENSBORO URBAN AREA MPO | U-5842 | DIVISION 7 | DIVISION 7 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2023 | 2023 | NO CHANGE | N/A | N/A | NO CHANGE | 2024 | 2024 | NO CHANGE
GUILFORD | SR 1001 (CHURCH STREET) | US 220 (WENDOVER AVENUE) TO EAST CONE BOULEVARD IN GREENSBORO. ADD LANES. | HIGHWAY | 7 | GREENSBORO URBAN AREA MPO | U-5851 | DIVISION 7 | DIVISION 7 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2028 | 2028 | NO CHANGE | 2028 | 2028 | NO CHANGE | 2030 | 2030 | NO CHANGE
GUILFORD | SR 1001 (NORTH CHURCH STREET) | SR 2516 (ARCHERGATE ROAD) AND SR 2329 (SPENCER-DIXON ROAD) IN GREENSBORO. REALIGN INTERSECTION. | HIGHWAY | 7 | GREENSBORO URBAN AREA MPO | U-6186 | DIVISION 7 | DIVISION 7 | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE
GUILFORD | SR 1007 (RANDLEMAN ROAD) | ELMSLEY DRIVE TO GLENDALE DRIVE IN GREENSBORO. WIDEN TO MULTLANES. | HIGHWAY | 7 | GREENSBORO URBAN AREA MPO | U-5850 | DIVISION 7 | DIVISION 7 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2022 | 2022 | NO CHANGE | 2022 | 2022 | NO CHANGE | 2025 | 2025 | NO CHANGE
GUILFORD | SR 1818 (JOHNSON STREET) / SR 1850 (SANDY RIDGE RO | SR 1820 (SKEET CLUB ROAD) TO SOUTH OF I-40 IN HIGH POINT. WIDEN TO FOUR LANES. | HIGHWAY | 7 | HIGH POINT URBAN AREA MPO | U-4758 | DIVISION 7 | DIVISION 7 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2022 | 2022 | NO CHANGE | 2022 | 2022 | NO CHANGE | 2024 | 2024 | NO CHANGE
GUILFORD | SR 1850 (SANDY RIDGE ROAD) | I-40 TO SR 1008 (WEST MARKET STREET) IN GREENSBORO. WIDEN TO MULTILANES. | HIGHWAY | 7 | GREENSBORO URBAN AREA MPO | U-6045 | DIVISION 7 | DIVISION 7 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2027 | 2027 | NO CHANGE | 2027 | 2027 | NO CHANGE | 2030 | 2030 | NO CHANGE
GUILFORD | SR 2085 (BENJAMIN PARKWAY / BRYAN BOULEVARD) | US 70 (WENDOVER AVENUE) TO HOLDEN ROAD IN GREENSBORO. ADD LANES. | HIGHWAY | 7 | GREENSBORO URBAN AREA MPO | U-5852 | DIVISION 7 | DIVISION 7 | SCHEDULED FOR DELIVERY | WILL BE REPRIORITIZED | 2023 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | PROJECT UNCOMMITTED | 2023 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | PROJECT UNCOMMITTED | 2025 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | PROJECT UNCOMMITTED |  | YES
GUILFORD | SR 2085 (BRYAN BOULEVARD) | NEW GARDEN ROAD AT HORSEPEN CREEK ROAD IN GREENSBORO. INTERCHANGE IMPROVEMENTS, INCLUDING NEW RAMP FROM WESTBOUND NEW GARDEN ROAD TO WESTBOUND SR 2085. | HIGHWAY | 7 | GREENSBORO URBAN AREA MPO | U-6008 | DIVISION 7 | DIVISION 7 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2027 | 2027 | NO CHANGE | 2027 | 2027 | NO CHANGE | 2029 | 2029 | NO CHANGE
GUILFORD | SR 2133 (PLEASANT RIDGE ROAD) | SR 2136 (FLEMING ROAD) IN SUMMERFIELD. CONSTRUCT TURN LANES. | HIGHWAY | 7 | GREENSBORO URBAN AREA MPO | U-6211 | DIVISION 7 | DIVISION 7 | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE
GUILFORD | SR 2835 (MCKNIGHT MILL ROAD) | SR 2842 (MINORWOOD ROAD). UPGRADE INTERSECTION. | HIGHWAY | 7 | GREENSBORO URBAN AREA MPO | U-6181 | DIVISION 7 | DIVISION 7 | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE
GUILFORD | US 220 (BATTLEGROUND AVENUE) | WESTRIDGE ROAD TO COTSWOLD AVENUE IN GREENSBORO. ADD LANES. | HIGHWAY | 7 | GREENSBORO URBAN AREA MPO | U-5892 | REGION D | REGION D | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2023 | 2023 | NO CHANGE | 2023 | 2023 | NO CHANGE | 2026 | 2026 | NO CHANGE
GUILFORD | US 29; US 70; US 220 | SR 4240 (GATE CITY BOULEVARD) TO SOUTH OF I-785 IN GREENSBORO. CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS AND SAFETY ENHANCEMENTS, INCLUDING RAMP CLOSURES AND CONSOLIDATIONS, RECONFIGURE SR 2526 (SUMMIT AVENUE) / PHILLIPS AVENUE INTERCHANGE, AND REPLACE BRI | HIGHWAY | 7 | GREENSBORO URBAN AREA MPO | U-6100 | NOT FUNDED | NOT FUNDED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE
GUILFORD | US 70 (WENDOVER AVENUE) | NC 68 (EASTCHESTER DRIVE) IN HIGH POINT TO SR 1541 (GUILFORD COLLEGE ROAD) IN GREENSBORO. WIDEN TO 6 LANES AND CONSTRUCT SIDEWALKS. | HIGHWAY | 7 | HIGH POINT URBAN AREA MPO, GREENSBORO URBAN AREA MPO | U-6121 | DIVISION 7 | DIVISION 7 | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE
GUILFORD | US 70 / US 220 (WENDOVER AVENUE) | US 220 (BATTLEGROUND AVENUE) IN GREENSBORO. RECONFIGURE BATTLEGROUND AVENUE, LAWNDALE DRIVE, AND WESTOVER TERRACE BETWEEN FERNWOOD DRIVE AND WENDOVER AVENUE. IMPROVE TRAFFIC FLOW AND SAFETY. IMPROVE WENDOVER AVENUE CONNECTIONS AT WESTOVER TERRACE, BATTLEG | HIGHWAY | 7 | GREENSBORO URBAN AREA MPO | U-6108 | REGION D | REGION D | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE
GUILFORD | VARIOUS | LAWNDALE DRIVE AND PISGAH CHURCH ROAD IN GREENSBORO. INTERSECTION IMPROVEMENTS AT LAWNDALE ROAD AND PISGAH CHURCH ROAD, AT LAWNDALE ROAD AND MARTINSVILLE ROAD, AND AT MARTINSVILLE ROAD AND PISGAH CHURCH ROAD | HIGHWAY | 7 | GREENSBORO URBAN AREA MPO | U-5812 | DIVISION 7 | DIVISION 7 | SCHEDULED FOR DELIVERY | WILL BE REPRIORITIZED | 2023 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | PROJECT UNCOMMITTED | N/A | N/A | NO CHANGE | 2024 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | PROJECT UNCOMMITTED |  | YES
GUILFORD | WEST FRIENDLY AVENUE | PEMBROKE ROAD INTERSECTION AND GREEN VALLEY ROAD INTERSECTION IN GREENSBORO. CONSTRUCT INTERSECTION AND PEDESTRIAN IMPROVEMENTS. FROM PEMBROKE ROAD TO GREEN VALLEY ROAD, CONSTRUCT ROADWAY AND ACCESS MANAGEMENT IMPROVEMENTS. | HIGHWAY | 7 | GREENSBORO URBAN AREA MPO | U-6129 | DIVISION 7 | DIVISION 7 | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE
GUILFORD | NCRR / NORFOLK SOUTHERN MAIN LINE | HOSKINS STREET IN HIGH POINT. CONSTRUCT GRADE SEPARATION AND CLOSE CROSSING 722351T. | RAIL | 7 | HIGH POINT URBAN AREA MPO | P-5752 | DIVISION 7 | DIVISION 7 | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE
GUILFORD | NCRR NORFOLK SOUTHERN | POMONA YARD. EXTEND AUXILIARY TRACK AND ADD POWER TURNOUTS. | RAIL | 7 | GREENSBORO URBAN AREA MPO | P-5714 | REGION D | REGION D | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | N/A | N/A | NO CHANGE | N/A | N/A | NO CHANGE | 2024 | 2025 | 1 YEAR DELAY | YES
GUILFORD | NCRR NORFOLK SOUTHERN H LINE | SOUTH ENGLISH STREET IN GREENSBORO. CONSTRUCT GRADE SEPARATION AND CLOSE CROSSING 722955X. | RAIL | 7 | GREENSBORO URBAN AREA MPO | P-5747 | REGION D | REGION D | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2025 | 2025 | NO CHANGE | N/A | N/A | NO CHANGE | 2026 | 2026 | NO CHANGE
GUILFORD | NORFOLK SOUTHERN | JAMESTOWN SIDING IN JAMESTOWN. CONSTRUCT EXTENSION. | RAIL | 7 | HIGH POINT URBAN AREA MPO | P-5721 | STATEWIDE MOBILITY | STATEWIDE MOBILITY | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | N/A | N/A | NO CHANGE | N/A | N/A | NO CHANGE | 2024 | 2024 | NO CHANGE
GUILFORD | NORFOLK SOUTHERN H LINE | CONSTRUCT GRADE SEPARATION AT FRANKLIN BOULEVARD CROSSING (722959A) IN GREENSBORO, AND CLOSE O'FERRELL STREET CROSSING (722961B). | RAIL | 7 | GREENSBORO URBAN AREA MPO | P-5709 | REGION D | REGION D | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2022 | 2022 | NO CHANGE | 2022 | 2022 | NO CHANGE | 2024 | 2024 | NO CHANGE
GUILFORD | NORFOLK SOUTHERN MAIN LINE | SR 1584 (YANCEYVILLE STREET) IN GREENSBORO. CONSTRUCT GRADE SEPARATION AND CLOSE CROSSING 722542D. | RAIL | 7 | GREENSBORO URBAN AREA MPO | P-5735 | STATEWIDE MOBILITY | STATEWIDE MOBILITY | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE
GUILFORD | NORTH CAROLINA RAILROAD (NCRR) / NORFOLK SOUTHERN | SR 1424 (HILLTOP ROAD) IN GREENSBORO. CONVERT AT-GRADE CROSSING TO GRADE SEPARATION. | RAIL | 7 | GREENSBORO URBAN AREA MPO | P-5713 | STATEWIDE MOBILITY | STATEWIDE MOBILITY | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2024 | 2025 | 1 YEAR DELAY | 2024 | 2025 | 1 YEAR DELAY | 2026 | 2027 | 1 YEAR DELAY
GUILFORD, FORSYTH | I-40 | NC 66 TO US 421 / BUSINESS 40. | HIGHWAY | 7, 9 | HIGH POINT URBAN AREA MPO, WINSTON-SALEM URBAN AREA MPO | I-5981C | STATEWIDE MOBILITY | STATEWIDE MOBILITY | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE
HALIFAX | (IXA) HALIFAX NORTHAMPTON REGIONAL AIRPORT | CONSTRUCT TAXI LANE AND PREPARATION FOR ADDITIONAL T-HANGARS. | AVIATION | 4 | PEANUT BELT RPO | AV-5822 | DIVISION 4 | DIVISION 4 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | N/A | N/A | NO CHANGE | N/A | N/A | NO CHANGE | 2024 | 2024 | NO CHANGE
HALIFAX | HALIFAX NORTHAMPTON REGIONAL AIRPORT (IXA) | CONSTRUCT TAXILANE AND APRON. | AVIATION | 4 | PEANUT BELT RPO | AV-5833 | DIVISION 4 | DIVISION 4 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | N/A | N/A | NO CHANGE | N/A | N/A | NO CHANGE | 2026 | 2026 | NO CHANGE
HALIFAX | EAST 10TH STREET | MARSHALL STREET TO PARKE AVENUE IN ROANOKE RAPIDS. CONSTRUCT SIDEWALK ON BOTH SIDES OF ROAD. | BIKE/PED | 4 | PEANUT BELT RPO | EB-5843 | DIVISION 4 | DIVISION 4 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | N/A | N/A | NO CHANGE | N/A | N/A | NO CHANGE | 2025 | 2025 | NO CHANGE
HALIFAX, NORTHAMPTON | CSX A LINE | CONSTRUCT NEW MAIN TRACK BETWEEN MP A-80.7 AND MP A-82.4 INCLUDING REHABILITATION OF CSX SA-LINE BRIDGE OVER ROANOKE RIVER. NEW CONNECTION BETWEEN A-LINE AND SA-LINE AT MP A-80.7. RECONSTRUCT MAIN TRACK BETWEEN MP A-82.4 AND MP A-84.7. CREATE SECOND MAIN. | RAIL | 1, 4 | PEANUT BELT RPO | P-5741 | STATEWIDE MOBILITY | STATEWIDE MOBILITY | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE
HARNETT | NC 55 | NC 27 IN COATS TO SR 1006 (OLD STAGE ROAD (NORTH)). WIDEN ROADWAY. | HIGHWAY | 6 | MID-CAROLINA RPO | R-5953 | NOT FUNDED | NOT FUNDED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE
HARNETT | NC 87/24 | SR 1117 (NURSERY ROAD). INTERSECTION IMPROVEMENTS. PROJECT FUNDED USING STBG-DA FUNDS. | HIGHWAY | 6 | FAYETTEVILLE AREA MPO | U-5933 | STATEWIDE MOBILITY | STATEWIDE MOBILITY | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2023 | 2023 | NO CHANGE | 2023 | 2023 | NO CHANGE | 2025 | 2023 | 2 YEAR ACCELERATION
HARNETT | US 401 (NORTH MAIN STREET) | PARKER LANE TO MCKINNEY PARKWAY. CONSTRUCT MEDIAN. | HIGHWAY | 6 | MID-CAROLINA RPO | R-5890 | REGION C | REGION C | SCHEDULED FOR DELIVERY | WILL BE REPRIORITIZED | 2028 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | PROJECT UNCOMMITTED | 2028 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | PROJECT UNCOMMITTED | 2030 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | PROJECT UNCOMMITTED
HAYWOOD | US 19 (SOCO ROAD) | SR 1304 (FIE TOP ROAD AT GHOST TOWN IN THE SKY) TO BLUE RIDGE PARKWAY. MODERNIZE ROADWAY. | HIGHWAY | 14 | FRENCH BROAD RIVER MPO | U-6160 | NOT FUNDED | NOT FUNDED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE
HAYWOOD | US 23 BUSINESS (SOUTH MAIN STREET) | SR 1164 (HYATT CREEK ROAD) TO US 276 (PIGEON STREET). WIDEN TO MULTI-LANES. | HIGHWAY | 14 | FRENCH BROAD RIVER MPO | U-4712 | DIVISION 14 | DIVISION 14 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2027 | 2027 | NO CHANGE | 2027 | 2027 | NO CHANGE | 2030 | 2030 | NO CHANGE
HAYWOOD | US 276 | SR 1134 (CRYMES COVE ROAD) AND RACCOON ROAD. INTERSECTION REALIGNMENT. | HIGHWAY | 14 | FRENCH BROAD RIVER MPO | U-6158 | DIVISION 14 | DIVISION 14 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2028 | 2028 | NO CHANGE | 2028 | 2028 | NO CHANGE | 2030 | 2030 | NO CHANGE
HAYWOOD | US 276 (JONATHAN CREEK) | US 19 TO I-40 UPGRADE. MODERNIZE ROADWAY. | HIGHWAY | 14 | LAND-OF-SKY RPO, FRENCH BROAD RIVER MPO | R-5921 | DIVISION 14 | DIVISION 14 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2023 | 2023 | NO CHANGE | 2023 | 2023 | NO CHANGE | 2024 | 2024 | NO CHANGE
HAYWOOD | US 276 (RUSS AVENUE) | US 23-74 (GREAT SMOKEY MOUNTAIN EXPRESSWAY) TO US 19 (DELLWOOD ROAD). ACCESS MANAGEMENT. | HIGHWAY | 14 | FRENCH BROAD RIVER MPO | U-6159 | DIVISION 14 | DIVISION 14 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2028 | 2028 | NO CHANGE | 2028 | 2028 | NO CHANGE | 2030 | 2030 | NO CHANGE
HAYWOOD, BUNCOMBE | US 19, US 23 | SR 1836 (CHESTNUT MOUNTAIN ROAD) TO SR 1200 (WIGGINS ROAD). UPGRADE ROADWAY. | HIGHWAY | 13, 14 | FRENCH BROAD RIVER MPO | U-6048 | DIVISION 13, 14 | DIVISION 14 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2028 | 2028 | NO CHANGE | 2028 | 2028 | NO CHANGE | 2030 | 2030 | NO CHANGE
HAYWOOD, JACKSON | US 23/US 74 (GREAT SMOKEY MOUNTAINS EXPRESSWAY) | SR 1777 (BALSAM VIEW DRIVE) TO SR 1158 (OLD BALSAM ROAD) MODERNIZE ROADWAY. | HIGHWAY | 14 | FRENCH BROAD RIVER MPO, SOUTHWESTERN RPO | U-6172 | DIVISION 14 | DIVISION 14 | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE
HENDERSON | BLYTHE STREET | BLYTHE STREET, US 64 (BREVARD ROAD) TO NC 191 (HAYWOOD ROAD). CONSTRUCT SIDEWALKS. | BIKE/PED | 14 | FRENCH BROAD RIVER MPO | EB-5860 | DIVISION 14 | DIVISION 14 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2025 | 2025 | NO CHANGE | 2025 | 2025 | NO CHANGE | 2026 | 2026 | NO CHANGE
HENDERSON | GROVE STREET | BARNWELL STREET TO US 176 (SPARTANBURG HIGHWAY). CONSTRUCT SIDEWALK. | BIKE/PED | 14 | FRENCH BROAD RIVER MPO | EB-5963 | DIVISION 14 | DIVISION 14 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2025 | 2025 | NO CHANGE | 2025 | 2025 | NO CHANGE | 2026 | 2026 | NO CHANGE
HENDERSON | I-26 | US 25 TO US 64 | HIGHWAY | 14 | FRENCH BROAD RIVER MPO | I-4400A | NOT FUNDED | NOT FUNDED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE
HENDERSON | I-26 | US 64 INTERCHANGE IMPROVEMENTS | HIGHWAY | 14 | FRENCH BROAD RIVER MPO | I-4400BA | STATEWIDE MOBILITY | DIVISION 14 | WILL BE REPRIORITIZED | SCHEDULED FOR DELIVERY | N/A | 2027 | PHASE ADDED | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2027 | PROJECT BECOMES COMMITTED | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2029 | PROJECT BECOMES COMMITTED |  | YES
HENDERSON | NC 191 | SR 1381 (MOUNTAIN ROAD) TO NC 280 SOUTH OF MILLS RIVER. | HIGHWAY | 14 | FRENCH BROAD RIVER MPO | R-2588B | DIVISION 14 | DIVISION 14 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2022 | 2022 | NO CHANGE | 2022 | 2022 | NO CHANGE | 2024 | 2024 | NO CHANGE
HENDERSON | NC 225 (SOUTH MAIN STREET) | SOUTH MAIN STREET AT SOUTH KING STREET TO US 176. WIDEN BRIDGE 440143 TO 5-LANES. | HIGHWAY | 14 | FRENCH BROAD RIVER MPO | U-6049 | REGION G | REGION G | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2023 | 2023 | NO CHANGE | 2023 | 2023 | NO CHANGE | 2026 | 2026 | NO CHANGE
HENDERSON | NC 280 (BOYLSTON HIGHWAY) | NC 191 (HAYWOOD ROAD) TO NC 191 (OLD HAYWOOD ROAD). CONSTRUCT ACCESS MANAGEMENT AND INTERSECTION IMPROVEMENTS. | HIGHWAY | 14 | FRENCH BROAD RIVER MPO | U-6124 | NOT FUNDED | NOT FUNDED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE
HENDERSON | SR 1127 (KANUGA ROAD) | US 25 BUSINESS (CHURCH STREET) TO SR 1123 (LITTLE RIVER ROAD). UPGRADE ROADWAY. | HIGHWAY | 14 | FRENCH BROAD RIVER MPO | R-5748 | DIVISION 14 | DIVISION 14 | SCHEDULED FOR DELIVERY | WILL BE REPRIORITIZED | 2027 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | PROJECT UNCOMMITTED | 2027 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | PROJECT UNCOMMITTED | 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | PROJECT UNCOMMITTED |  | YES
HENDERSON | SR 1170 (WHITE STREET) | SR 1171 (WILLOW ROAD) TO US 176 (SPARTANBURG HIGHWAY). REALIGN AND EXTEND ROADWAY. | HIGHWAY | 14 | FRENCH BROAD RIVER MPO | U-5886 | DIVISION 14 | DIVISION 14 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2023 | 2023 | NO CHANGE | 2023 | 2023 | NO CHANGE | 2026 | 2026 | NO CHANGE
HENDERSON | US 64 | SR 1180 (BLYTHE STREET) TO SR 1173 (WHITE PINE DRIVE)/SR 1186 (DANIEL DRIVE). WIDEN ROADWAY. | HIGHWAY | 14 | FRENCH BROAD RIVER MPO | U-5783 | REGION G | REGION G | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2022 | 2022 | NO CHANGE | 2022 | 2022 | NO CHANGE | 2024 | 2024 | NO CHANGE
HERTFORD | TRI-COUNTY AIRPORT (ASJ) | RUNWAY EXTENSION. | AVIATION | 1 | PEANUT BELT RPO | AV-5778 | DIVISION 1 | DIVISION 1 | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | N/A | N/A | NO CHANGE | N/A | N/A | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE
HERTFORD | TRI-COUNTY AIRPORT (ASJ) | CONSTRUCT ACCESS ROAD TO T-HANGARS. | AVIATION | 1 | PEANUT BELT RPO | AV-5878 | NOT FUNDED | NOT FUNDED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | N/A | N/A | NO CHANGE | N/A | N/A | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE
HERTFORD | US 13/NC 11 | NC 11/NC 561 INTERSECTION NEAR AHOSKIE TO US 13/US 158/NC 45 INTERSECTION NEAR WINTON. | HIGHWAY | 1 | PEANUT BELT RPO | R-5311B | REGION A | REGION A | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2028 | 2028 | NO CHANGE | 2028 | 2028 | NO CHANGE | 2030 | 2031 | 1 YEAR DELAY
HERTFORD | US 13/NC 42/NC 561 (MEMORIAL DRIVE) | PEACHTREE STREET TO NC 42. WIDEN TO MULTI-LANES. | HIGHWAY | 1 | PEANUT BELT RPO | R-5796 | REGION A | REGION A | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2024 | 2024 | NO CHANGE | 2024 | 2024 | NO CHANGE | 2025 | 2025 | NO CHANGE
HOKE | SR 1305 (WAYSIDE ROAD); SR 1418 (LINDSAY ROAD) | SR 1305, US 401 TO PLANK ROAD, AND SR 1418, US 401 TO SR 1406 (ROCKFISH ROAD). WIDEN TO MULTILANES. | HIGHWAY | 8 | FAYETTEVILLE AREA MPO | U-5753 | DIVISION 8 | DIVISION 8 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2022 | 2022 | NO CHANGE | 2022 | 2022 | NO CHANGE | 2024 | 2026 | 2 YEAR DELAY | YES
HOKE | SR 1406 (ROCKFISH ROAD); NEW ROUTE (GILLIS HILL RO | SR 1406 (ROCKFISH ROAD) FROM SR 1003 (CAMDEN ROAD) TO NORTH OF WESTFIELD DRIVE AND GILLIS HILL ROAD EXTENSION FROM NORTH OF WESTFIELD DRIVE TO SR 1418 (LINDSAY ROAD). WIDEN TO MULTI-LANES, PART ON NEW LOCATION. | HIGHWAY | 8 | FAYETTEVILLE AREA MPO | U-5857 | DIVISION 8 | DIVISION 8 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2027 | 2027 | NO CHANGE | 2027 | 2027 | NO CHANGE | 2029 | 2029 | NO CHANGE
HOKE, MOORE | NC 211 | US 15 / US 501 IN ABERDEEN TO EAST OF SR 1244 (WEST PALMER STREET) / SR 1311 (MOCKINGBIRD HILL ROAD) IN RAEFORD. WIDEN TO MULTILANES. | HIGHWAY | 8 | LUMBER RIVER RPO, TRIANGLE AREA RPO | R-5709 | REGION E | REGION E | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2021 | 2021 | NO CHANGE | 2021 | 2021 | NO CHANGE | 2024 | 2024 | NO CHANGE
HOKE, SCOTLAND | US 401 | US 401 BUSINESS NORTH OF LAURINBURG TO US 401 BUSINESS EAST OF RAEFORD. CONSTRUCT PASSING LANES, TURN LANES, AND PAVED SHOULDERS. | HIGHWAY | 8 | LUMBER RIVER RPO, FAYETTEVILLE AREA MPO | R-3333 | NOT FUNDED | NOT FUNDED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE
IREDELL | STATESVILLE REGIONAL AIRPORT (SVH) | RELOCATE EAST AVIATION DRIVE TO ALLOW FOR FUTURE RUNWAY EXTENSION. | AVIATION | 12 | CHARLOTTE REGIONAL TPO | AV-5896 | DIVISION 12 | DIVISION 12 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2026 | 2026 | NO CHANGE | N/A | N/A | NO CHANGE | 2027 | 2027 | NO CHANGE
IREDELL | I-77 | I-77 AT SR 1302 (CORNELIUS ROAD). CONVERT GRADE SEPARATION TO INTERCHANGE. | HIGHWAY | 12 | CHARLOTTE REGIONAL TPO | I-5962 | STATEWIDE MOBILITY | STATEWIDE MOBILITY | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2026 | 2027 | 1 YEAR DELAY | 2026 | 2027 | 1 YEAR DELAY | 2028 | 2029 | 1 YEAR DELAY
IREDELL | NC 115 | SR 1645 (OLD WILKESBORO ROAD) TO HARTNESS ROAD. WIDEN TO MULTI-LANES. | HIGHWAY | 12 | CHARLOTTE REGIONAL TPO | U-5779 | REGION F | REGION F | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE
IREDELL | NC 150 | INTERSECTION OF NC 150 AND SR 2399 (WIGGINS ROAD). REALIGN INTERSECTION. | HIGHWAY | 12 | CHARLOTTE REGIONAL TPO | U-5780 | REGION F | REGION F | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | UNDERWAY | UNDERWAY | NO CHANGE | UNDERWAY | UNDERWAY | NO CHANGE | 2024 | 2024 | NO CHANGE
IREDELL | NC 150 (OAK RIDGE FARM HIGHWAY) | NC 115 TO NC 801 (PARK AVENUE). WIDEN TO MULTI-LANES. | HIGHWAY | 12 | CHARLOTTE REGIONAL TPO | U-5960 | REGION F | REGION F | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE
IREDELL | NC 3 | CABARRUS-IREDELL COUNTY LINE TO SR 1147 (ROCKY RIVER ROAD). WIDEN TO MULTI-LANES. | HIGHWAY | 12 | CHARLOTTE REGIONAL TPO | U-6145 | NOT FUNDED | NOT FUNDED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE
IREDELL | SR 1005 (OLD MOUNTAIN ROAD) | US 21/NC 115 (NORTH MAIN STREET) TO SR 1004 (BUFFALO SHOALS ROAD). WIDEN TO FOUR LANES WITH A MEDIAN. | HIGHWAY | 12 | CHARLOTTE REGIONAL TPO | U-6175 | NOT FUNDED | NOT FUNDED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE
IREDELL | SR 1100 (BRAWLEY SCHOOL ROAD) | I-77 TO US 21 | HIGHWAY | 12 | CHARLOTTE REGIONAL TPO | R-3833C | DIVISION 12 | DIVISION 12 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | UNDERWAY | UNDERWAY | NO CHANGE | UNDERWAY | UNDERWAY | NO CHANGE | 2024 | 2024 | NO CHANGE
IREDELL | SR 1109 (WILLIAMSON ROAD) | I-77 TO SR 1100 (BRAWLEY SCHOOL ROAD). WIDEN TO MULTI-LANES. | HIGHWAY | 12 | CHARLOTTE REGIONAL TPO | R-5100A | DIVISION 12 | DIVISION 12 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2020 | 2020 | NO CHANGE | 2020 | 2020 | NO CHANGE | 2025 | 2025 | NO CHANGE
IREDELL | SR 1109 (WILLIAMSON ROAD) | SR 1100 (BRAWLEY SCHOOL ROAD) TO NC 150. WIDEN TO MULTI-LANES. | HIGHWAY | 12 | CHARLOTTE REGIONAL TPO | R-5100B | DIVISION 12 | DIVISION 12 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2019 | 2019 | NO CHANGE | 2019 | 2019 | NO CHANGE | 2025 | 2025 | NO CHANGE
IREDELL | SR 1246 (FAIRVIEW ROAD) | EXTEND SR 1246 (FAIRVIEW ROAD) OVER I-77 TO CONNECT WITH SR 1206 (ALCOVE ROAD) AND CONSTRUCT PARALLEL NORTH-SOUTH CONNECTOR ROADS TO SR 1109 (WILLIAMSON ROAD). | HIGHWAY | 12 | CHARLOTTE REGIONAL TPO | U-5817 | DIVISION 12 | DIVISION 12 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2019 | 2019 | NO CHANGE | 2019 | 2019 | NO CHANGE | 2025 | 2025 | NO CHANGE
IREDELL | SR 1305 (OATES ROAD - MIDNIGHT LANE) | US 21 (CHARLOTTE HIGHWAY) TO SR 1474 (BLUEFIELD ROAD). WIDEN TO THREE-LANES WITH OVERPASS OVER I-77. | HIGHWAY | 12 | CHARLOTTE REGIONAL TPO | U-5816 | DIVISION 12 | DIVISION 12 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2026 | 2026 | NO CHANGE | 2026 | 2026 | NO CHANGE | 2029 | 2029 | NO CHANGE
IREDELL | US 21 | INTERSECTION OF US 21 AND SR 2375 (HOUSTON ROAD)/SR 1312 (FLOWER HOUSE ROAD). REALIGN AND SIGNALIZE. | HIGHWAY | 12 | CHARLOTTE REGIONAL TPO | R-5711 | REGION F | REGION F | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | UNDERWAY | UNDERWAY | NO CHANGE | UNDERWAY | UNDERWAY | NO CHANGE | 2025 | 2025 | NO CHANGE
IREDELL | US 21 - NC 115 | CEDAR LANE IN TROUTMAN TO BARIUM LANE IN BARIUM SPRINGS. WIDEN TO MULTI-LANES. | HIGHWAY | 12 | CHARLOTTE REGIONAL TPO | R-2522 | REGION F | REGION F | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE
IREDELL | US 21 (CHARLOTTE HIGHWAY) | NC 150 (PLAZA DRIVE) TO SR 1245 (MEDICAL PARK ROAD). WIDEN TO 4-LANES DIVIDED. | HIGHWAY | 12 | CHARLOTTE REGIONAL TPO | U-6037 | DIVISION 12 | DIVISION 12 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2027 | 2027 | NO CHANGE | 2027 | 2027 | NO CHANGE | 2030 | 2030 | NO CHANGE
IREDELL | US 64 (DAVIE AVENUE) | US 64 (DAVIE AVENUE) AND US 21 (SULLIVAN ROAD). CONVERT 5-APPROACH INTERSECTION TO A SINGLE LANE ROUNDABOUT. | HIGHWAY | 12 | CHARLOTTE REGIONAL TPO | U-5964 | REGION F | REGION F | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2024 | 2024 | NO CHANGE | 2024 | 2024 | NO CHANGE | 2026 | 2026 | NO CHANGE
IREDELL, CATAWBA | NC 150 | EAST OF SR 1840 (GREENWOOD ROAD) IN CATAWBA COUNTY TO WEST OF SR 1303/SR 1180 (PERTH ROAD/DOOLIE ROAD) IN IREDELL COUNTY. WIDEN TO 4-LANES. SR 1383/SR 1180 TO US 21 IN IREDELL COUNTY. WIDEN TO 6-LANES. | HIGHWAY | 12 | CHARLOTTE REGIONAL TPO, GREATER HICKORY MPO | R-2307B | REGION F | REGION F | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | UNDERWAY | UNDERWAY | NO CHANGE | UNDERWAY | UNDERWAY | NO CHANGE | 2025 | 2025 | NO CHANGE
JACKSON | NC 107 | 500 FEET SOUTH OF SR 1135 (SHOOK COVE ROAD) TO 1000 FEET NORTH OF THE LAKE TUCKASEEGEE DAM. | HIGHWAY | 14 | SOUTHWESTERN RPO | R-5841A | DIVISION 14 | NOT FUNDED | SCHEDULED FOR DELIVERY | WILL BE REPRIORITIZED | 2028 | NOT FUNDED | PROJECT NO LONGER FUNDED | 2028 | NOT FUNDED | PROJECT NO LONGER FUNDED | 2030 | NOT FUNDED | PROJECT NO LONGER FUNDED |  | YES
JACKSON | NC 107 (US 23 BUSINESS) | NC 116 TO US 23 BUSINESS. US 23 BUSINESS, SR 1432 (SKYLAND DRIVE) TO MUNICIPAL DRIVE. CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | HIGHWAY | 14 | SOUTHWESTERN RPO | R-5600 | REGION G | REGION G | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2022 | 2022 | NO CHANGE | 2022 | 2022 | NO CHANGE | 2025 | 2025 | NO CHANGE
JACKSON | US 64 | NC 107 INTERSECTION. IMPROVE INTERSECTION AND ADD AUXILLARY LANE FROM PEBBLE CREEK DRIVE TO US 64/NC 107 INTERSECTION. | HIGHWAY | 14 | SOUTHWESTERN RPO | R-5881 | NOT FUNDED | DIVISION 14 | WILL BE REPRIORITIZED | SCHEDULED FOR DELIVERY | NOT FUNDED | 2028 | PROJECT BECOMES COMMITTED | NOT FUNDED | 2028 | PROJECT BECOMES COMMITTED | NOT FUNDED | 2030 | PROJECT BECOMES COMMITTED |  | YES
JACKSON | US 74 (GREAT SMOKEY MOUNTAINS EXPRESSWAY) | US 441 GATEWAY INTERCHANGE TO SR 1391 (WEST PINEY MOUNTAIN ROAD). MODERNIZE ROADWAY, INCLUDING REPLACEMENT OF BRIDGE 490043 OVER THE TUCKASEGEE RIVER. | HIGHWAY | 14 | SOUTHWESTERN RPO | R-5907 | DIVISION 14 | DIVISION 14 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2028 | 2028 | NO CHANGE | 2028 | 2028 | NO CHANGE | 2030 | 2030 | NO CHANGE
JOHNSTON | EAST CLAYTON CONNECTOR GREENWAY | SR 2851 (EAST FRONT STREET) TO SR 1902 (GLEN LAUREL ROAD). CONSTRUCT GREENWAY. | BIKE/PED | 4 | CAPITAL AREA MPO | EB-6016 | DIVISION 4 | DIVISION 4 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2027 | 2027 | NO CHANGE | N/A | N/A | NO CHANGE | 2028 | 2028 | NO CHANGE
JOHNSTON | MOUNTAINS TO SEA TRAIL | FOX RIDGE ROAD TO NEUSE RIVER BRIDGE. CONSTRUCT GREENWAY. | BIKE/PED | 4 | CAPITAL AREA MPO | EB-6017 | DIVISION 4 | DIVISION 4 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | N/A | N/A | NO CHANGE | N/A | N/A | NO CHANGE | 2028 | 2028 | NO CHANGE
JOHNSTON | CLAYTON | CLAYTON SIGNAL SYSTEM. | HIGHWAY | 4 | CAPITAL AREA MPO | U-5943 | REGION A | REGION A | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2023 | 2023 | NO CHANGE | 2023 | 2023 | NO CHANGE | 2025 | 2025 | NO CHANGE
JOHNSTON | I-95 | US 70 BUSINESS. UPGRADE INTERCHANGE. | HIGHWAY | 4 | UPPER COASTAL PLAIN RPO | I-5972 | REGION A | REGION A | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | UNDERWAY | UNDERWAY | NO CHANGE | UNDERWAY | UNDERWAY | NO CHANGE | 2024 | 2024 | NO CHANGE
JOHNSTON | I-95 | US 701/NC 96. CONSTRUCT INTERCHANGE. | HIGHWAY | 4 | UPPER COASTAL PLAIN RPO | I-5974 | REGION A | REGION A | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2026 | 2026 | NO CHANGE | 2026 | 2026 | NO CHANGE | 2028 | 2028 | NO CHANGE
JOHNSTON | I-95 | SR 1007 (BROGDEN ROAD). IMPROVE INTERCHANGE. | HIGHWAY | 4 | UPPER COASTAL PLAIN RPO | I-6061 | DIVISION 4 | DIVISION 4 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2027 | 2027 | NO CHANGE | 2027 | 2027 | NO CHANGE | 2029 | 2029 | NO CHANGE
JOHNSTON | I-95 | SR 2339 (BAGLEY ROAD). IMPROVE INTERCHANGE. | HIGHWAY | 4 | UPPER COASTAL PLAIN RPO | I-6062 | DIVISION 4 | DIVISION 4 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2027 | 2027 | NO CHANGE | 2027 | 2027 | NO CHANGE | 2029 | 2029 | NO CHANGE
JOHNSTON | NC 210 | NC 50 TO SR 1330 (RALEIGH ROAD). UPGRADE TO SUPERSTREET. | HIGHWAY | 4 | CAPITAL AREA MPO | U-6203 | DIVISION 4 | DIVISION 4 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2026 | 2026 | NO CHANGE | 2026 | 2026 | NO CHANGE | 2028 | 2028 | NO CHANGE
JOHNSTON | NC 242 | SR 1168 (TARHEEL ROAD) TO I-40. WIDEN ROADWAY. | HIGHWAY | 4 | UPPER COASTAL PLAIN RPO | R-5761 | DIVISION 4 | DIVISION 4 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2027 | 2027 | NO CHANGE | 2027 | 2027 | NO CHANGE | 2029 | 2029 | NO CHANGE
JOHNSTON | NC 42 | NC 50 TO US 70 BUSINESS. WIDEN TO MULTI-LANES. | HIGHWAY | 4 | CAPITAL AREA MPO | R-3410 | REGION A | REGION A | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2027 | 2027 | NO CHANGE | 2027 | 2027 | NO CHANGE | 2029 | 2029 | NO CHANGE
JOHNSTON | NC 42 | SR 1003 (BUFFALO ROAD) TO WILSON COUNTY LINE. MODERNIZE ROADWAY. | HIGHWAY | 4 | CAPITAL AREA MPO, UPPER COASTAL PLAIN RPO | U-5998 | DIVISION 4 | DIVISION 4 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2025 | 2025 | NO CHANGE | 2025 | 2025 | NO CHANGE | 2027 | 2027 | NO CHANGE
JOHNSTON | NEW ROUTE | SR 1010 (CLEVELAND ROAD) TO NC 42. CONSTRUCT ROADWAY ON NEW LOCATION. | HIGHWAY | 4 | CAPITAL AREA MPO | U-6208 | DIVISION 4 | DIVISION 4 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2027 | 2027 | NO CHANGE | 2027 | 2027 | NO CHANGE | 2029 | 2029 | NO CHANGE
JOHNSTON | SR 1003 (BUFFALO ROAD) | US 70 TO SR 1934 (OLD BEULAH ROAD). WIDEN TO THREE LANES. | HIGHWAY | 4 | UPPER COASTAL PLAIN RPO | R-5718 | DIVISION 4 | DIVISION 4 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2022 | 2022 | NO CHANGE | 2022 | 2022 | NO CHANGE | 2025 | 2025 | NO CHANGE
JOHNSTON | SR 1010 (CLEVELAND ROAD) | NC 42 TO SR 1555 (BARBER MILL ROAD). WIDEN TO MULTI-LANES. | HIGHWAY | 4 | CAPITAL AREA MPO | U-6216 | DIVISION 4 | DIVISION 4 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2027 | 2027 | NO CHANGE | 2027 | 2027 | NO CHANGE | 2029 | 2029 | NO CHANGE
JOHNSTON | SR 1501 (SWIFT CREEK ROAD) | AIRPORT INDUSTRIAL DRIVE TO DRIVEWAY JUST NORTH OF JOHNSTON COUNTY AIRPORT. WIDEN ROADWAY. | HIGHWAY | 4 | UPPER COASTAL PLAIN RPO | R-5950 | DIVISION 4 | DIVISION 4 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2027 | 2027 | NO CHANGE | 2027 | 2027 | NO CHANGE | 2029 | 2029 | NO CHANGE
JOHNSTON | US 301/NC 39/NC 96 | SR 1623 (BOOKER DAIRY ROAD) TO SR 2302 (RICKS ROAD). CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | HIGHWAY | 4 | UPPER COASTAL PLAIN RPO | U-5726 | DIVISION 4 | DIVISION 4 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2025 | 2025 | NO CHANGE | 2025 | 2025 | NO CHANGE | 2027 | 2027 | NO CHANGE
JOHNSTON | US 70 | US 301 TO I-95. ACCESS MANAGEMENT. | HIGHWAY | 4 | UPPER COASTAL PLAIN RPO | R-5795 | REGION A | REGION A | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2027 | 2027 | NO CHANGE | 2027 | 2027 | NO CHANGE | 2029 | 2029 | NO CHANGE
JOHNSTON | US 70 | WEST OF SR 2372 (EDWARDS ROAD / NORTH PEARL STREET) TO EAST OF SR 2314 (PONDFIELD ROAD). UPGRADE TO FREEWAY STANDARDS. | HIGHWAY | 4 | UPPER COASTAL PLAIN RPO | R-5829B | STATEWIDE MOBILITY | STATEWIDE MOBILITY | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE
JOHNSTON | JOHNSTON COUNTY | PURCHASE EXPANSION VEHICLES. | PUBLIC TRANSIT | 4 | UPPER COASTAL PLAIN RPO, CAPITAL AREA MPO | TA-6720 | DIVISION 4 | DIVISION 4 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | N/A | N/A | NO CHANGE | N/A | N/A | NO CHANGE | 2026 | 2026 | NO CHANGE
JOHNSTON | NS/NCRR H LINE | CONSTRUCT GRADE SEPARATION AT SR 1553 (SHOTWELL ROAD). CLOSE EXISTING AT-GRADE CROSSING IN CLAYTON. | RAIL | 4 | CAPITAL AREA MPO | P-5743 | NOT FUNDED | NOT FUNDED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE
JOHNSTON, WAKE | US 70 BUSINESS | GREENFIELD PARKWAY TO NC 42. UPGRADE ROADWAY TO SUPERSTREET. | HIGHWAY | 4, 5 | CAPITAL AREA MPO | U-6113 | NOT FUNDED | NOT FUNDED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE
JOHNSTON, WAKE | VARIOUS | BUS RAPID TRANSIT SERVICE, GARNER TO CLAYTON. CONSTRUCT INFRASTRUCTURE, PURCHASE VEHICLES, AND ESTABLISH SERVICE. | PUBLIC TRANSIT | 4, 5 | CAPITAL AREA MPO | TO-6166D | REGION A, C | REGION A, C | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE
LEE | RALEIGH EXECUTIVE JETPORT (TTA) | RUNWAY 21 AND RUNWAY 3 BYPASS TAXIWAY. CONSTRUCT AIRPLANE RUN-UP LANE AT EACH END OF TAXIWAY. | AVIATION | 8 | TRIANGLE AREA RPO | AV-5899 | DIVISION 8 | DIVISION 8 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | N/A | N/A | NO CHANGE | N/A | N/A | NO CHANGE | 2024 | 2024 | NO CHANGE
LEE | MCIVER STREET | MOORE STREET TO OAKWOOD AVENUE IN SANFORD. CONSTRUCT SIDEWALKS. | BIKE/PED | 8 | TRIANGLE AREA RPO | EB-6003 | NOT FUNDED | NOT FUNDED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE
LEE | NC 42 (WICKER STREET) | LEGION DRIVE TO NORTH OF HIGH RIDGE DRIVE AT KIWANIS FAMILY PARK IN SANFORD. CONSTRUCT MULTIUSE PATH. | BIKE/PED | 8 | TRIANGLE AREA RPO | EB-5742 | DIVISION 8 | DIVISION 8 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | N/A | N/A | NO CHANGE | N/A | N/A | NO CHANGE | 2024 | 2024 | NO CHANGE
LEE | SR 1002 (CHARLOTTE AVENUE) | CHATHAM STREET TO SR 1002 (11TH STREET) IN SANFORD. CONSTRUCT SIDEWALKS AND IMPLEMENT ROAD DIET WITH BICYCLE LANES. | BIKE/PED | 8 | TRIANGLE AREA RPO | EB-6002 | DIVISION 8 | DIVISION 8 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | N/A | N/A | NO CHANGE | N/A | N/A | NO CHANGE | 2025 | 2025 | NO CHANGE
LEE | NEW ROUTE | SR 1133 (LEE AVENUE) TO EXISTING COMMERCE DRIVE IN SANFORD. CONSTRUCT 2-LANE EXTENSION OF COMMERCE DRIVE. | HIGHWAY | 8 | TRIANGLE AREA RPO | R-5960 | DIVISION 8 | DIVISION 8 | SCHEDULED FOR DELIVERY | WILL BE REPRIORITIZED | 2028 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | PROJECT UNCOMMITTED | 2028 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | PROJECT UNCOMMITTED | 2030 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | PROJECT UNCOMMITTED
LEE | SR 1237 (CARTHAGE STREET) | SR 1152 (FIRE TOWER ROAD) TO NC 42 (WICKER STREET) IN SANFORD. WIDEN ROADWAY. | HIGHWAY | 8 | TRIANGLE AREA RPO | U-5709 | DIVISION 8 | DIVISION 8 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2022 | 2022 | NO CHANGE | 2022 | 2022 | NO CHANGE | 2024 | 2025 | 1 YEAR DELAY | YES
LEE | SR 1521 (KELLY DRIVE) | SR 1519 (NASH STREET) TO NORTHEAST OF CENTRAL CAROLINA COMMUNITY COLLEGE. CONSTRUCT 3-LANE REALIGNMENT OF KELLY DRIVE. | HIGHWAY | 8 | TRIANGLE AREA RPO | R-5959 | DIVISION 8 | DIVISION 8 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2023 | 2023 | NO CHANGE | 2023 | 2023 | NO CHANGE | 2025 | 2025 | NO CHANGE
LEE | US 1 / US 15 / US 501 | SOUTH OF SR 1198 (BRYAN DRIVE) TO SR 1237 (CARTHAGE STREET) IN SANFORD. UPGRADE TO SUPERSTREET AND RELOCATE NC 78 (TRAMWAY ROAD). | HIGHWAY | 8 | TRIANGLE AREA RPO | U-5727 | REGION E | REGION E | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2023 | 2023 | NO CHANGE | 2023 | 2023 | NO CHANGE | 2026 | 2026 | NO CHANGE
LEE | US 1 / US 15 / US 501 | US 15 / US 501 (WHITE HILL ROAD) / SR 1179 (ROCKY FORK CHURCH ROAD) TO SOUTH OF SR 1198 (BRYAN DRIVE). UPGRADE TO SUPERSTREET. | HIGHWAY | 8 | TRIANGLE AREA RPO | U-5975 | REGION E | REGION E | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2023 | 2023 | NO CHANGE | 2023 | 2023 | NO CHANGE | 2026 | 2026 | NO CHANGE
LEE | US 421 BUSINESS / NC 87 | US 1 / US 15 / US 501 TO FORMER ATLANTIC COAST LINE RAILROAD CROSSING EAST OF WASHINGTON AVENUE IN SANFORD. RECONSTRUCT AS A "COMPLETE STREET" WITH IMPROVEMENTS SUCH AS MEDIANS, SIDEWALKS, BICYCLE FACILITIES, AND STREETSCAPING. | HIGHWAY | 8 | TRIANGLE AREA RPO | U-5722 | REGION E | REGION E | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2027 | 2028 | 1 YEAR DELAY | 2027 | 2028 | 1 YEAR DELAY | 2030 | 2031 | 1 YEAR DELAY
LENOIR | SR 1569 (CAREY ROAD EXTENSION) | SR 1572 (ROUSE ROAD) TO US 258. CONSTRUCT MULTI-LANES ON NEW LOCATION. | HIGHWAY | 2 | EASTERN CAROLINA RPO | U-3618 | DIVISION 2 | DIVISION 2 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2026 | 2025 | 1 YEAR ACCELERATION | 2026 | 2025 | 1 YEAR ACCELERATION | 2028 | 2028 | NO CHANGE
LENOIR | US 70 | SR 1227 (JIM SUTTON ROAD)/SR 1252 (WILLIE MEASLEY ROAD). CONSTRUCT AT GRADE INTERSECTION TO INTERCHANGE | HIGHWAY | 2 | EASTERN CAROLINA RPO | R-5813 | NOT FUNDED | NOT FUNDED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE
LENOIR | US 70 (FUTURE I-42) | SR 1522 (ALBERT SUGGS ROAD) TO NC 148 (HARVEY PARKWAY). | HIGHWAY | 2 | EASTERN CAROLINA RPO | R-2553B | NOT FUNDED | NOT FUNDED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE
LENOIR | US 70 (FUTURE I-42) | NC 148 (HARVEY PARKWAY) TO US 70 EAST OF NC 58. | HIGHWAY | 2 | EASTERN CAROLINA RPO | R-2553C | STATEWIDE MOBILITY | STATEWIDE MOBILITY | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE
LENOIR, GREENE | US 258 | SR 1101 (BROWNTOWN ROAD) TO SR 2010 (C. F. HARVEY PARKWAY). WIDEN TO MULTI-LANES. | HIGHWAY | 2 | EASTERN CAROLINA RPO | R-5814 | DIVISION 2 | DIVISION 2 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2027 | 2027 | NO CHANGE | 2027 | 2027 | NO CHANGE | 2029 | 2029 | NO CHANGE
LINCOLN | NC 150 | US 321 AT LINCOLNTON TO US 321 BYPASS. | HIGHWAY | 12 | GASTON-CLEVELAND-LINCOLN MPO | R-0617C | NOT FUNDED | NOT FUNDED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE
LINCOLN | NC 16 | SR 1389 (FAIRFIELD FOREST ROAD) TO SR 1379 (WEBBS ROAD). WIDEN TO MULTI-LANES. | HIGHWAY | 12 | GASTON-CLEVELAND-LINCOLN MPO | U-6144 | NOT FUNDED | NOT FUNDED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE
LINCOLN | NC 16 BUSINESS | NC 16 BUSINESS, SR 1373 (CAMPGROUND ROAD), SR 1386 (WILL PROCTOR ROAD). REALIGN OFFSET INTERSECTIONS. | HIGHWAY | 12 | GASTON-CLEVELAND-LINCOLN MPO | U-5962 | REGION F | REGION F | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2024 | 2024 | NO CHANGE | 2024 | 2024 | NO CHANGE | 2026 | 2026 | NO CHANGE
LINCOLN | NC 16 BYPASS | SR 1380 (OPTIMIST CLUB ROAD) INTERSECTION. UPGRADE AT-GRADE INTERSECTION TO INTERCHANGE. | HIGHWAY | 12 | GASTON-CLEVELAND-LINCOLN MPO | U-6134 | REGION F | REGION F | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2024 | 2024 | NO CHANGE | 2024 | 2024 | NO CHANGE | 2026 | 2026 | NO CHANGE
LINCOLN | NC 27 (EAST MAIN STREET) | US 321 BUS TO NC 150 (EAST). CONSTRUCT ACCESS MANAGEMENT AND INTERSECTION IMPROVEMENTS. INCLUDES CONSTRUCTION OF NORTHBOUND TURN LANE FROM SR 1294 (LITHINA INN ROAD) TO NC 27 (E MAIN STREET) AND WIDENING OF BRIDGE #540042 OVER SEABOARD RR ON NC 150. | HIGHWAY | 12 | GASTON-CLEVELAND-LINCOLN MPO | U-6140 | REGION F | REGION F | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE
LINCOLN | NC 73 | SR 1383 (INGLESIDE FARM ROAD) TO NC 16. WIDEN TO MULTI-LANES. | HIGHWAY | 12 | GASTON-CLEVELAND-LINCOLN MPO | U-6139 | NOT FUNDED | NOT FUNDED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE
LINCOLN | NC 73 EXTENSION | US 321 TO SR 1356 (CAMP CREEK ROAD) CONSTRUCT MULTI-LANES ON NEW LOCATION. | HIGHWAY | 12 | GASTON-CLEVELAND-LINCOLN MPO | U-6142 | NOT FUNDED | NOT FUNDED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE
LINCOLN, MECKLENBURG | NC 73 | NC 16 TO VANCE ROAD EXTENSION/BEATTIES FORD ROAD. | HIGHWAY | 10, 12 | GASTON-CLEVELAND-LINCOLN MPO, CHARLOTTE REGIONAL TPO | R-5721A | REGION E, F | REGION E, F | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2026 | 2026 | NO CHANGE | 2026 | 2026 | NO CHANGE | 2029 | 2029 | NO CHANGE
MACON | MACON COUNTY AIRPORT | EXTEND RUNWAY. | AVIATION | 14 | SOUTHWESTERN RPO | AV-5850 | DIVISION 14 | DIVISION 14 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2028 | 2028 | NO CHANGE | N/A | N/A | NO CHANGE | 2029 | 2029 | NO CHANGE
MACON | EAST MAIN ST/US 441 BUS | NC 28 (HIGHLANDS ROAD). CONSTRUCT SIDEWALK LOOP. | BIKE/PED | 14 | SOUTHWESTERN RPO | EB-5964 | DIVISION 14 | DIVISION 14 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2023 | 2023 | NO CHANGE | N/A | N/A | NO CHANGE | 2024 | 2024 | NO CHANGE
MACON | US 23/US 441 | SR 1652 (WIDE HORIZON DRIVE)/SR 1152 (BELDEN CIRCLE) TO SR 1649 (PRENTISS BRIDGE ROAD). | HIGHWAY | 14 | SOUTHWESTERN RPO | R-5734B | NOT FUNDED | NOT FUNDED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE
MACON | US 23/US 441 | SR 1649 (PRENTISS BRIDGE ROAD) TO GEORGIA STATE LINE. | HIGHWAY | 14 | SOUTHWESTERN RPO | R-5734C | NOT FUNDED | NOT FUNDED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE
MADISON | MARSHALL | US 25/70, SR 1601 (DERINGER DRIVE) TO BEGINNING OF INGLE'S PARKING LOT. CONSTRUCT SIDEWALKS, INSTALL CROSSWALKS, ADA RAMPS, PEDESTRIAN SIGNAL AND PEDESTRIAN REFUGE. | BIKE/PED | 13 | LAND-OF-SKY RPO | EB-5918 | DIVISION 13 | DIVISION 13 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | N/A | N/A | NO CHANGE | N/A | N/A | NO CHANGE | 2024 | 2024 | NO CHANGE
MADISON | US 25 | US 25/70 BUSINESS (NORTH MAIN STREET) TO SR 1143 (BRUSH CREEK ROAD). WIDEN TO MULTI-LANES. | HIGHWAY | 13 | LAND-OF-SKY RPO | R-5837 | NOT FUNDED | NOT FUNDED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE
MADISON | US 25/70 | EAST OF SR 1392 (SKYWAY DRIVE) TO US 25/70 BUSINESS (NORTH MAIN STREET). MODERNIZE ROADWAY. | HIGHWAY | 13 | LAND-OF-SKY RPO | R-5924 | NOT FUNDED | NOT FUNDED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE
MARTIN | EAST MAIN STREET | BOULEVARD STREET TO RIVER ROAD IN WILLIAMSTON. INSTALL SIDEWALKS AND CURB RAMPS. | BIKE/PED | 1 | MID-EAST RPO | EB-5979 | DIVISION 1 | DIVISION 1 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | N/A | N/A | NO CHANGE | N/A | N/A | NO CHANGE | 2027 | 2027 | NO CHANGE
MARTIN | US 13/US 17 | MAIN STREET IN WILLIAMSTON. IMPROVE INTERSECTION. | HIGHWAY | 1 | MID-EAST RPO | R-5879 | REGION A | REGION A | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2025 | 2025 | NO CHANGE | 2025 | 2025 | NO CHANGE | 2027 | 2027 | NO CHANGE
MARTIN | US 17 | SR 1119 (RALPH TAYLOR ROAD) TO SR 1205 (HOLLY CREEK ROAD). ACCESS MANAGEMENT. | HIGHWAY | 1 | MID-EAST RPO | R-5810 | DIVISION 1 | DIVISION 1 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2023 | 2025 | 2 YEAR DELAY | 2023 | 2025 | 2 YEAR DELAY | 2025 | 2027 | 2 YEAR DELAY
McDOWELL | FONTA FLORA TRAIL | US 70 TO RESISTOFLEX ROAD. CONSTRUCT GREENWAY. | BIKE/PED | 13 | FOOTHILLS RPO | EB-5916 | DIVISION 13 | DIVISION 13 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2023 | 2023 | NO CHANGE | N/A | N/A | NO CHANGE | 2024 | 2024 | NO CHANGE
McDOWELL | NC 226 | US 221 TO NC 226A. WIDEN ROADWAY TO 3 LANES. | HIGHWAY | 13 | FOOTHILLS RPO | R-5923 | NOT FUNDED | NOT FUNDED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE
McDOWELL | US 221 | NORTH OF I-40 TO SR 1153 (GOOSE CREEK ROAD) | HIGHWAY | 13 | FOOTHILLS RPO | R-0204E | DIVISION 13 | DIVISION 13 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2025 | 2025 | NO CHANGE | 2025 | 2025 | NO CHANGE | 2028 | 2028 | NO CHANGE
McDOWELL | US 221 BUSINESS | US 221/NC 226 TO GEORGIA AVENUE. WIDEN EXISTING ROADWAY. | HIGHWAY | 13 | FOOTHILLS RPO | U-5835 | DIVISION 13 | DIVISION 13 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2023 | 2023 | NO CHANGE | 2023 | 2023 | NO CHANGE | 2025 | 2025 | NO CHANGE
MECKLENBURG | CHARLOTTE DOUGLAS INTERNATIONAL AIRPORT (CLT) | CONSTRUCT FOURTH PARALLEL RUNWAY. | AVIATION | 10 | CHARLOTTE REGIONAL TPO | AV-5879 | STATEWIDE MOBILITY | STATEWIDE MOBILITY | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | N/A | N/A | NO CHANGE | N/A | N/A | NO CHANGE | 2024 | 2024 | NO CHANGE
MECKLENBURG | CHARLOTTE DOUGLAS INTERNATIONAL AIRPORT (CLT) | EXPAND CONCOURSE A (PHASE II). | AVIATION | 10 | CHARLOTTE REGIONAL TPO | AV-5893 | REGION E | REGION E | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | N/A | N/A | NO CHANGE | N/A | N/A | NO CHANGE | 2025 | 2025 | NO CHANGE
MECKLENBURG | IRWIN CREEK GREENWAY EASTERN EXTENSION | EXISTING IRWIN CREEK GREENWAY TO HAMILTON STREET. CONSTRUCT GREENWAY. | BIKE/PED | 10 | CHARLOTTE REGIONAL TPO | EB-5970 | DIVISION 10 | DIVISION 10 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | N/A | N/A | NO CHANGE | N/A | N/A | NO CHANGE | 2028 | 2028 | NO CHANGE
MECKLENBURG | JETTON STREET | GRIFFITH STREET TO POTTS STREET. CONSTRUCT SIDEWALK ON SOUTH SIDE OF JETTON STREET. | BIKE/PED | 10 | CHARLOTTE REGIONAL TPO | EB-5971 | DIVISION 10 | DIVISION 10 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | N/A | N/A | NO CHANGE | N/A | N/A | NO CHANGE | 2025 | 2025 | NO CHANGE
MECKLENBURG | NC 51 MULTI-USE PATH | TRADE STREET TO INDEPENDENCE POINTE PARKWAY. CONSTRUCT MULTI-USE PATH ON SOUTH SIDE OF NC 51. | BIKE/PED | 10 | CHARLOTTE REGIONAL TPO | EB-5969 | DIVISION 10 | DIVISION 10 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | N/A | 2025 | PHASE ADDED | N/A | N/A | NO CHANGE | 2025 | 2027 | 2 YEAR DELAY | YES
MECKLENBURG | ARDREY KELL ROAD | US 521 (JOHNSTON ROAD) TO SR 3624 (REA ROAD). WIDEN TO MULTI-LANES. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-6167 | NOT FUNDED | NOT FUNDED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE
MECKLENBURG | BAILEY ROAD EXTENSION | US 21 (STATESVILLE ROAD) TO FUTURE NORTHCROSS DRIVE EXTENSION. CONSTRUCT 2 LANE ROADWAY ON NEW LOCATION. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-6171 | NOT FUNDED | NOT FUNDED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE
MECKLENBURG | CHARLOTTE | SR 2940 (EASTWAY DRIVE) AND SHAMROCK DRIVE. CONSTRUCT INTERSECTION IMPROVEMENTS. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-5803 | DIVISION 10 | DIVISION 10 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2024 | 2024 | NO CHANGE | 2024 | 2024 | NO CHANGE | 2025 | 2025 | NO CHANGE
MECKLENBURG | I-277 | KENILWORTH AVENUE TO NORTH DAVIDSON STREET AND US 74 (INDEPENDENCE BOULEVARD) FROM I-277 TO PECAN AVENUE. UPGRADE INTERCHANGES. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | I-6022A | NOT FUNDED | NOT FUNDED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE
MECKLENBURG | I-485 | I-485 AND NC 16 (PROVIDENCE ROAD). CONSTRUCT INTERCHANGE IMPROVEMENTS. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | I-5963 | STATEWIDE MOBILITY | STATEWIDE MOBILITY | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE
MECKLENBURG | I-485 | NC 51 (PINEVILLE-MATTHEWS ROAD) INTERCHNAGE. IMPROVE INTERCHANGE. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | I-6015 | NOT FUNDED | NOT FUNDED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE
MECKLENBURG | I-485 | NC 49 (SOUTH TRYON STREET) INTERCHANGE. IMPROVE INTERCHANGE. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | I-6019 | NOT FUNDED | NOT FUNDED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE
MECKLENBURG | I-77 | NC 73 INTERCHANGE. UPGRADE EXISTING INTERCHANGE TO SPLIT DIAMOND CONFIGURATION. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | I-5715 | STATEWIDE MOBILITY | STATEWIDE MOBILITY | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2023 | 2023 | NO CHANGE | 2023 | 2023 | NO CHANGE | 2025 | 2026 | 1 YEAR DELAY
MECKLENBURG | I-77 | SOUTH CAROLINA STATE LINE TO I-277/US 74 (BELK FREEWAY). WIDEN EXISTING FREEWAY TO TEN LANES BY CONSTRUCTING MANAGED LANES, RECONSTRUCT I-77/I-277 (BELK FREEWAY) INTERCHANGE, AND INSTALL RAMP METERS. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | I-5718A | STATEWIDE MOBILITY | STATEWIDE MOBILITY | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE
MECKLENBURG | I-77 | I-85 INTERCHANGE. IMPROVE INTERCHANGE. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | I-6014 | STATEWIDE MOBILITY | STATEWIDE MOBILITY | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE
MECKLENBURG | I-77 | US 21/SR 2108 (SUNSET ROAD) INTERCHANGE. IMPROVE INTERCHANGE. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | I-6056 | NOT FUNDED | NOT FUNDED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE
MECKLENBURG | I-85 | I-485 INTERCHANGE NORTHEAST OF CHARLOTTE. IMPROVE INTERCHANGE | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | I-6012 | STATEWIDE MOBILITY | STATEWIDE MOBILITY | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE
MECKLENBURG | I-85 | NC 24 (W.T. HARRIS BOULEVARD) INTERCHANGE. IMPROVE INTERCHANGE. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | I-6013 | STATEWIDE MOBILITY | STATEWIDE MOBILITY | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE
MECKLENBURG | I-85 | I-485 INTERCHANGE WEST OF CHARLOTTE. IMPROVE INTERCHANGE. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | I-6016 | STATEWIDE MOBILITY | STATEWIDE MOBILITY | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE
MECKLENBURG | I-85 | SR 2472 (MALLARD CREEK CHURCH ROAD) INTERCHANGE. IMPROVE INTERCHANGE. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | I-6017 | NOT FUNDED | NOT FUNDED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE
MECKLENBURG | I-85 | NC 16 (BROOKSHIRE BOULEVARD) INTERCHANGE. IMPROVE INTERCHANGE. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | I-6020 | NOT FUNDED | NOT FUNDED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE
MECKLENBURG | I-85 | SR 2480 (SUGAR CREEK ROAD) INTERCHANGE. IMPROVE INTERCHANGE | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | I-6053 | NOT FUNDED | NOT FUNDED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE
MECKLENBURG | INDEPENDENCE POINTE PARKWAY | SARDIS ROAD TO SR 3474 (SAM NEWELL ROAD). CONSTRUCT ROADWAY ON NEW LOCATION. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-2509EB | NOT FUNDED | DIVISION 10 | NOT FUNDED | SCHEDULED FOR DELIVERY | NOT FUNDED | 2026 | PROJECT BECOMES COMMITTED | NOT FUNDED | 2026 | PROJECT BECOMES COMMITTED | NOT FUNDED | 2029 | PROJECT BECOMES COMMITTED |  | YES
MECKLENBURG | NC 115 (OLD STATESVILLE ROAD) | NC 24 (HARRIS BOULEVARD) TO I-485. WIDEN TO MULTI-LANES. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-5772 | REGION E | REGION E | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2028 | 2028 | NO CHANGE | 2028 | 2028 | NO CHANGE | 2030 | 2031 | 1 YEAR DELAY
MECKLENBURG | NC 16 (BROOKSHIRE BOULEVARD) | I-85 TO IDAHO DRIVE. ADD WESTBOUND THROUGH LANE ON NC 16 BETWEEN A POINT WEST OF IDAHO DRIVE AND I-85. CONVERT NC 16 AND IDAHO DRIVE INTERSECTION TO AN INTERCHANGE. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-5955B | REGION E | REGION E | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2025 | 2025 | NO CHANGE | 2025 | 2025 | NO CHANGE | 2028 | 2028 | NO CHANGE
MECKLENBURG | NC 160 | SOUTH CAROLINA LINE TO NC 49 (SOUTH TRYON ROAD). WIDEN TO MULTI-LANES. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-5766A | REGION E | REGION E | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2025 | 2025 | NO CHANGE | 2025 | 2025 | NO CHANGE | 2028 | 2028 | NO CHANGE
MECKLENBURG | NC 160 | NC 49 (SOUTH TRYON ROAD) TO I-485. WIDEN TO MULTI-LANES. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-5766B | REGION E | REGION E | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2025 | 2025 | NO CHANGE | 2025 | 2025 | NO CHANGE | 2028 | 2029 | 1 YEAR DELAY | YES
MECKLENBURG | NC 27 (FREEDOM DRIVE) | SR 1644 (TODDVILLE ROAD) TO SR 1600 (MOORES CHAPEL ROAD). WIDEN TO 4-LANES. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-5957 | REGION E | REGION E | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2026 | 2026 | NO CHANGE | 2026 | 2026 | NO CHANGE | 2028 | 2029 | 1 YEAR DELAY
MECKLENBURG | NC 49 & BACK CREEK CHURCH ROAD | NC 49, JOHN KIRK DRIVE TO I-485. WIDEN EXISTING ROADWAY. REALIGN BACK CREEK CHURCH ROAD ON NEW LOCATION TO THE NC 49 AND MALLARD CREEK CHURCH ROAD INTERSECTION. CLOSE EXISTING AT GRADE RAIL CROSSING AT NC 49 AND BACK CREEK CHURCH ROAD. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-5768 | REGION E | REGION E | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2026 | 2026 | NO CHANGE | 2026 | 2026 | NO CHANGE | 2029 | 2029 | NO CHANGE
MECKLENBURG | NC 51 | MATTHEWS TOWNSHIP PARKWAY TO SR 3128 (LAWYERS ROAD). WIDEN TO MULTI-LANES. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-5007 | REGION E | REGION E | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE
MECKLENBURG | NC 51 (MATTHEWS TOWNSHIP PARKWAY) | SR 3356 (SARDIS ROAD) TO SR 1010 (EAST JOHN STREET/ MONROE ROAD). WIDEN EXISTING ROADWAY. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-5763 | REGION E | REGION E | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2026 | 2026 | NO CHANGE | 2026 | 2026 | NO CHANGE | 2029 | 2029 | NO CHANGE
MECKLENBURG | NC 73 | NC 115 TO SR 2693 (DAVIDSON-CONCORD ROAD). | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | R-2632AB | REGION E | REGION E | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2023 | 2023 | NO CHANGE | 2023 | 2023 | NO CHANGE | 2026 | 2026 | NO CHANGE
MECKLENBURG | NC 73 | VANCE ROAD EXTENSION/BEATTIES FORD ROAD TO SR 5544 (WEST CATAWBA AVENUE). | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | R-5721B | REGION E | REGION E | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2023 | 2023 | NO CHANGE | 2023 | 2023 | NO CHANGE | 2026 | 2026 | NO CHANGE
MECKLENBURG | NC 73 (SAM FURR ROAD) | SR 5544 (WEST CATAWBA AVENUE) TO SR 2316 (NORTHCROSS DRIVE). WIDEN EXISTING ROADWAY. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-5765 | REGION E | REGION E | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2023 | 2023 | NO CHANGE | 2023 | 2023 | NO CHANGE | 2026 | 2026 | NO CHANGE
MECKLENBURG | NEW ROUTE | SR 3168 (SAM NEWELL ROAD) TO SR 5215 (NORTHEAST PARKWAY. CONSTRUCT MULTI-LANES ON NEW LOCATION. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-6166 | NOT FUNDED | NOT FUNDED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE
MECKLENBURG | SR 1009 (JOHN STREET-OLD MONROE ROAD) | SR 3448-SR 3474 (TRADE STREET) TO WEST OF I-485. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-4714AA | DIVISION 10 | DIVISION 10 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2028 | 2028 | NO CHANGE | 2028 | 2028 | NO CHANGE | 2030 | 2030 | NO CHANGE
MECKLENBURG | SR 1441 (CAROWINDS BOULEVARD EXTENSION) | NC 49 (SOUTH TRYON STREET TO NC 160 (STEELE CREEK ROAD). CONSTRUCT TWO LANE DIVIDED ROADWAY ON NEW LOCATION. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-6168 | NOT FUNDED | NOT FUNDED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE
MECKLENBURG | SR 2136 (GILEAD ROAD) | US 21 (STATESVILLE ROAD) TO NC 115. WIDEN TO MULTI-LANES. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-5807 | DIVISION 10 | DIVISION 10 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2028 | 2028 | NO CHANGE | 2028 | 2028 | NO CHANGE | 2030 | 2030 | NO CHANGE
MECKLENBURG | SR 2467 (MALLARD CREEK ROAD) | SR 2472 (MALLARD CREEK CHURCH ROAD) TO BREEZEWOOD DRIVE. WIDEN TO FOUR-LANES. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-6028 | DIVISION 10 | DIVISION 10 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2026 | 2027 | 1 YEAR DELAY | 2026 | 2027 | 1 YEAR DELAY | 2028 | 2030 | 2 YEAR DELAY | YES
MECKLENBURG | SR 3440 (MCKEE ROAD) EXTENSION | SR 3448 (PLEASANT PLAINS ROAD) TO SR 1009 (JOHN STREET) | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-4713A | DIVISION 10 | DIVISION 10 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2020 | 2020 | NO CHANGE | 2020 | 2020 | NO CHANGE | 2024 | 2024 | NO CHANGE
MECKLENBURG | SR 3687 (PARK ROAD) | JOHNSTON ROAD TO NC 51 (PINEVILLE-MATTHEWS ROAD). WIDEN TO MULTI-LANES. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-6165 | NOT FUNDED | NOT FUNDED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE
MECKLENBURG | SR 4979 (BALLANTYNE COMMONS PARKWAY) | ANNALEXA LANE TO WILLIAMS POND LANE. WIDEN TO FOUR-LANES. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-6030 | NOT FUNDED | NOT FUNDED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE
MECKLENBURG | SR 5544 (WEST CATAWBA AVENUE) | NC 73 (SAM FURR ROAD) TO SR 2151 (JETTON ROAD). WIDEN TO FOUR-LANES DIVIDED. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | R-2555B | DIVISION 10 | DIVISION 10 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | UNDERWAY | UNDERWAY | NO CHANGE | UNDERWAY | UNDERWAY | NO CHANGE | 2025 | 2025 | NO CHANGE
MECKLENBURG | US 21 | SR 2136 (GILEAD ROAD) TO HOLLY POINT DRIVE. WIDEN TO MULTI-LANES. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-5771 | REGION E | REGION E | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2022 | 2022 | NO CHANGE | 2022 | 2022 | NO CHANGE | 2025 | 2025 | NO CHANGE
MECKLENBURG | US 21 (STATESVILLE ROAD) | NORTHCROSS CENTER COURT TO SR 2147 (WESTMORELAND ROAD). WIDEN TO MULTI-LANES. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-5767 | REGION E | REGION E | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2026 | 2026 | NO CHANGE | 2026 | 2026 | NO CHANGE | 2029 | 2029 | NO CHANGE
MECKLENBURG | US 521 (LANCASTER HIGHWAY/ JOHNSTON ROAD) | SOUTH CAROLINA STATE LINE TO SR 4979 (BALLANTYNE COMMONS PARKWAY). WIDEN TO MULTILANES. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-6109 | REGION E | REGION E | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2024 | 2025 | 1 YEAR DELAY | 2024 | 2025 | 1 YEAR DELAY | 2026 | 2028 | 2 YEAR DELAY | YES
MECKLENBURG | US 74 | SHARON FOREST DRIVE AND HARRIS BOULEVARD/VILLAGE LAKE DRIVE INTERSECTION AREA. CONSTRUCT GRADE SEPARATION AT SHARON FOREST DRIVE AND INTERCHANGE AT VILLAGE LAKE DRIVE. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-2509AA | STATEWIDE MOBILITY | STATEWIDE MOBILITY | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2024 | 2024 | NO CHANGE | 2024 | 2024 | NO CHANGE | 2027 | 2028 | 1 YEAR DELAY | YES
MECKLENBURG | US 74 | SARDIS ROAD AND SAM NEWELL ROAD INTERSECTION AREA. CONSTRUCT INTERCHANGES AT SARDIS ROAD NORTH AND SAM NEWELL ROAD, CONSTRUCT EXTENSION OF SARDIS ROAD NORTH FROM US 74 TO AREQUIPA DRIVE EXTENSION, AND CONSTRUCT EXTENSION OF AREQUIPA DRIVE FROM SARDIS ROA | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-2509AB | STATEWIDE MOBILITY | STATEWIDE MOBILITY | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2024 | 2024 | NO CHANGE | 2024 | 2024 | NO CHANGE | 2027 | 2028 | 1 YEAR DELAY | YES
MECKLENBURG | US 74 | INDEPENDENCE POINTE PARKWAY. CONSTRUCT ROADWAY ON NEW LOCATION FROM WINDSOR SQUARE DRIVE TO NC 51 (MATTHEWS TOWNSHIP PARKWAY). | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-2509AC | STATEWIDE MOBILITY | STATEWIDE MOBILITY | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2024 | 2024 | NO CHANGE | 2024 | 2024 | NO CHANGE | 2027 | 2028 | 1 YEAR DELAY | YES
MECKLENBURG | US 74 | MATTHEWS-MINT HILL ROAD INTERSECTION AREA. CONSTRUCT INTERCHANGE AT MATTHEWS-MINT HILL ROAD AND EXTENSION OF NORTHEAST PARKWAY FROM OVERCASH DRIVE TO WAITING STREET. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-2509AD | STATEWIDE MOBILITY | STATEWIDE MOBILITY | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2024 | 2024 | NO CHANGE | 2024 | 2024 | NO CHANGE | 2027 | 2028 | 1 YEAR DELAY | YES
MECKLENBURG | US 74 | WEST OF IDLEWILD ROAD TO WALLACE LANE. ADD GENERAL PURPOSE AND EXPRESS LANES AND CONSTRUCT EXPRESS LANE INTERCHANGE ON WEST SIDE OF CONFERENCE DRIVE. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-2509B | STATEWIDE MOBILITY | STATEWIDE MOBILITY | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2024 | 2025 | 1 YEAR DELAY | 2024 | 2025 | 1 YEAR DELAY | 2027 | 2028 | 1 YEAR DELAY | YES
MECKLENBURG | US 74 | WALLACE LANE TO SARDIS ROAD. ADD GENERAL PURPOSE AND EXPRESS LANES AND CONSTRUCT EXPRESS LANE INTERCHANGE AT SARDIS ROAD. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-2509C | STATEWIDE MOBILITY | STATEWIDE MOBILITY | SCHEDULED FOR DELIVERY | WILL BE REPRIORITIZED | 2024 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | PROJECT UNCOMMITTED | 2024 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | PROJECT UNCOMMITTED | 2027 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | PROJECT UNCOMMITTED |  | YES
MECKLENBURG | US 74 | SARDIS ROAD TO I-485. ADD GENERAL PURPOSE AND EXPRESS LANES, CONSTRUCT EXPRESS LANE INTERCHANGES AT I-485 AND EAST SIDE OF CONFERENCE DRIVE, AND RECONSTRUCT INTERCHANGE AT NC 51 (MATTHEWS TOWNSHIP PARKWAY). | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-2509D | STATEWIDE MOBILITY | STATEWIDE MOBILITY | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE
MECKLENBURG | US 74 (INDEPENDENCE BOULEVARD) | I-277 TO WEST OF IDLEWILD ROAD. WIDEN ROADWAY TO ALLOW FOR TWO-WAY EXPRESS LANES. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-6103 | STATEWIDE MOBILITY | STATEWIDE MOBILITY | WILL BE REPRIORITIZED | SCHEDULED FOR DELIVERY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2025 | PROJECT BECOMES COMMITTED | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2025 | PROJECT BECOMES COMMITTED | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2028 | PROJECT BECOMES COMMITTED |  | YES
MECKLENBURG | US 74 PARALLEL ROUTES | KREFELD DRIVE, AREQUIPA DRIVE, AND INDEPENDENCE POINTE PARKWAY. CONSTRUCT MULTIPLE SEGMENTS, PART ON NEW LOCATION. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-2509E | NOT FUNDED | NOT FUNDED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE
MECKLENBURG | CLANTON ROAD | EXTEND CLANTON ROAD TO US 29/74 (WILKINSON BOULEVARD) WITH A GRADE SEPARATION OF NORFOLK SOUTHERN RAILROAD AND CLOSE THE DONALD ROSS ROAD CROSSING. | RAIL | 10 | CHARLOTTE REGIONAL TPO | P-5730 | REGION E | REGION E | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2024 | 2024 | NO CHANGE | N/A | N/A | NO CHANGE | 2025 | 2025 | NO CHANGE
MECKLENBURG, CABARRUS | NC 73 (DAVIDSON HIGHWAY) | EAST OF SR 2693 (DAVIDSON-CONCORD ROAD) TO EAST OF SR 1394 (POPLAR TENT ROAD). | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO, CABARRUS-ROWAN MPO | R-5706A | REGION E | REGION E | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2024 | 2024 | NO CHANGE | 2024 | 2024 | NO CHANGE | 2026 | 2026 | NO CHANGE
MECKLENBURG, CABARRUS | SR 2467 (MALLARD CREEK ROAD)/ SR 1445 (DERITA ROAD | I-485 TO CONCORD MILLS BOULEVARD (SR 2894). WIDEN TO MULTI-LANES. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO, CABARRUS-ROWAN MPO | U-6032 | DIVISION 10 | DIVISION 10 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2022 | 2022 | NO CHANGE | 2022 | 2022 | NO CHANGE | 2025 | 2025 | NO CHANGE
MITCHELL | NC 226 | BLUE RIDGE PARKWAY TO SR 1274 (SUMMIT AVENUE). WIDEN TO 3-LANES. | HIGHWAY | 13 | HIGH COUNTRY RPO | R-5804 | NOT FUNDED | NOT FUNDED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE
MONTGOMERY | NC 109 | SR 1127 (HEARNE FARM ROAD) TO SR 1174 (PEE DEE ROAD). | HIGHWAY | 8 | PIEDMONT TRIAD RPO | R-5826B | DIVISION 8 | DIVISION 8 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2023 | 2023 | NO CHANGE | 2023 | 2023 | NO CHANGE | 2026 | 2026 | NO CHANGE
MONTGOMERY | NC 24 / NC 27 | NC 73 TO TROY BYPASS. WIDEN TO MULTILANES. | HIGHWAY | 8 | PIEDMONT TRIAD RPO | R-2527 | REGION E | REGION E | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2019 | 2019 | NO CHANGE | 2019 | 2019 | NO CHANGE | 2024 | 2025 | 1 YEAR DELAY | YES
MOORE | SR 2055 (NORTH POPLAR STREET) | JOHNSON STREET TO US 1 (SANDHILLS BOULEVARD) IN ABERDEEN. CONSTRUCT SIDEWALK. | BIKE/PED | 8 | TRIANGLE AREA RPO | EB-6001 | DIVISION 8 | DIVISION 8 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2024 | 2024 | NO CHANGE | N/A | N/A | NO CHANGE | 2025 | 2025 | NO CHANGE
MOORE | VARIOUS | CONSTRUCT PEDESTRIAN IMPROVEMENTS AT 5 INTERSECTIONS AND ONE MID-BLOCK LOCATION IN THE CENTRAL BUSINESS DISTRICT OF ABERDEEN. | BIKE/PED | 8 | TRIANGLE AREA RPO | EB-6005 | NOT FUNDED | NOT FUNDED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | N/A | N/A | NO CHANGE | N/A | N/A | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE
MOORE | NC 211 | NC 73 IN WEST END TO WEST OF SR 1241 (HOLLY GROVE SCHOOL ROAD). WIDEN TO MULTILANES. | HIGHWAY | 8 | TRIANGLE AREA RPO | R-5726 | REGION E | REGION E | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | UNDERWAY | UNDERWAY | NO CHANGE | UNDERWAY | UNDERWAY | NO CHANGE | 2025 | 2025 | NO CHANGE
MOORE | NC 24 / NC 27 | SR 1006 (GLENDON-CARTHAGE ROAD) IN CARTHAGE. IMPROVE INTERSECTION AND ADJACENT INTERSECTIONS OF EACH FACILITY WITH US 15 / US 501. | HIGHWAY | 8 | TRIANGLE AREA RPO | R-5929 | DIVISION 8 | DIVISION 8 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2023 | 2026 | 3 YEAR DELAY | 2023 | 2026 | 3 YEAR DELAY | 2025 | 2028 | 3 YEAR DELAY | YES
MOORE | NC 24 / NC 27 | COURTHOUSE WEST OF NC 22 (MCNEILL STREET) TO US 15 / US 501 IN CARTHAGE. WIDEN TO THREE LANES WITH CURB AND GUTTER AND BICYCLE / PEDESTRIAN ACCOMMODATIONS. | HIGHWAY | 8 | TRIANGLE AREA RPO | U-3628 | REGION E | REGION E | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | UNDERWAY | UNDERWAY | NO CHANGE | UNDERWAY | UNDERWAY | NO CHANGE | 2025 | 2025 | NO CHANGE
MOORE | NC 5 | US 1 IN ABERDEEN TO THE INTERSECTION OF TROTTER DRIVE / BLAKE BOULEVARD IN PINEHURST. WIDEN TO MULTILANES. | HIGHWAY | 8 | TRIANGLE AREA RPO | U-5756 | REGION E | REGION E | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2023 | 2023 | NO CHANGE | 2023 | 2023 | NO CHANGE | 2025 | 2025 | NO CHANGE
MOORE | NC 5 (BEULAH HILL ROAD) | INTERSECTION OF TROTTER DRIVE / BLAKE BOULEVARD TO NC 211 IN PINEHURST. ADD TURN LANES, SIGNAL IMPROVEMENTS, AND OTHER OPERATIONAL IMPROVEMENTS ALONG CORRIDOR AS APPROPRIATE. | HIGHWAY | 8 | TRIANGLE AREA RPO | R-5892 | REGION E | REGION E | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2028 | 2028 | NO CHANGE | 2028 | 2028 | NO CHANGE | 2030 | 2030 | NO CHANGE
MOORE | NC 690 (LOBELIA ROAD) | US 1 IN VASS TO CUMBERLAND COUNTY LINE. UPGRADE ROADWAY, TO INCLUDE TURN LANES AT VARIOUS LOCATIONS AND SOME REALIGNMENT. | HIGHWAY | 8 | TRIANGLE AREA RPO | R-5824 | REGION E | REGION E | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2023 | 2024 | 1 YEAR DELAY | 2023 | 2024 | 1 YEAR DELAY | 2025 | 2027 | 2 YEAR DELAY | YES
MOORE | US 1 (SANDHILLS BOULEVARD) | SR 1112 (ROSELAND ROAD) TO KNIGHT STREET IN ABERDEEN. | HIGHWAY | 8 | TRIANGLE AREA RPO | U-5815A | REGION E | REGION E | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2025 | 2025 | NO CHANGE | 2025 | 2025 | NO CHANGE | 2027 | 2027 | NO CHANGE
MOORE | US 1 (SANDHILLS BOULEVARD) | KNIGHT STREET IN ABERDEEN TO OLD US 1 IN SOUTHERN PINES, TO INCLUDE SR 1112 (ROSELAND ROAD) REALIGNMENT AT US1 AND RADII IMPROVEMENT I AT US 15 / US 501 / NC 211. | HIGHWAY | 8 | TRIANGLE AREA RPO | U-5815B | REGION E | REGION E | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | UNDERWAY | UNDERWAY | NO CHANGE | UNDERWAY | UNDERWAY | NO CHANGE | 2025 | 2025 | NO CHANGE
MOORE | US 15 / US 501 | NC 2 AND NC 211 TRAFFIC CIRCLE IN PINEHURST TO NC 73. WIDEN TO MULTILANES. | HIGHWAY | 8 | TRIANGLE AREA RPO | R-5927 | DIVISION 8 | DIVISION 8 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2026 | 2026 | NO CHANGE | 2026 | 2026 | NO CHANGE | 2029 | 2029 | NO CHANGE
MOORE | US 15 / US 501 | SR 1905 (VOIT GILMORE LANE) IN SOUTHERN PINES TO SR 1208 PAGE ROAD IN PINEHURST. UPGRADE SR 1208 INTERSECTION AND CONSTRUCT IMPROVEMENTS TO PINEHURST TRAFFIC CIRCLE AND APPROACHES. | HIGHWAY | 8 | TRIANGLE AREA RPO | U-5976 | DIVISION 8 | DIVISION 8 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2024 | 2028 | 4 YEAR DELAY | 2024 | 2028 | 4 YEAR DELAY | 2026 | 2030 | 4 YEAR DELAY | YES
MOORE | US 15 / US 501 / NC 211 | SR 1205 / SR 1309 (MORGANTON ROAD) IN SOUTHERN PINES. CONVERT AT-GRADE INTERSECTION TO INTERCHANGE. | HIGHWAY | 8 | TRIANGLE AREA RPO | R-5891 | REGION E | REGION E | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2027 | 2028 | 1 YEAR DELAY | 2027 | 2028 | 1 YEAR DELAY | 2029 | 2031 | 2 YEAR DELAY
MOORE | US 15 / US 501 / NC 211 | US 1 (SANDHILLS BOULEVARD) IN ABERDEEN TO BRUCEWOOD ROAD IN SOUTHERN PINES. ACCESS MANAGEMENT IMPROVEMENTS. | HIGHWAY | 8 | TRIANGLE AREA RPO | U-5814 | REGION E | REGION E | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | UNDERWAY | UNDERWAY | NO CHANGE | UNDERWAY | UNDERWAY | NO CHANGE | 2025 | 2025 | NO CHANGE
MOORE, MONTGOMERY | NC 24 / NC 27 | I-73 / I-74 / US 220 TO SR 1644 (OLD GLENDON ROAD). MODERNIZE ROADWAY. | HIGHWAY | 8 | TRIANGLE AREA RPO, PIEDMONT TRIAD RPO | R-5932 | NOT FUNDED | NOT FUNDED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE
NASH | US 301 BUSINESS (CHURCH STREET) | US 64 TO NC 97 (RALEIGH BOULEVARD) OVERPASS. CONSTRUCT STREETSCAPE IMPROVEMENTS. ADD SIDEWALK AND BICYCLE LANES. | BIKE/PED | 4 | ROCKY MOUNT URBAN AREA MPO | EB-5761 | DIVISION 4 | DIVISION 4 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2024 | 2024 | NO CHANGE | N/A | N/A | NO CHANGE | 2025 | 2025 | NO CHANGE
NASH | US 64 BUSINESS (THOMAS STREET) | SR 1005 (EAST RALEIGH BOULEVARD TO US 64 BUSINESS (SUNSET AVENUE) IN ROCKY MOUNT. ADD PEDESTRIAN SIGNALS. | BIKE/PED | 4 | ROCKY MOUNT URBAN AREA MPO | EB-5905 | DIVISION 4 | DIVISION 4 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | N/A | N/A | NO CHANGE | N/A | N/A | NO CHANGE | 2027 | 2027 | NO CHANGE
NASH | NC 43 | SR 1613 (WOODRUFF AVENUE) TO I-95. | HIGHWAY | 4 | UPPER COASTAL PLAIN RPO | U-2561C | DIVISION 4 | DIVISION 4 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2026 | 2026 | NO CHANGE | 2026 | 2026 | NO CHANGE | 2028 | 2028 | NO CHANGE
NASH | NC 48 | SR 1524 (RED OAK/BATTLEBORO ROAD) TO NC 4. WIDEN TO MULTI-LANES. | HIGHWAY | 4 | ROCKY MOUNT URBAN AREA MPO | U-5911 | DIVISION 4 | DIVISION 4 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2025 | 2025 | NO CHANGE | 2025 | 2025 | NO CHANGE | 2027 | 2027 | NO CHANGE
NASH | TAR RIVER TRANSIT | ENLARGE DRIVERS BREAKROOM | PUBLIC TRANSIT | 4 | ROCKY MOUNT URBAN AREA MPO | TD-5281 | DIVISION 4 | DIVISION 4 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | N/A | N/A | NO CHANGE | N/A | N/A | NO CHANGE | 2025 | 2025 | NO CHANGE
NASH, EDGECOMBE | US 64 | NC 58 (WASHINGTON STREET), EXIT 459, TO SR 1233 (THOMAS ROAD) OVERPASS. UPGRADE TO INTERSTATE STANDARDS. | HIGHWAY | 4 | ROCKY MOUNT URBAN AREA MPO | U-6149 | NOT FUNDED | NOT FUNDED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE
NEW HANOVER | INTERNATIONAL (ILM) WILMINGTON | INCREASE WIDTH OF ALL TAXIWAYS. | AVIATION | 3 | WILMINGTON URBAN AREA MPO | AV-5796 | NOT FUNDED | NOT FUNDED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | N/A | N/A | NO CHANGE | N/A | N/A | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE
NEW HANOVER | WILIMINGTON INTERNATION (ILM) | TAXIWAY J IMPROVEMENTS. | AVIATION | 3 | WILMINGTON URBAN AREA MPO | AV-5886 | NOT FUNDED | NOT FUNDED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | N/A | N/A | NO CHANGE | N/A | N/A | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE
NEW HANOVER | WILMINGTON INTERNATIONAL (ILM) | EXPAND THE GENERAL AVIATION APRON. | AVIATION | 3 | WILMINGTON URBAN AREA MPO | AV-5795 | STATEWIDE MOBILITY | STATEWIDE MOBILITY | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | N/A | N/A | NO CHANGE | N/A | N/A | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE
NEW HANOVER | WILMINGTON INTERNATIONAL (ILM) | TAXIWAY IMPROVEMENTS. | AVIATION | 3 | WILMINGTON URBAN AREA MPO | AV-5798 | STATEWIDE MOBILITY | STATEWIDE MOBILITY | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | N/A | N/A | NO CHANGE | N/A | N/A | NO CHANGE | 2028 | 2028 | NO CHANGE
NEW HANOVER | WILMINGTON INTERNATIONAL (ILM) | WIDEN NORTH-SOUTH TAXIWAY SYSTEM. | AVIATION | 3 | WILMINGTON URBAN AREA MPO | AV-5799 | NOT FUNDED | NOT FUNDED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | N/A | N/A | NO CHANGE | N/A | N/A | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE
NEW HANOVER | WILMINGTON INTERNATIONAL AIRPORT (ILM) | REHABILITATE RUNWAY. | AVIATION | 3 | WILMINGTON URBAN AREA MPO | AV-5885 | NOT FUNDED | STATEWIDE MOBILITY | WILL BE REPRIORITIZED | SCHEDULED FOR DELIVERY | N/A | N/A | NO CHANGE | N/A | N/A | NO CHANGE | NOT FUNDED | 2024 | PROJECT BECOMES COMMITTED |  | YES
NEW HANOVER | SR 1219 (SOUTH 17TH STREET) | HARBOUR DRIVE TO SHIPYARD BOULEVARD. CONSTRUCT MULTI-USE PATH. | BIKE/PED | 3 | WILMINGTON URBAN AREA MPO | EB-5600 | DIVISION 3 | DIVISION 3 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2024 | 2024 | NO CHANGE | N/A | N/A | NO CHANGE | 2024 | 2024 | NO CHANGE
NEW HANOVER | NC 132 (COLLEGE ROAD) | SR 1272 (NEW CENTRE DRIVE) TO US 117 (SHIPYARD BOULEVARD). ACCESS MANAGEMENT AND TRAVEL TIME IMPROVEMENTS. | HIGHWAY | 3 | WILMINGTON URBAN AREA MPO | U-5702A | STATEWIDE MOBILITY | STATEWIDE MOBILITY | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2028 | 2028 | NO CHANGE | 2028 | 2028 | NO CHANGE | 2030 | 2030 | NO CHANGE
NEW HANOVER | NC 132 (COLLEGE ROAD) | US 117 (SHIPYARD BOULEVARD) TO US 421 (CAROLINA BEACH ROAD). ACCESS MANAGEMENT AND TRAVEL TIME IMPROVEMENTS. | HIGHWAY | 3 | WILMINGTON URBAN AREA MPO | U-5702B | NOT FUNDED | NOT FUNDED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE
NEW HANOVER | NC 132 (COLLEGE ROAD) | US 76 (OLEANDER DRIVE). INTERSECTION IMPROVEMENTS. | HIGHWAY | 3 | WILMINGTON URBAN AREA MPO | U-5704 | STATEWIDE MOBILITY | STATEWIDE MOBILITY | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE
NEW HANOVER | NC 132 (COLLEGE ROAD) | SR 2048 (GORDON ROAD) TO SR 1272 (NEW CENTRE DRIVE). UPGRADE ROADWAY. | HIGHWAY | 3 | WILMINGTON URBAN AREA MPO | U-5881 | STATEWIDE MOBILITY | STATEWIDE MOBILITY | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE
NEW HANOVER | NC 133 (CASTLE HAYNE ROAD) | I-140/US 17 (WILMINGTON BYPASS) TO SR 1310 (DIVISION DRIVE) IN WILMINGTON. WIDEN TO MULTI-LANES | HIGHWAY | 3 | WILMINGTON URBAN AREA MPO | U-5863 | NOT FUNDED | NOT FUNDED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE
NEW HANOVER | NC 133 (CASTLE HAYNE ROAD) | NORTH 23RD STREET. CONSTRUCT A ROUNDABOUT. | HIGHWAY | 3 | WILMINGTON URBAN AREA MPO | U-5954 | REGION B | REGION B | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2025 | 2025 | NO CHANGE | 2025 | 2025 | NO CHANGE | 2027 | 2027 | NO CHANGE
NEW HANOVER | SR 1175 (KERR AVENUE) | SR 1175 (KERR AVENUE) INTERCHANGE AT US 74 (MLK, JR. PARKWAY). | HIGHWAY | 3 | WILMINGTON URBAN AREA MPO | U-3338C | REGION B | REGION B | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | UNDERWAY | UNDERWAY | NO CHANGE | UNDERWAY | UNDERWAY | NO CHANGE | 2026 | 2028 | 2 YEAR DELAY |  | YES
NEW HANOVER | SR 1175 (KERR AVENUE) | SR 1411 (WRIGHTSVILLE AVENUE) TO US 76 (OLEANDER DRIVE). CONSTRUCT ROADWAY ON NEW LOCATION. | HIGHWAY | 3 | WILMINGTON URBAN AREA MPO | U-6201 | DIVISION 3 | DIVISION 3 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2028 | 2028 | NO CHANGE | 2028 | 2028 | NO CHANGE | 2030 | 2030 | NO CHANGE
NEW HANOVER | SR 1209 (INDEPENDENCE BOULEVARD EXTENSION) | RANDALL PARKWAY TO US 74 (MLK, JR. PARKWAY) IN WILMINGTON. MULTI-LANES ON NEW LOCATION. | HIGHWAY | 3 | WILMINGTON URBAN AREA MPO | U-4434 | DIVISION 3 | DIVISION 3 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2026 | 2027 | 1 YEAR DELAY | 2026 | 2027 | 1 YEAR DELAY | 2028 | 2031 | 3 YEAR DELAY | YES
NEW HANOVER | SR 2048 (GORDON ROAD) | US 17 (MARKET STREET) TO I-40. WIDEN ROADWAY. | HIGHWAY | 3 | WILMINGTON URBAN AREA MPO | U-6202 | DIVISION 3 | DIVISION 3 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2022 | 2022 | NO CHANGE | 2022 | 2022 | NO CHANGE | 2024 | 2025 | 1 YEAR DELAY | YES
NEW HANOVER | US 17 BUSINESS (MARKET STREET) | CSX RAILROAD TO CINEMA DRIVE; JACKSONVILLE STREET TO NORTH OF US 117/NC 132 (COLLEGE ROAD). | HIGHWAY | 3 | WILMINGTON URBAN AREA MPO | U-4902B | REGION B | NOT FUNDED | SCHEDULED FOR DELIVERY | WILL BE REPRIORITIZED | 2027 | NOT FUNDED | PROJECT NO LONGER FUNDED | 2027 | NOT FUNDED | PROJECT NO LONGER FUNDED | 2029 | NOT FUNDED | PROJECT NO LONGER FUNDED |  | YES
NEW HANOVER | US 17 BUSINESS (MARKET STREET) | NORTH OF US 117/NC 132 (COLLEGE ROAD) TO STATION ROAD. | HIGHWAY | 3 | WILMINGTON URBAN AREA MPO | U-4902C | STATEWIDE MOBILITY | STATEWIDE MOBILITY | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2027 | 2028 | 1 YEAR DELAY | 2027 | 2028 | 1 YEAR DELAY | 2029 | 2030 | 1 YEAR DELAY
NEW HANOVER | US 421 | US 421 (BURNETT AVENUE) TO US 117 (SHIPYARD BOULEVARD) IN WILMINGTON. UPGRADE ROADWAY. | HIGHWAY | 3 | WILMINGTON URBAN AREA MPO | U-5729REG | REGION B | REGION B | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2027 | 2028 | 1 YEAR DELAY | 2027 | 2028 | 1 YEAR DELAY | 2029 | 2030 | 1 YEAR DELAY
NEW HANOVER | US 421 | US 117 (SHIPYARD BOULEVARD). INTERSECTION IMPROVEMENTS. | HIGHWAY | 3 | WILMINGTON URBAN AREA MPO | U-5729SW | STATEWIDE MOBILITY | STATEWIDE MOBILITY | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2027 | 2028 | 1 YEAR DELAY | 2027 | 2028 | 1 YEAR DELAY | 2029 | 2030 | 1 YEAR DELAY
NEW HANOVER | US 421 (CAROLINA BEACH ROAD) | NC 132 (SOUTH COLLEGE ROAD) TO SANDERS ROAD IN WILMINGTON. WIDEN EXISTING ROADWAY AND CONSTRUCT FLYOVERS AT US 421 AND NC 132. | HIGHWAY | 3 | WILMINGTON URBAN AREA MPO | U-5790 | DIVISION 3 | DIVISION 3 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2027 | 2027 | NO CHANGE | 2027 | 2027 | NO CHANGE | 2029 | 2029 | NO CHANGE
NEW HANOVER | US 421 (SOUTH FRONT STREET) | US 17 BUSINESS/US 76/US 421 (CAPE FEAR MEMORIAL BRIDGE) TO US 421 (BURNETT BOULEVARD) IN WILMINGTON. WIDEN TO MULTI-LANES. | HIGHWAY | 3 | WILMINGTON URBAN AREA MPO | U-5734 | REGION B | REGION B | WILL BE REPRIORITIZED | SCHEDULED FOR DELIVERY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2025 | PROJECT BECOMES COMMITTED | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2025 | PROJECT BECOMES COMMITTED | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2027 | PROJECT BECOMES COMMITTED |  | YES
NEW HANOVER | US 74 | US 17/US 421 IN WILMINGTON. CONSTRUCT A FLY-OVER AND FREE FLOW RAMP AT INTERCHANGE. | HIGHWAY | 3 | WILMINGTON URBAN AREA MPO | U-5731 | STATEWIDE MOBILITY | STATEWIDE MOBILITY | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2026 | 2027 | 1 YEAR DELAY | 2026 | 2027 | 1 YEAR DELAY | 2028 | 2029 | 1 YEAR DELAY
NEW HANOVER | US 74 (EASTWOOD ROAD) | SR 1409 (MILITARY CUTOFF ROAD) INTERSECTION IN WILMINGTON. CONVERT AT-GRADE INTERSECTION TO AN INTERCHANGE. | HIGHWAY | 3 | WILMINGTON URBAN AREA MPO | U-5710 | STATEWIDE MOBILITY | STATEWIDE MOBILITY | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2023 | 2023 | NO CHANGE | 2023 | 2023 | NO CHANGE | 2025 | 2026 | 1 YEAR DELAY
NEW HANOVER | US 74 (MARTIN LUTHER KING, JR. PARKWAY) | US 117/NC 132 (COLLEGE ROAD) IN WILMINGTON. CONVERT AT-GRADE INTERSECTION TO INTERCHANGE. | HIGHWAY | 3 | WILMINGTON URBAN AREA MPO | U-5792 | DIVISION 3 | DIVISION 3 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2024 | 2025 | 1 YEAR DELAY | 2024 | 2025 | 1 YEAR DELAY | 2026 | 2027 | 1 YEAR DELAY | YES
NEW HANOVER | US 76 (OLEANDER DRIVE) | GREENVILLE LOOP ROAD AND GREENVILLE AVENUE. UPGRADE INTERSECTION. | HIGHWAY | 3 | WILMINGTON URBAN AREA MPO | U-6128 | NOT FUNDED | REGION B | WILL BE REPRIORITIZED | SCHEDULED FOR DELIVERY | NOT FUNDED | 2027 | PROJECT BECOMES COMMITTED | NOT FUNDED | 2027 | PROJECT BECOMES COMMITTED | NOT FUNDED | 2029 | PROJECT BECOMES COMMITTED |  | YES
NEW HANOVER | WILMINGTON | WILMINGTON CITYWIDE SIGNAL SYSTEM. | HIGHWAY | 3 | WILMINGTON URBAN AREA MPO | U-6199 | DIVISION 3 | DIVISION 3 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2028 | 2028 | NO CHANGE | 2028 | 2028 | NO CHANGE | 2030 | 2030 | NO CHANGE
NEW HANOVER | WILMINGTON INTERNATIONAL AIRPORT (ILM) | EXTEND RUNWAY 6-24 PHASE 1. |  | 3 | WILMINGTON URBAN AREA MPO | AV-5730 | STATEWIDE MOBILITY | NOT FUNDED | SCHEDULED FOR DELIVERY | WILL BE REPRIORITIZED | N/A | N/A | NO CHANGE | N/A | N/A | NO CHANGE | 2022 | NOT FUNDED | PROJECT NO LONGER FUNDED |  | YES
NORTHAMPTON | NC 305 | SEABOARD TOWN LIMITS TO HERTFORD COUNTY LINE. UPGRADE ROADWAY. | HIGHWAY | 1 | PEANUT BELT RPO | R-5757 | DIVISION 1 | DIVISION 1 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2023 | 2023 | NO CHANGE | 2023 | 2023 | NO CHANGE | 2024 | 2025 | 1 YEAR DELAY | YES
NORTHAMPTON | NC 46 | NC 48 IN GASTON TO THE VIRGINIA STATE LINE. UPGRADE AND WIDEN EXISTING FACILITY. | HIGHWAY | 1 | PEANUT BELT RPO | R-5739 | DIVISION 1 | DIVISION 1 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2022 | 2022 | NO CHANGE | 2022 | 2022 | NO CHANGE | 2025 | 2025 | NO CHANGE
ONSLOW | ALBERT J. ELLIS AIRPORT (OAJ) | EXTEND RUNWAY 23 AND TAXIWAY A. | AVIATION | 3 | JACKSONVILLE URBAN AREA MPO | AV-5806 | REGION B | REGION B | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | N/A | N/A | NO CHANGE | N/A | N/A | NO CHANGE | 2025 | 2025 | NO CHANGE
ONSLOW | NC 210 | US 17 TO SOUTH OF SR 1518 (OLD FOLKSTONE ROAD). WIDEN TO MULTI-LANES. | HIGHWAY | 3 | JACKSONVILLE URBAN AREA MPO | U-5949 | REGION B | REGION B | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2028 | 2028 | NO CHANGE | 2028 | 2028 | NO CHANGE | 2030 | 2032 | 2 YEAR DELAY | YES
ONSLOW | NC 24 | US 258 (RICHLANDS HIGHWAY) INTERSECTION. CONVERT AT-GRADE INTERSECTION TO INTERCHANGE. | HIGHWAY | 3 | JACKSONVILLE URBAN AREA MPO | U-5716 | STATEWIDE MOBILITY | STATEWIDE MOBILITY | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2027 | 2028 | 1 YEAR DELAY | 2027 | 2028 | 1 YEAR DELAY | 2029 | 2030 | 1 YEAR DELAY
ONSLOW | NC 24 (LEJEUNE BOULEVARD) | NC 53 (WESTERN BOULEVARD) IN JACKSONVILLE. UPGRADE INTERSECTION AND DRAINAGE. | HIGHWAY | 3 | JACKSONVILLE URBAN AREA MPO | U-5508 | STATEWIDE MOBILITY | STATEWIDE MOBILITY | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2027 | 2028 | 1 YEAR DELAY | 2027 | 2028 | 1 YEAR DELAY | 2029 | 2030 | 1 YEAR DELAY
ONSLOW | NC 24 (LEJEUNE BOULEVARD) | NC 24 BUSINESS (JOHNSON BOULEVARD) TO NC 172. CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | HIGHWAY | 3 | JACKSONVILLE URBAN AREA MPO | U-5741 | REGION B | REGION B | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE
ONSLOW | NC 24 (WEST CORBETT AVENUE) | BELGRADE-SWANSBORO ROAD TO FRONT STREET. CONSTRUCT SUPERSTREET. | HIGHWAY | 3 | JACKSONVILLE URBAN AREA MPO | R-5885 | NOT FUNDED | NOT FUNDED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE
ONSLOW | NC 53 | NC 53: FROM US 17 (MARINE BOULEVARD) TO SR 2716 (EXCHANGE DRIVE). | HIGHWAY | 3 | JACKSONVILLE URBAN AREA MPO | U-4007E | STATEWIDE MOBILITY | STATEWIDE MOBILITY | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2027 | 2028 | 1 YEAR DELAY | 2027 | 2028 | 1 YEAR DELAY | 2029 | 2030 | 1 YEAR DELAY
ONSLOW | NC 53 (WESTERN BOULEVARD) | US 17 (MARINE BOULEVARD) TO NC 24 (LEJEUNE BOULEVARD) IN JACKSONVILLE. CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | HIGHWAY | 3 | JACKSONVILLE URBAN AREA MPO | U-5736 | REGION B | REGION B | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2027 | 2027 | NO CHANGE | 2027 | 2027 | NO CHANGE | 2029 | 2029 | NO CHANGE
ONSLOW | NC 53 (WESTERN BOULEVARD) | SR 2714 (JACKSONVILLE PARKWAY). IMPROVE INTERSECTION. | HIGHWAY | 3 | JACKSONVILLE URBAN AREA MPO | U-5789 | REGION B | REGION B | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | UNDERWAY | UNDERWAY | NO CHANGE | UNDERWAY | UNDERWAY | NO CHANGE | 2025 | 2025 | NO CHANGE
ONSLOW | NC 53 (WESTERN BOULEVARD) | SR 1308 (GUM BRANCH ROAD) TO US 17 (MARINE BOULEVARD). UPGRADE TO SUPERSTREET. | HIGHWAY | 3 | JACKSONVILLE URBAN AREA MPO | U-6081 | NOT FUNDED | NOT FUNDED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE
ONSLOW | SR 1308 (BELL FORK ROAD) | SR 1403 (COUNTRY CLUB ROAD/HARGETT STREET). IMPROVE INTERSECTION. | HIGHWAY | 3 | JACKSONVILLE URBAN AREA MPO | U-6082 | DIVISION 3 | DIVISION 3 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2025 | 2025 | NO CHANGE | 2025 | 2025 | NO CHANGE | 2027 | 2028 | 1 YEAR DELAY | YES
ONSLOW | SR 1308 (GUM BRANCH ROAD) | SR 1322 (SUMMERSILL SCHOOL ROAD) TO SR 1324 (RAMSEY ROAD). | HIGHWAY | 3 | JACKSONVILLE URBAN AREA MPO | U-5793A | DIVISION 3 | DIVISION 3 | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE
ONSLOW | SR 1308 (GUM BRANCH ROAD) | SR 1324 (RAMSEY ROAD) TO SR 1390 (COUNTRY CLUB BOULEVARD). | HIGHWAY | 3 | JACKSONVILLE URBAN AREA MPO | U-5793B | DIVISION 3 | DIVISION 3 | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE
ONSLOW | SR 1308 (GUM BRANCH ROAD) | WILLIAMSBURG PARKWAY TO INDIAN DRIVE. UPGRADE TO SUPERSTREET. | HIGHWAY | 3 | JACKSONVILLE URBAN AREA MPO | U-6200 | NOT FUNDED | NOT FUNDED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE
ONSLOW | SR 1336 (HENDERSON ROAD) | SR 1308 (GUM BRANCH ROAD) TO NC 53 (WESTERN BOULEVARD). UPGRADE TO SUPERSTREET. | HIGHWAY | 3 | JACKSONVILLE URBAN AREA MPO | U-5903 | DIVISION 3 | DIVISION 3 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2028 | 2028 | NO CHANGE | 2028 | 2028 | NO CHANGE | 2030 | 2030 | NO CHANGE
ONSLOW | SR 1509 (QUEENS CREEK ROAD) | JONES ROAD TO SR 1565 (SMALLWOOD ROAD). WIDEN ROADWAY. | HIGHWAY | 3 | JACKSONVILLE URBAN AREA MPO | R-5948 | NOT FUNDED | NOT FUNDED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE
ONSLOW | SR 2714 | NC 53 (WESTERN BOULEVARD) TO SR 1324 (RAMSEY ROAD). | HIGHWAY | 3 | JACKSONVILLE URBAN AREA MPO | U-5791A | DIVISION 3 | DIVISION 3 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2024 | 2026 | 2 YEAR DELAY | 2024 | 2026 | 2 YEAR DELAY | 2026 | 2028 | 2 YEAR DELAY | YES
ONSLOW | SR 2715 (TRADE STREET) | NC 53 (WESTERN BOULEVARD) TO MCDANIEL DRIVE IN JACKSONVILLE. CONSTRUCT ROADWAY ON NEW LOCATION. | HIGHWAY | 3 | JACKSONVILLE URBAN AREA MPO | U-5787 | DIVISION 3 | DIVISION 3 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2023 | 2024 | 1 YEAR DELAY | 2023 | 2024 | 1 YEAR DELAY | 2025 | 2026 | 1 YEAR DELAY | YES
ONSLOW | US 17 | US 17 BUSINESS (MARINE BOULEVARD). UPGRADE AT-GRADE INTERSECTION TO PARTIAL INTERCHANGE. | HIGHWAY | 3 | JACKSONVILLE URBAN AREA MPO | U-5951 | REGION B | REGION B | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2028 | 2028 | NO CHANGE | 2028 | 2028 | NO CHANGE | 2030 | 2030 | NO CHANGE
ONSLOW | US 17 | NC 172 (SNEADS FERRY ROAD/SR 1518 (OLD FOLKSTONE ROAD). INSTALL SUPER-STREET WITH INTERSECTION IMPROVEMENTS. | HIGHWAY | 3 | JACKSONVILLE URBAN AREA MPO | U-6065 | STATEWIDE MOBILITY | STATEWIDE MOBILITY | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2024 | 2025 | 1 YEAR DELAY | 2024 | 2025 | 1 YEAR DELAY | 2026 | 2027 | 1 YEAR DELAY
ONSLOW | US 17 | MCDANIEL DRIVE /WORKSHOP LANE. UPGRADE INTERSECTION. | HIGHWAY | 3 | JACKSONVILLE URBAN AREA MPO | U-6107 | STATEWIDE MOBILITY | STATEWIDE MOBILITY | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE
ONSLOW | US 17 (WILMINGTON HIGHWAY) | SR 1130 (OLD MAPLEHURST ROAD) IN JACKSONVILLE. CONSTRUCT INTERCHANGE AND ASSOCIATED IMPROVEMENTS TO MCAS NEW RIVER MAIN GATE. | HIGHWAY | 3 | JACKSONVILLE URBAN AREA MPO | U-5735 | REGION B | REGION B | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2027 | 2027 | NO CHANGE | 2027 | 2027 | NO CHANGE | 2029 | 2031 | 2 YEAR DELAY | YES
ONSLOW | US 17 BUSINESS (MARINE BOULEVARD) | SR 1308 (BELL FORK ROAD) IN JACKSONVILLE. IMPROVE INTERSECTION. | HIGHWAY | 3 | JACKSONVILLE URBAN AREA MPO | U-5728 | REGION B | REGION B | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | UNDERWAY | UNDERWAY | NO CHANGE | UNDERWAY | UNDERWAY | NO CHANGE | 2025 | 2025 | NO CHANGE
ONSLOW | US 17 BUSINESS (MARINE BOULEVARD) | SR 1336 (HENDERSON DRIVE). IMPROVE INTERSECTION. | HIGHWAY | 3 | JACKSONVILLE URBAN AREA MPO | U-5950 | REGION B | REGION B | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2025 | 2025 | NO CHANGE | 2025 | 2025 | NO CHANGE | 2027 | 2027 | NO CHANGE
ONSLOW | US 258/NC 24 (RICHLANDS HIGHWAY) | SR 1212 (PONY FARM ROAD) TO SR 1213 (BLUE CREEK ROAD). CONSTRUCT SUPERSTREET. | HIGHWAY | 3 | JACKSONVILLE URBAN AREA MPO | U-5739 | REGION B | REGION B | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2027 | 2027 | NO CHANGE | 2027 | 2027 | NO CHANGE | 2029 | 2029 | NO CHANGE
ONSLOW | US 258/NC 24 (RICHLANDS HIGHWAY) | SR 1329 (RHODESTOWN FIRE DEPARTMENT ROAD). IMPROVE INTERSECTION. | HIGHWAY | 3 | JACKSONVILLE URBAN AREA MPO | U-6148 | NOT FUNDED | NOT FUNDED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE
ORANGE | BARNES STREET | KING STREET TO SR 1005 (JONES FERRY ROAD) IN CARRBORO. CONSTRUCT SIDEWALK. | BIKE/PED | 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | EB-5890 | DIVISION 7 | DIVISION 7 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2024 | 2024 | NO CHANGE | N/A | N/A | NO CHANGE | 2025 | 2025 | NO CHANGE
ORANGE | NC 54 | ANDERSON PARK TO JAMES STREET IN CARRBORO. CONSTRUCT MULTIUSE PATH ON NORTH SIDE OF NC 54. | BIKE/PED | 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | EB-5994 | DIVISION 7 | DIVISION 7 | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | N/A | N/A | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE
ORANGE | SR 1005 (JONES FERRY ROAD) | DAVIE ROAD TO SR 1010 (WEST MAIN STREET) IN CARRBORO. CONSTRUCT SIDEWALK ON NORTH SIDE. | BIKE/PED | 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | EB-5880 | DIVISION 7 | DIVISION 7 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2024 | 2024 | NO CHANGE | N/A | N/A | NO CHANGE | 2025 | 2025 | NO CHANGE
ORANGE | SR 1780 (ESTES DRIVE) | SR 1772 (NORTH GREENSBORO STREET) TO SOUTH OF NORFOLK-SOUTHERN RR TRACKS IN CARRBORO | BIKE/PED | 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | EB-5886A | DIVISION 7 | DIVISION 7 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2024 | 2024 | NO CHANGE | N/A | N/A | NO CHANGE | 2026 | 2026 | NO CHANGE
ORANGE | SR 1780 (ESTES DRIVE) | SOUTH OF NORFOLK-SOUTHERN RR TRACKS TO NC 86 (MARTIN LUTHER KING, JR. BLVD) IN CHAPEL HILL | BIKE/PED | 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | EB-5886B | DIVISION 7 | DIVISION 7 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2023 | 2023 | NO CHANGE | N/A | N/A | NO CHANGE | 2025 | 2025 | NO CHANGE
ORANGE | US 15 / US 501 | WILLOW DRIVE TO SR 1741 / SR 1838 (OLD DURHAM-CHAPEL HILL ROAD) IN CHAPEL HILL. CONSTRUCT MULTIUSE PATHS. | BIKE/PED | 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | EB-5998 | DIVISION 7 | DIVISION 7 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | N/A | N/A | NO CHANGE | N/A | N/A | NO CHANGE | 2026 | 2026 | NO CHANGE
ORANGE | I-40 | NC 86 UPGRADE TO SUPERSTREET FROM NORTHWOOD DRIVE TO RAMP C/D AT I-40 INTERCHANGE. | HIGHWAY | 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | I-3306AC | REGION D | REGION D | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2024 | 2024 | NO CHANGE | 2024 | 2024 | NO CHANGE | 2026 | 2026 | NO CHANGE
ORANGE | I-85 | SR 1009 (SOUTH CHURTON STREET) IN HILLSBOROUGH. INTERCHANGE IMPROVEMENTS. | HIGHWAY | 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | I-5967 | STATEWIDE MOBILITY | STATEWIDE MOBILITY | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2028 | 2028 | NO CHANGE | 2028 | 2028 | NO CHANGE | 2031 | 2031 | NO CHANGE
ORANGE | I-85 | NC 86 IN HILLSBOROUGH. UPGRADE INTERCHANGE. | HIGHWAY | 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | I-5984 | STATEWIDE MOBILITY | STATEWIDE MOBILITY | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE
ORANGE | NC 54 | SR 1006 (ORANGE GROVE ROAD) TO SR 1107 / SR 1937 (OLD FAYETTEVILLE ROAD). CONSTRUCT OPERATIONAL IMPROVEMENTS, INCLUDING BICYCLE/PEDESTRIAN ACCOMMODATIONS | HIGHWAY | 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | R-5821A | REGION D | REGION D | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE
ORANGE | SR 1009 (SOUTH CHURTON STREET) | I-40 TO ENO RIVER IN HILLSBOROUGH. WIDEN TO MULTILANES. | HIGHWAY | 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | U-5845 | DIVISION 7 | DIVISION 7 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2028 | 2028 | NO CHANGE | 2028 | 2028 | NO CHANGE | 2031 | 2031 | NO CHANGE
ORANGE | US 15 / US 501 | NC 86 (SOUTH COLUMBIA STREET). INTERCHANGE IMPROVEMENTS. | HIGHWAY | 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | U-5304A | NOT FUNDED | NOT FUNDED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE
ORANGE | US 15 / US 501 | NC 86 (SOUTH COLUMBIA STREET) TO NC 54 (RALEIGH ROAD). CAPACITY IMPROVEMENTS , WITH SIDEWALKS, WIDE OUTSIDE LANES AND TRANSIT ACCOMMODATIONS. | HIGHWAY | 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | U-5304B | NOT FUNDED | NOT FUNDED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE
ORANGE | US 15 / US 501 | NC 54 (RALEIGH ROAD). TO SR 1742 (EPHESUS CHURCH ROAD). CAPACITY IMPROVEMENTS , WITH SIDEWALKS, WIDE OUTSIDE LANES AND TRANSIT ACCOMMODATIONS. | HIGHWAY | 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | U-5304D | NOT FUNDED | NOT FUNDED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE
ORANGE | US 15 / US 501 | SR 1902 (MANNING DRIVE). CONVERT AT-GRADE INTERSECTION TO INTERCHANGE. | HIGHWAY | 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | U-5304E | NOT FUNDED | NOT FUNDED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE
ORANGE | GO TRIANGLE | UNC HOSPITALS AREA IN CHAPEL HILL. CONSTRUCT NEIGHBORHOOD TRANSIT CENTER TRANSFER STATION. 400; 405; 420; 800; 805; CRX; FCX | PUBLIC TRANSIT | 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | TD-5284 | REGION D | REGION D | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | N/A | N/A | NO CHANGE | N/A | N/A | NO CHANGE | 2024 | 2024 | NO CHANGE
ORANGE, DURHAM | I-85 | WEST OF SR 1006 (ORANGE GROVE ROAD) IN ORANGE COUNTY TO WEST OF SR 1400 (SPARGER ROAD) IN DURHAM COUNTY. ADD LANES. | HIGHWAY | 5, 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | I-0305 | STATEWIDE MOBILITY | STATEWIDE MOBILITY | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE
ORANGE, DURHAM | NC 54 | WEST OF US 15 / US 501 IN ORANGE COUNTY TO EAST OF SR 1110 (BARBEE CHAPEL ROAD) IN DURHAM COUNTY. UPGRADE ROADWAY CORRIDOR. | HIGHWAY | 5, 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | U-5774B | REGION C, D | REGION C, D | SCHEDULED FOR DELIVERY | WILL BE REPRIORITIZED | 2027 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | PROJECT UNCOMMITTED | 2027 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | PROJECT UNCOMMITTED | 2030 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | PROJECT UNCOMMITTED |  | YES
ORANGE, DURHAM | US 15 / US 501 | SR 1742 (EPHESUS CHURCH ROAD) TO I-40. CORRIDOR CAPACITY IMPROVEMENTS. | HIGHWAY | 5, 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | U-5304F | NOT FUNDED | REGION D, C | WILL BE REPRIORITIZED | SCHEDULED FOR DELIVERY | NOT FUNDED | 2028 | PROJECT BECOMES COMMITTED | NOT FUNDED | 2028 | PROJECT BECOMES COMMITTED | NOT FUNDED | 2030 | PROJECT BECOMES COMMITTED |  | YES
PASQUOTANK | US 17 (HUGHES BOULEVARD) | SR 1308 (CHURCH STREET) TO US 17 BUSINESS (NORTH ROAD STREET). ACCESS MANAGEMENT. | HIGHWAY | 1 | ALBEMARLE RPO | U-5940 | REGION A | REGION A | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2025 | 2025 | NO CHANGE | 2025 | 2025 | NO CHANGE | 2027 | 2027 | NO CHANGE
PASQUOTANK | US 17 BUSINESS | SR 1145 (OAK STUMP ROAD). IMPROVE INTERSECTION. | HIGHWAY | 1 | ALBEMARLE RPO | U-5939 | REGION A | REGION A | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2024 | 2024 | NO CHANGE | 2024 | 2024 | NO CHANGE | 2025 | 2025 | NO CHANGE
PENDER | HENDERSON FIELD (ACZ) | APRON EXPANSION. | AVIATION | 3 | CAPE FEAR RPO | AV-5815 | DIVISION 3 | DIVISION 3 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | N/A | N/A | NO CHANGE | N/A | N/A | NO CHANGE | 2024 | 2024 | NO CHANGE
PENDER | NC 210 | SR 1560 (WATTS LANDING ROAD). CONSTRUCT ROUNDABOUT. | HIGHWAY | 3 | CAPE FEAR RPO | R-5899 | NOT FUNDED | DIVISION 3 | WILL BE REPRIORITIZED | SCHEDULED FOR DELIVERY | NOT FUNDED | 2025 | PROJECT BECOMES COMMITTED | NOT FUNDED | 2025 | PROJECT BECOMES COMMITTED | NOT FUNDED | 2027 | PROJECT BECOMES COMMITTED |  | YES
PENDER | NC 50/NC 210 | SR 1534 (BELT ROAD). CONSTRUCT ROUNDABOUT. | HIGHWAY | 3 | CAPE FEAR RPO | R-5900 | NOT FUNDED | DIVISION 3 | WILL BE REPRIORITIZED | SCHEDULED FOR DELIVERY | NOT FUNDED | 2025 | PROJECT BECOMES COMMITTED | NOT FUNDED | 2025 | PROJECT BECOMES COMMITTED | NOT FUNDED | 2028 | PROJECT BECOMES COMMITTED |  | YES
PENDER | NC 53 | US 117 BUSINESS (WALKER STREET/WILMINGTON STREET). IMPROVE INTERSECTION. | HIGHWAY | 3 | CAPE FEAR RPO | R-5701 | REGION B | REGION B | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2025 | 2025 | NO CHANGE | 2025 | 2025 | NO CHANGE | 2027 | 2027 | NO CHANGE
PENDER | NC 53 | US 117 BYPASS TO STAG PARK ROAD. WIDEN TO THREE LANES. | HIGHWAY | 3 | CAPE FEAR RPO | R-5850 | DIVISION 3 | NOT FUNDED | SCHEDULED FOR DELIVERY | WILL BE REPRIORITIZED | 2023 | NOT FUNDED | PROJECT NO LONGER FUNDED | 2023 | NOT FUNDED | PROJECT NO LONGER FUNDED | 2025 | NOT FUNDED | PROJECT NO LONGER FUNDED |  | YES
PENDER | US 17 | NC 210 (SURF CITY). INTERSECTION IMPROVEMENT AT US 17 AND NC 210 NEAR SURF CITY. | HIGHWAY | 3 | CAPE FEAR RPO | R-5877 | NOT FUNDED | NOT FUNDED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE
PENDER | US 17 | US 17 FROM SR 1582 (WASHINGTON ACRES ROAD) TO VISTA LANE. CONVERT TO SUPERSTREET. | HIGHWAY | 3 | WILMINGTON URBAN AREA MPO | U-5732 | REGION B | REGION B | SCHEDULED FOR DELIVERY | WILL BE REPRIORITIZED | UNDERWAY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | PROJECT UNCOMMITTED | UNDERWAY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | PROJECT UNCOMMITTED | 2026 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | PROJECT UNCOMMITTED |  | YES
PENDER, NEW HANOVER | US 17 | US 17 BYPASS SOUTH OF HAMPSTEAD TO NC 210. | HIGHWAY | 3 | WILMINGTON URBAN AREA MPO | R-3300A | REGION B | REGION B | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | UNDERWAY | UNDERWAY | NO CHANGE | UNDERWAY | UNDERWAY | NO CHANGE | 2027 | 2026 | 1 YEAR ACCELERATION |  | YES
PERQUIMANS | SR 1300 (NEW HOPE ROAD) | WOODLAND CHURCH ROAD TO WOODVILLE ROAD (SR 1329). MODERNIZE ROADWAY. | HIGHWAY | 1 | ALBEMARLE RPO | R-5939 | DIVISION 1 | DIVISION 1 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2028 | 2028 | NO CHANGE | 2028 | 2028 | NO CHANGE | 2030 | 2030 | NO CHANGE
PERQUIMANS | US 17 | SR 1336 (HARVEY POINT ROAD) AND SR 1338 (WYNNE FORK ROAD). CONVERT AT-GRADE INTERSECTION TO AN INTERCHANGE. | HIGHWAY | 1 | ALBEMARLE RPO | R-5869A | DIVISION 1 | DIVISION 1 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2028 | 2028 | NO CHANGE | 2028 | 2028 | NO CHANGE | 2030 | 2031 | 1 YEAR DELAY
PERQUIMANS | US 17 | SR 1300 (NEW HOPE ROAD). CONVERT AT-GRADE INTERSECTION TO INTERCHANGE. | HIGHWAY | 1 | ALBEMARLE RPO | R-5869B | DIVISION 1 | DIVISION 1 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2028 | 2028 | NO CHANGE | 2028 | 2028 | NO CHANGE | 2030 | 2032 | 2 YEAR DELAY
PERSON | PERSON COUNTY EXECUTIVE AIRPORT (TDF) | EXTEND RUNWAY TO TOTAL LENGTH OF 7000 FT, CONSTRUCT TAXIWAY EXTENSION AND RELOCATE SR 1311 (CATES MILL ROAD). | AVIATION | 5 | KERR-TAR RPO | AV-5818 | DIVISION 5 | DIVISION 5 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | N/A | N/A | NO CHANGE | N/A | N/A | NO CHANGE | 2028 | 2028 | NO CHANGE
PERSON | US 501 | SOUTH OF US 158 TO NC 157. | HIGHWAY | 5 | KERR-TAR RPO | U-5969A | DIVISION 5 | DIVISION 5 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2027 | 2027 | NO CHANGE | 2027 | 2027 | NO CHANGE | 2029 | 2029 | NO CHANGE
PERSON | US 501 | NC 157 TO SR 1596 (WEST MOREHEAD STREET) | HIGHWAY | 5 | KERR-TAR RPO | U-5969B | REGION C | REGION C | SCHEDULED FOR DELIVERY | WILL BE REPRIORITIZED | 2023 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | PROJECT UNCOMMITTED | 2023 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | PROJECT UNCOMMITTED | 2025 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | PROJECT UNCOMMITTED
PERSON | US 501 / NC 49 | SR 1596 (WEST MOREHEAD STREET) TO SR 1601 (NORTH MAIN STREET) | HIGHWAY | 5 | KERR-TAR RPO | U-5969C | REGION C | REGION C | SCHEDULED FOR DELIVERY | WILL BE REPRIORITIZED | 2023 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | PROJECT UNCOMMITTED | 2023 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | PROJECT UNCOMMITTED | 2025 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | PROJECT UNCOMMITTED
PITT | NC 11 (MEMORIAL DRIVE) | NC 43 (WEST FIFTH STREET) TO SR 1128 (DAVENPORT FARM ROAD) IN GREENVILLE. CONSTRUCT SIDEWALK. | BIKE/PED | 2 | GREENVILLE URBAN AREA MPO | EB-5981 | NOT FUNDED | NOT FUNDED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE
PITT | US 264-A (GREENVILLE BOULEVARD) | US 264-A TO US 13 (DICKINSON AVENUE) IN GREENVILLE. CONSTRUCT SIDEWALK AND CURB AND GUTTER. | BIKE/PED | 2 | GREENVILLE URBAN AREA MPO | EB-5980 | NOT FUNDED | NOT FUNDED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE
PITT | GREENVILLE | GREENVILLE SIGNAL SYSTEM. | HIGHWAY | 2 | GREENVILLE URBAN AREA MPO | U-5952 | REGION B | REGION B | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | N/A | N/A | NO CHANGE | 2026 | 2026 | NO CHANGE | 2028 | 2028 | NO CHANGE
PITT | NC 33 | SR 1755 (BLACKJACK-SIMPSON ROAD) TO SR 1760 (MOBLEYS BRIDGE ROAD). WIDEN TO MULTI-LANES. | HIGHWAY | 2 | GREENVILLE URBAN AREA MPO, MID-EAST RPO | U-6215 | NOT FUNDED | NOT FUNDED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE
PITT | NC 33 (10TH STREET) | OXFORD ROAD TO SR 1702 (EVANS STREET). ACCESS MANAGEMENT. | HIGHWAY | 2 | GREENVILLE URBAN AREA MPO | U-6125 | NOT FUNDED | NOT FUNDED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE
PITT | NC 43 | SR 1708 (FIRETOWER ROAD) TO SR 1711 (WORTHINGTON ROAD). WIDEN TO MULTI-LANES. | HIGHWAY | 2 | GREENVILLE URBAN AREA MPO | U-5991 | DIVISION 2 | DIVISION 2 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2027 | 2027 | NO CHANGE | 2027 | 2027 | NO CHANGE | 2029 | 2029 | NO CHANGE
PITT | NC 43 (CHARLES BOULEVARD) | US 264A (GREENVILLE BOULEVARD) TO SR 1726 (BELLS FORK ROAD). ACCESS MANAGEMENT. | HIGHWAY | 2 | GREENVILLE URBAN AREA MPO | U-6147 | NOT FUNDED | NOT FUNDED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE
PITT | SR 1203 (ALLEN ROAD) | SR 1467 (STANTONSBURG ROAD) TO US 13 (DICKINSON AVENUE EXTENSION). WIDEN TO MULTI-LANES. | HIGHWAY | 2 | GREENVILLE URBAN AREA MPO | U-5875 | DIVISION 2 | DIVISION 2 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | UNDERWAY | UNDERWAY | NO CHANGE | UNDERWAY | UNDERWAY | NO CHANGE | 2024 | 2024 | NO CHANGE
PITT | SR 1467 (STANTONSBURG ROAD) | SR 1204 (B'S BARBEQUE ROAD) TO NC 11 (MEMORIAL DRIVE). ACCESS MANAGEMENT. | HIGHWAY | 2 | GREENVILLE URBAN AREA MPO | U-6195 | NOT FUNDED | NOT FUNDED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE
PITT | SR 1700 (EVANS STREET/ OLD TAR ROAD) | SR 1711 (WORTHINGTON ROAD) IN WINTERVILLE TO US 264 ALTERNATE (GREENVILLE BOULEVARD) IN GREENVILLE. WIDEN TO MULTI-LANES. | HIGHWAY | 2 | GREENVILLE URBAN AREA MPO | U-2817 | DIVISION 2 | DIVISION 2 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2019 | 2019 | NO CHANGE | 2019 | 2019 | NO CHANGE | 2025 | 2025 | NO CHANGE
PITT | SR 1702 (EVANS STREET) | SR 1155 (RED BANKS ROAD) TO WEST 5TH STREET. ACCESS MANAGEMENT. | HIGHWAY | 2 | GREENVILLE URBAN AREA MPO | U-6196 | NOT FUNDED | NOT FUNDED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE
PITT | SR 1704 (FOURTEENTH STREET) | RED BANKS ROAD TO SR 1708 (FIRETOWER ROAD). WIDEN TO MULTI-LANES. | HIGHWAY | 2 | GREENVILLE URBAN AREA MPO | U-5917 | DIVISION 2 | DIVISION 2 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2019 | 2019 | NO CHANGE | 2019 | 2019 | NO CHANGE | 2026 | 2026 | NO CHANGE
PITT | SR 1708 (FIRETOWER ROAD) | WEST OF EAST ARLINGTON BOULEVARD TO SR 1704 (FOURTEENTH STREET) IN GREENVILLE. WIDEN TO MULTI-LANES. | HIGHWAY | 2 | GREENVILLE URBAN AREA MPO | U-5785 | DIVISION 2 | DIVISION 2 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2024 | 2024 | NO CHANGE | 2024 | 2024 | NO CHANGE | 2026 | 2026 | NO CHANGE
PITT | SR 1708 (FIRETOWER ROAD) | SR 1704 (FOURTEENTH STREET) TO NC 33 (EAST 10TH STREET) IN GREENVILLE. WIDEN TO MULTI-LANES. | HIGHWAY | 2 | GREENVILLE URBAN AREA MPO | U-5870 | DIVISION 2 | DIVISION 2 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2024 | 2024 | NO CHANGE | 2024 | 2024 | NO CHANGE | 2026 | 2026 | NO CHANGE
PITT | SR 1711 (WORTHINGTON ROAD) | SR 1725 (COUNTY HOME ROAD). UPGRADE INTERSECTION. | HIGHWAY | 2 | GREENVILLE URBAN AREA MPO | U-6197 | DIVISION 2 | DIVISION 2 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2027 | 2027 | NO CHANGE | 2027 | 2027 | NO CHANGE | 2029 | 2029 | NO CHANGE
PITT | US 13 (MEMORIAL DRIVE) | NC 43 (5TH STREET). UPGRADE INTERSECTION. | HIGHWAY | 2 | GREENVILLE URBAN AREA MPO | U-5730 | REGION B | REGION B | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | UNDERWAY | UNDERWAY | NO CHANGE | UNDERWAY | UNDERWAY | NO CHANGE | 2025 | 2025 | NO CHANGE
POLK | I-26 | CONSTRUCT IMPROVEMENTS ON NC 108 AT EXIT 67. | HIGHWAY | 14 | FOOTHILLS RPO | I-4729B | REGION G | REGION G | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2027 | 2027 | NO CHANGE | 2027 | 2027 | NO CHANGE | 2029 | 2029 | NO CHANGE
POLK | NC 9 | US 74 TO NC 108. ADD PAVED SHOULDERS. | HIGHWAY | 14 | FOOTHILLS RPO | R-5840 | DIVISION 14 | DIVISION 14 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2022 | 2022 | NO CHANGE | 2022 | 2022 | NO CHANGE | 2025 | 2025 | NO CHANGE
POLK | US 74 | NC 108 INTERCHANGE. IMPROVE INTERCHANGE. | HIGHWAY | 14 | FOOTHILLS RPO | R-5873 | STATEWIDE MOBILITY | STATEWIDE MOBILITY | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | N/A | N/A | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE
RANDOLPH | REGIONAL AIRPORT (HBI) ASHEBORO | CONSTRUCT TAXILANE EXTENSION, EXTEND ACCESS ROAD, AND CONSTRUCT NEW ACCESS ROAD. | AVIATION | 8 | PIEDMONT TRIAD RPO | AV-5858 | DIVISION 8 | DIVISION 8 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | N/A | N/A | NO CHANGE | N/A | N/A | NO CHANGE | 2025 | 2025 | NO CHANGE
RANDOLPH | SR 1950 (WEST NAOMI STREET) | WEST ACADEMY STREET TO US 220 BUSINESS (SOUTH MAIN STREET) IN RANDLEMAN. CONSTRUCT SIDEWALK, IMPLEMENT ROAD DIET, AND INSTALL RAISED CROSSWALK AND MEDIAN. | BIKE/PED | 8 | PIEDMONT TRIAD RPO | EB-5898 | DIVISION 8 | DIVISION 8 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2024 | 2024 | NO CHANGE | N/A | N/A | NO CHANGE | 2024 | 2024 | NO CHANGE
RANDOLPH | US 64 / NC 49 (EAST DIXIE DRIVE) | EXECUTIVE WAY TO CENTERPOINT PLAZA SHOPPING CENTER IN ASHEBORO. CONSTRUCT SIDEWALK. | BIKE/PED | 8 | PIEDMONT TRIAD RPO | EB-6004 | DIVISION 8 | DIVISION 8 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | N/A | N/A | NO CHANGE | N/A | N/A | NO CHANGE | 2024 | 2024 | NO CHANGE
RANDOLPH | I-85 | SR 1009 (SOUTH MAIN STREET) IN ARCHDALE. INTERCHANGE IMPROVEMENTS. | HIGHWAY | 8 | HIGH POINT URBAN AREA MPO | U-5770 | REGION E | REGION E | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2022 | 2022 | NO CHANGE | 2022 | 2022 | NO CHANGE | N/A | N/A | NO CHANGE
RANDOLPH | NC 159 (ZOO PARKWAY) | RIDGE STREET IN ASHEBORO. IMPROVE INTERSECTION. | HIGHWAY | 8 | PIEDMONT TRIAD RPO | R-5958 | DIVISION 8 | DIVISION 8 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2023 | 2024 | 1 YEAR DELAY | 2023 | 2024 | 1 YEAR DELAY | 2025 | 2026 | 1 YEAR DELAY | YES
RANDOLPH | NC 42 | SR 2237 (EAST SALISBURY STREET) TO NORTH OF US 64 / NC 49 (DIXIE DRIVE) IN ASHEBORO. WIDEN TO THREE LANES. | HIGHWAY | 8 | PIEDMONT TRIAD RPO | U-5743 | REGION E | REGION E | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2022 | 2022 | NO CHANGE | 2022 | 2022 | NO CHANGE | 2024 | 2025 | 1 YEAR DELAY | YES
RANDOLPH | NC 42 (EAST SALISBURY STREET) | SR 2189 (MARTIN LUTHER KING, JR. DRIVE) / NORTH RANDOLPH AVENUE TO SR 2237 (EAST SALISBURY STREET) IN ASHEBORO. IMPROVE CORRIDOR. | HIGHWAY | 8 | PIEDMONT TRIAD RPO | R-5957 | NOT FUNDED | NOT FUNDED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE
RANDOLPH | NC 49 | SR 1174 (WAYNICK MEADOW ROAD) TO SOUTH OF SR 1193 (OLD NC 49). WIDEN TO MULTILANES. | HIGHWAY | 8 | PIEDMONT TRIAD RPO | R-5931 | NOT FUNDED | NOT FUNDED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE
RANDOLPH | NC 62 | SR 3252 (SURRETT DRIVE) IN TRINITY TO SR 1009 (NORTH MAIN STREET) IN ARCHDALE. MODERNIZE ROADWAY. | HIGHWAY | 8 | HIGH POINT URBAN AREA MPO | U-6191 | DIVISION 8 | DIVISION 8 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2027 | 2028 | 1 YEAR DELAY | 2027 | 2028 | 1 YEAR DELAY | 2029 | 2030 | 1 YEAR DELAY
RANDOLPH | SR 1009 (SOUTH MAIN STREET) | WEST OF COLUMBUS AVENUE TO SR 3182 (COMANCHE ROAD/TARHEEL ROAD). MILLING AND RESURFACING. | HIGHWAY | 8 | HIGH POINT URBAN AREA MPO | U-5770A | REGION E | REGION E | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | N/A | N/A | NO CHANGE | N/A | N/A | NO CHANGE | 2023 | 2023 | NO CHANGE
RANDOLPH | SR 1009 (SOUTH MAIN STREET) | WEST OF COLUMBUS AVENUE TO SR 3182 (COMANCHE ROAD/TARHEEL ROAD). CONSTRUCT DDI AND RCI IMPROVEMENTS. | HIGHWAY | 8 | HIGH POINT URBAN AREA MPO | U-5770B | REGION E | REGION E | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | N/A | N/A | NO CHANGE | N/A | N/A | NO CHANGE | 2025 | 2026 | 1 YEAR DELAY | YES
RANDOLPH | SR 1547 (FINCH FARM ROAD) | SR 3106 (KENNEDY ROAD) TO I-85 IN TRINITY. WIDEN TO MULTILANES. | HIGHWAY | 8 | HIGH POINT URBAN AREA MPO | U-5308 | DIVISION 8 | DIVISION 8 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2019 | 2020 | 1 YEAR DELAY | 2019 | 2020 | 1 YEAR DELAY | 2025 | 2027 | 2 YEAR DELAY | YES
RANDOLPH | SR 1712 (PINEVIEW STREET) | WEST OF SYLVAN STREET TO US 220 BUSINESS IN ASHEBORO. WIDEN TO MULTILANES. | HIGHWAY | 8 | PIEDMONT TRIAD RPO | U-5711 | DIVISION 8 | DIVISION 8 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | UNDERWAY | UNDERWAY | NO CHANGE | UNDERWAY | UNDERWAY | NO CHANGE | 2024 | 2024 | NO CHANGE
RANDOLPH | US 220 BUSINESS | SR 2123 (CAUDLE ROAD) TO SR 2270 (US 311 EXTENSION) IN RANDLEMAN. WIDEN TO 4-LANE DIVIDED FACILITY. | HIGHWAY | 8 | PIEDMONT TRIAD RPO | U-6006 | DIVISION 8 | DIVISION 8 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2023 | 2024 | 1 YEAR DELAY | 2023 | 2024 | 1 YEAR DELAY | 2026 | 2027 | 1 YEAR DELAY | YES
RANDOLPH | US 220 BUSINESS (NORTH FAYETTEVILLE STREET) | SR 2269 (VISION DRIVE) TO SR 2149 (HUB MORRIS ROAD). WIDEN TO MULTILANES. | HIGHWAY | 8 | PIEDMONT TRIAD RPO | R-5956A | NOT FUNDED | NOT FUNDED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE
RANDOLPH | US 220 BUSINESS (NORTH FAYETTEVILLE STREET) | SR 2149 (HUB MORRIS ROAD) TO SR 2123 (CAUDLE ROAD). WIDEN TO MULTILANES. | HIGHWAY | 8 | PIEDMONT TRIAD RPO | R-5956B | NOT FUNDED | NOT FUNDED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE
RANDOLPH | US 64 | SR 1409 (LAKE PARK ROAD) TO ASHEBORO BYPASS | HIGHWAY | 8 | PIEDMONT TRIAD RPO | R-2220DA | REGION E | REGION E | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2027 | 2028 | 1 YEAR DELAY | 2027 | 2028 | 1 YEAR DELAY | 2029 | 2031 | 2 YEAR DELAY
RANDOLPH, GUILFORD | SR 1577 / SR 1004 (ARCHDALE ROAD) | US 311 (MAIN STREET) TO EAST OF SPRINGWOOD LANE IN ARCHDALE. WIDEN TO MULTILANES. | HIGHWAY | 7, 8 | HIGH POINT URBAN AREA MPO | U-3400 | DIVISION 7, 8 | DIVISION 7, 8 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2023 | 2024 | 1 YEAR DELAY | 2023 | 2024 | 1 YEAR DELAY | 2026 | 2029 | 3 YEAR DELAY | YES
RANDOLPH, GUILFORD | SR 1595 / SR 4053 (SURRETT DRIVE) | I-85 IN TRINITY TO SR 1300 (WEST FAIRFIELD ROAD) IN HIGH POINT. WIDEN TO MULTILANES. | HIGHWAY | 7, 8 | HIGH POINT URBAN AREA MPO | U-5864 | DIVISION 7, 8 | DIVISION 7, 8 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2026 | 2026 | NO CHANGE | 2026 | 2026 | NO CHANGE | 2029 | 2029 | NO CHANGE
RICHMOND | RICHMOND COUNTY AIRPORT (RCZ) | EXTEND RUNWAY 14-32 TO 5500 FEET. | AVIATION | 8 | LUMBER RIVER RPO | AV-5763 | DIVISION 8 | DIVISION 8 | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | N/A | N/A | NO CHANGE | N/A | N/A | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE
RICHMOND | SR 1639 (SPRING STREET); SR 1615 (SOUTH MAIN STREE | SPRING STREET FROM SR 1640 (WIREGRASS ROAD) TO NC 177 AND MAIN STREET FROM BRIDGES STREET TO NC 38 IN HAMLET. CONSTRUCT SIDEWALKS. | BIKE/PED | 8 | LUMBER RIVER RPO | EB-6018 | DIVISION 8 | DIVISION 8 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2024 | 2024 | NO CHANGE | 2024 | 2024 | NO CHANGE | 2025 | 2025 | NO CHANGE
RICHMOND | US 1 | US 74 BUSINESS TO NORTH OF SR 1606 (FOX ROAD) | HIGHWAY | 8 | LUMBER RIVER RPO | R-2501BC | NOT FUNDED | NOT FUNDED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE
RICHMOND | US 1 | SR 1640 (WIREGRASS ROAD) TO LOCH LAURIN LANE. WIDEN TO MULTILANES. | HIGHWAY | 8 | LUMBER RIVER RPO | R-5928 | DIVISION 8 | DIVISION 8 | SCHEDULED FOR DELIVERY | WILL BE REPRIORITIZED | 2027 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | PROJECT UNCOMMITTED | 2027 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | PROJECT UNCOMMITTED | 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | PROJECT UNCOMMITTED
RICHMOND | US 1 (PROPOSED) /SR 1516 (GREENE STREET) | US 220 TO US 1 IN ROCKINGHAM. WIDEN TO 3-LANE FACILITY AND RE-ROUTE US 1 ALONG PROJECT. | HIGHWAY | 8 | LUMBER RIVER RPO | U-6027 | DIVISION 8 | DIVISION 8 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2023 | 2024 | 1 YEAR DELAY | 2023 | 2024 | 1 YEAR DELAY | 2025 | 2027 | 2 YEAR DELAY | YES
RICHMOND | US 74 / FUTURE I-74 | US 1 (EXIT 311). INTERCHANGE IMPROVEMENTS. | HIGHWAY | 8 | LUMBER RIVER RPO | I-5979 | DIVISION 8 | DIVISION 8 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2022 | 2022 | NO CHANGE | 2022 | 2022 | NO CHANGE | 2024 | 2024 | NO CHANGE
RICHMOND | VARIOUS | US 74 BUSINESS TO SR 1426 (ABERDEEN ROAD). CONSTRUCT TWO LANE FACILITY UTILIZING SECTIONS OF SR 1641 (CLEMMER ROAD) AND SR 1645 (MT. OLIVE CHURCH ROAD), REMAINDER ON NEW LOCATION. | HIGHWAY | 8 | LUMBER RIVER RPO | U-5706 | DIVISION 8 | DIVISION 8 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2023 | 2025 | 2 YEAR DELAY | 2023 | 2025 | 2 YEAR DELAY | 2026 | 2027 | 1 YEAR DELAY | YES
ROBESON | LUMBERTON REGIONAL AIRPORT (LBT) | RUNWAY 13-31. CONSTRUCT TAXIWAYS. | AVIATION | 6 | LUMBER RIVER RPO | AV-5901 | DIVISION 6 | DIVISION 6 | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | N/A | N/A | NO CHANGE | N/A | N/A | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE
ROBESON | NC 711 (THIRD STREET) | SR 1563 (UNION CHAPEL ROAD) TO WALMART SHOPPING CENTER/JOHNES ROAD IN PEMBROKE. CONSTRUCT SIDEWALKS. | BIKE/PED | 6 | LUMBER RIVER RPO | EB-6013 | DIVISION 6 | DIVISION 6 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2028 | 2028 | NO CHANGE | N/A | N/A | NO CHANGE | 2029 | 2029 | NO CHANGE
ROBESON | I-95 | CONSTRUCT WEIGH IN MOTION STATION. | HIGHWAY | 6 | LUMBER RIVER RPO | I-5987AA | REGION C | REGION C | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | N/A | N/A | NO CHANGE | N/A | N/A | NO CHANGE | 2025 | 2025 | NO CHANGE
ROBESON | NC 20 | SR 1743 (COVINGTON FARM ROAD) TO I-95. WIDEN TO MULTI-LANES. | HIGHWAY | 6 | LUMBER RIVER RPO | R-5904 | NOT FUNDED | NOT FUNDED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE
ROBESON | NC 41 (EAST ELIZABETHTOWN ROAD) | SR 2110 (SNAKE ROAD) TO SYCAMORE LANE. WIDEN EXISTING ROADWAY. | HIGHWAY | 6 | LUMBER RIVER RPO | R-5888 | REGION C | REGION C | SCHEDULED FOR DELIVERY | WILL BE REPRIORITIZED | 2028 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | PROJECT UNCOMMITTED | 2028 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | PROJECT UNCOMMITTED | 2030 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | PROJECT UNCOMMITTED
ROBESON | NC 41 (MARTIN LUTHER KING DRIVE) | US 74 TO MARION ROAD. WIDEN ROADWAY. | HIGHWAY | 6 | LUMBER RIVER RPO | R-5951 | NOT FUNDED | NOT FUNDED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE
ROBESON | NC 711 | SR 1340 (ODOM STREET-PHILADELPHUS ROAD) IN PEMBROKE TO SR 1557 (REDMOND ROAD). WIDEN TO MULTI-LANES. | HIGHWAY | 6 | LUMBER RIVER RPO | R-4428 | REGION C | REGION C | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE
ROBESON | SR 1945 (MEADOW ROAD) | SR 1984 (LINKHAW ROAD). IMPROVE INTERSECTION. | HIGHWAY | 6 | LUMBER RIVER RPO | R-5954 | NOT FUNDED | NOT FUNDED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE
ROBESON | SR 1997 (FAYETTEVILLE ROAD) | I-95 TO FARRINGTON STREET. WIDEN ROADWAY. | HIGHWAY | 6 | LUMBER RIVER RPO | R-5955 | NOT FUNDED | NOT FUNDED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE
ROBESON | SR 1997 (FAYETTEVILLE ROAD) | FARRINGTON STREET TO EAST 22ND STREET. WIDEN TO MULTI-LANES. | HIGHWAY | 6 | LUMBER RIVER RPO | U-5797 | DIVISION 6 | DIVISION 6 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2023 | 2023 | NO CHANGE | 2023 | 2023 | NO CHANGE | 2024 | 2024 | NO CHANGE
ROBESON | US 74 | CONVERT AT-GRADE INTERSECTION OF US 74 AND SR 2225 (CREEK ROAD) TO GRADE SEPARATION. | HIGHWAY | 6 | LUMBER RIVER RPO | I-6011A | DIVISION 6 | DIVISION 6 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2025 | 2025 | NO CHANGE | 2025 | 2025 | NO CHANGE | 2027 | 2027 | NO CHANGE
ROCKINGHAM | ROCKINGHAM COUNTY / NC SHILOH AIRPORT (SIF) | CONSTRUCT T-HANGAR TAXILANES FOR ADDITION OF T-HANGARS. | AVIATION | 7 | PIEDMONT TRIAD RPO | AV-5898 | DIVISION 7 | DIVISION 7 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | N/A | N/A | NO CHANGE | N/A | N/A | NO CHANGE | 2025 | 2025 | NO CHANGE
ROCKINGHAM | ROCKINGHAM COUNTY AIRPORT (SIF) | EXTEND RUNWAY TO 5500 FT. | AVIATION | 7 | PIEDMONT TRIAD RPO | AV-5852 | DIVISION 7 | DIVISION 7 | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | N/A | N/A | NO CHANGE | N/A | N/A | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE
ROCKINGHAM | FUTURE I-73 / US 220 | US 311 / NC 135 INTERCHANGE. REPLACE BRIDGE 780074 AND UPGRADE INTERCHANGE. | HIGHWAY | 7 | PIEDMONT TRIAD RPO | I-5898 | REGION D | REGION D | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2022 | 2022 | NO CHANGE | 2022 | 2022 | NO CHANGE | 2025 | 2025 | NO CHANGE
ROCKINGHAM | NC 65 / NC 87 | WEST OF SR 2371 (OLD COUNTY HOME ROAD) IN WENTWORTH TO SR 1001 (SANDY CROSS ROAD) / SR 1998 (WENTWORTH STREET) | HIGHWAY | 7 | PIEDMONT TRIAD RPO | R-5766A | DIVISION 7 | DIVISION 7 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2024 | 2024 | NO CHANGE | 2024 | 2024 | NO CHANGE | 2026 | 2026 | NO CHANGE
ROCKINGHAM | NC 65 / NC 87 | SR 1001 (SANDY CROSS ROAD) / SR 1998 (WENTWORTH STREET) TO SR 2413 (VANCE STREET EXTENSION) | HIGHWAY | 7 | PIEDMONT TRIAD RPO | R-5766B | DIVISION 7 | DIVISION 7 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2024 | 2024 | NO CHANGE | 2024 | 2024 | NO CHANGE | 2026 | 2026 | NO CHANGE
ROCKINGHAM | NC 65 / NC 87 | SR 2413 (VANCE STREET EXTENSION) TO US 158 / US 29 BUSINESS IN REIDSVILLE | HIGHWAY | 7 | PIEDMONT TRIAD RPO | R-5766C | DIVISION 7 | DIVISION 7 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2024 | 2024 | NO CHANGE | 2024 | 2024 | NO CHANGE | 2026 | 2026 | NO CHANGE
ROCKINGHAM | US 311 / NC 14 (SOUTH VAN BUREN ROAD) | SR 2066 (KINGS HIGHWAY) IN EDEN. CONVERT AT-GRADE INTERSECTION TO INTERCHANGE. | HIGHWAY | 7 | PIEDMONT TRIAD RPO | U-5893 | REGION D | REGION D | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2024 | 2024 | NO CHANGE | 2024 | 2024 | NO CHANGE | 2026 | 2026 | NO CHANGE
ROCKINGHAM, GUILFORD | NC 65 / NC 68 | NC 65 IN STOKESDALE (SOUTHERNMOST INTERSECTION) TO US 220 / FUTURE I-73. WIDEN TO MULTILANES. | HIGHWAY | 7 | PIEDMONT TRIAD RPO, GREENSBORO URBAN AREA MPO | R-5823 | DIVISION 7 | DIVISION 7 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2024 | 2024 | NO CHANGE | 2024 | 2024 | NO CHANGE | 2026 | 2026 | NO CHANGE
ROCKINGHAM, GUILFORD | US 29 (FUTURE I-785) | NORTH OF I-785 TO NC 150. UPGRADE CORRIDOR TO INTERSTATE STANDARDS. | HIGHWAY | 7 | GREENSBORO URBAN AREA MPO | R-5889A | REGION D | REGION D | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2028 | 2028 | NO CHANGE | 2028 | 2028 | NO CHANGE | 2031 | 2031 | NO CHANGE
ROCKINGHAM, GUILFORD | US 29 (FUTURE I-785) | NC 150 TO US 158 / NC 14 IN REIDSVILLE. UPGRADE CORRIDOR TO INTERSTATE STANDARDS. | HIGHWAY | 7 | PIEDMONT TRIAD RPO, GREENSBORO URBAN AREA MPO | R-5889B | REGION D | REGION D | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2028 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | PROJECT UNCOMMITTED | 2028 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | PROJECT UNCOMMITTED | 2031 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | PROJECT UNCOMMITTED | YES
ROWAN | SR 2739 (NORTH MAIN STREET) | 12TH STREET TO 22ND STREET IN KANNAPOLIS. CONSTRUCT SIDEWALK. | BIKE/PED | 9 | CABARRUS-ROWAN MPO | EB-5921 | DIVISION 9 | DIVISION 9 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2024 | 2028 | 4 YEAR DELAY | N/A | N/A | NO CHANGE | 2025 | 2031 | 6 YEAR DELAY | YES
ROWAN | THIRD STREET GREENWAY | 3RD STREET TO YADKIN RIVER IN SPENCER. CONSTRUCT ALTERNATE ROUTE, INCLUDING SPUR FROM GRANTS CREEK. | BIKE/PED | 9 | CABARRUS-ROWAN MPO | EB-5861 | DIVISION 9 | DIVISION 9 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | N/A | N/A | NO CHANGE | N/A | N/A | NO CHANGE | 2024 | 2024 | NO CHANGE
ROWAN | NEW ROUTE | AIRPORT PARKWAY, SR 1710 (HARRISON ROAD) NEAR US 70 / US 601 (JAKE ALEXANDER BOULEVARD) TO SR 2539 (PEACH ORCHARD ROAD) AT US 29 IN SALISBURY. CONSTRUCT 2-LANE ROADWAY ON MULTILANE RIGHT OF WAY. | HIGHWAY | 9 | CABARRUS-ROWAN MPO | U-5901 | DIVISION 9 | DIVISION 9 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2027 | 2027 | NO CHANGE | 2027 | 2027 | NO CHANGE | 2030 | 2030 | NO CHANGE
ROWAN | US 29 | NC 152 IN CHINA GROVE. RAMP AND INTERSECTION IMPROVEMENTS. | HIGHWAY | 9 | CABARRUS-ROWAN MPO | U-6130 | REGION D | REGION D | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE
ROWAN | US 52 | PROPOSED MISENHEIMER BYPASS TO PROPOSED ROCKWELL BYPASS. UPGRADE ROADWAY AND ACCESS MANAGEMENT. | HIGHWAY | 9 | CABARRUS-ROWAN MPO | R-5860A | DIVISION 9 | DIVISION 9 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2027 | 2027 | NO CHANGE | 2027 | 2027 | NO CHANGE | 2029 | 2029 | NO CHANGE
ROWAN | US 52 | PROPOSED ROCKWELL BYPASS. CONSTRUCT FACILITY ON NEW LOCATION. | HIGHWAY | 9 | CABARRUS-ROWAN MPO, ROCKY RIVER RPO | R-5860B | DIVISION 9, 10 | NOT FUNDED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE
ROWAN | US 52 | PROPOSED GRANITE QUARRY BYPASS. CONSTRUCT FACILITY ON NEW LOCATION. | HIGHWAY | 9 | CABARRUS-ROWAN MPO | R-5860C | DIVISION 9 | NOT FUNDED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE
ROWAN | NORFOLK SOUTHERN | CITY OF SALISBURY. UPGRADE STATION BUILDING, EXPAND WAITING SPACE AND SURFACE PARKING. | RAIL | 9 | CABARRUS-ROWAN MPO | P-5733 | DIVISION 9 | DIVISION 9 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2025 | 2025 | NO CHANGE | N/A | N/A | NO CHANGE | 2026 | 2026 | NO CHANGE
ROWAN | RAILROAD NORFOLK SOUTHERN | NS MAINLINE IN ROWAN COUNTY. CONSTRUCT TRACK IMPROVEMENTS, SECOND PLATFORM, PEDESTRIAN UNDERPASS, SITEWORK, RETAINING WALL AND SIGNAL EQUIPMENT. | RAIL | 9 | CABARRUS-ROWAN MPO | P-5726 | REGION D | REGION D | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | N/A | N/A | NO CHANGE | N/A | N/A | NO CHANGE | 2024 | 2025 | 1 YEAR DELAY | YES
ROWAN, CABARRUS | SR 2739 (NORTH MAIN STREET / SOUTH MAIN STREET) | SR 2000 (JACKSON PARK ROAD) / NORTH LOOP ROAD IN KANNAPOLIS TO SR 1211 (KIMBALL ROAD) IN CHINA GROVE. UPGRADE ROADWAY INCORPORATING BICYCLE LANES AND SIDEWALKS. | HIGHWAY | 9, 10 | CABARRUS-ROWAN MPO | U-6062 | DIVISION 9, 10 | DIVISION 9, 10 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2028 | 2028 | NO CHANGE | 2028 | 2028 | NO CHANGE | 2031 | 2031 | NO CHANGE
RUTHERFORD | THERMAL BELT RAIL TRAIL IN RUTHERFORDTON. | CONSTRUCT SIDEWALK CONNECTIONS TO THERMAL BELT RAIL TRAIL ALONG VICTORY DRIVE, ALLEN STREET/RAILROAD STREET, PINE STREET, BROADWAY, EAST LIBERTY STREET/BEAVER STREET, MAIN STREET, AND WESTVIEW STREET | BIKE/PED | 13 | FOOTHILLS RPO | EB-5966 | DIVISION 13 | DIVISION 13 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2025 | 2025 | NO CHANGE | N/A | N/A | NO CHANGE | 2026 | 2026 | NO CHANGE
RUTHERFORD | NC 108 (CHARLOTTE STREET) | NC 108 (MAPLE STREET), SOUTH WASHINGTON STREET, MONFREDO STREET INTERSECTION IN RUTHERFORDTON. IMPROVE INTERSECTION. | HIGHWAY | 13 | FOOTHILLS RPO | R-5916 | NOT FUNDED | NOT FUNDED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE
RUTHERFORD | US 221 | NORTH OF US 74 BYPASS TO SOUTH OF US 74 BUSINESS | HIGHWAY | 13 | FOOTHILLS RPO | R-2233BA | DIVISION 13 | DIVISION 13 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2024 | 2024 | NO CHANGE | 2024 | 2024 | NO CHANGE | 2027 | 2027 | NO CHANGE
RUTHERFORD | US 221 | NORTH OF SR 1366 (ROPER LOOP ROAD) TO SR 1325 (NANNEY TOWN ROAD). WIDEN TO MULTI-LANES. | HIGHWAY | 13 | FOOTHILLS RPO | R-2597A | NOT FUNDED | NOT FUNDED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE
RUTHERFORD | US 221 | SR 2201 (THUNDER ROAD) / SR 1005 (COXE ROAD) INTERSECTION. IMPROVE INTERSECTION. | HIGHWAY | 13 | FOOTHILLS RPO | R-5880 | NOT FUNDED | NOT FUNDED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE
RUTHERFORD | US 221A (EAST MAIN STREET) | KENTUCKY STREET/OAKLAND ROAD INTERSECTION IN RUTHERFORDTON. IMPROVE INTERSECTION | HIGHWAY | 13 | FOOTHILLS RPO | R-5918 | NOT FUNDED | NOT FUNDED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE
RUTHERFORD | US 64 (EAST MOUNTAIN STREET) | NORTH WASHINGTON STREET INTERSECTION IN RUTHERFORDTON. IMPROVE INTERSECTION. | HIGHWAY | 13 | FOOTHILLS RPO | R-5917 | NOT FUNDED | NOT FUNDED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE
SAMPSON | CLINTON SAMPSON COUNTY AIRPORT (CTZ) | OVERLAY RUNWAY TO ACCOMMODATE LARGER AIRCRAFT. | AVIATION | 3 | MID-CAROLINA RPO | AV-5823 | DIVISION 3 | DIVISION 3 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | N/A | N/A | NO CHANGE | N/A | N/A | NO CHANGE | 2025 | 2025 | NO CHANGE
SAMPSON | BEAMAN STREET | NORTH BOULEVARD TO SAMPSON REGIONAL MEDICAL CENTER IN CLINTON. CONSTRUCT SIDEWALK. | BIKE/PED | 3 | MID-CAROLINA RPO | EB-6011 | NOT FUNDED | NOT FUNDED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE
SAMPSON | NC 24 (SOUTHWEST BOULEVARD/MLK JR BOULEVARD) | BUTLER ROAD/TRAM ROAD. IMPROVE INTERSECTION. | HIGHWAY | 3 | MID-CAROLINA RPO | U-6126 | NOT FUNDED | NOT FUNDED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE
SAMPSON, DUPLIN | NC 24 | SR 1935 (CECIL ODIE ROAD) IN SAMPSON COUNTY TO I-40 IN DUPLIN COUNTY. | HIGHWAY | 3 | MID-CAROLINA RPO, EASTERN CAROLINA RPO | R-2303F | NOT FUNDED | NOT FUNDED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE
SCOTLAND | LAURINBURG- MAXTON AIRPORT (MEB) | CONSTRUCT 1500 FT RUNWAY EXTENSION. | AVIATION | 8 | LUMBER RIVER RPO | AV-5854 | DIVISION 8 | DIVISION 8 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | N/A | N/A | NO CHANGE | N/A | N/A | NO CHANGE | 2024 | 2024 | NO CHANGE
SCOTLAND | SR 1108 (WEST BOULEVARD) | SR 1105 (TURNPIKE ROAD) TO GLASGOW DRIVE AND EAST OF US 15 / US 401 / US 501 TO SUNSET DRIVE IN LAURINBURG. | BIKE/PED | 8 | LUMBER RIVER RPO | EB-5872A | DIVISION 8 | DIVISION 8 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2024 | 2024 | NO CHANGE | N/A | N/A | NO CHANGE | 2024 | 2024 | NO CHANGE
SCOTLAND | US 401 BUSINESS (SOUTH MAIN STREET | PLAZA ROAD TO CREPE MYRTLE AVENUE IN LAURINBURG. CONSTRUCT SIDEWALKS | BIKE/PED | 8 | LUMBER RIVER RPO | EB-6015B | DIVISION 8 | DIVISION 8 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2024 | 2024 | NO CHANGE | N/A | N/A | NO CHANGE | 2025 | 2025 | NO CHANGE
SCOTLAND | US 15 / US 401 | SOUTH CAROLINA STATE LINE TO SOUTH OF SR 1105 (TURNPIKE ROAD) IN LAURINBURG. WIDEN TO MULTILANES. | HIGHWAY | 8 | LUMBER RIVER RPO | U-5977 | REGION E | REGION E | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2028 | 2028 | NO CHANGE | 2028 | 2028 | NO CHANGE | 2030 | 2030 | NO CHANGE
SCOTLAND, RICHMOND | US 74 / FUTURE I-74 | US 74 BUSINESS EAST OF HAMLET TO US 74 BUSINESS WEST OF LAURINBURG. UPGRADE CORRIDOR TO INTERSTATE STANDARDS. | HIGHWAY | 8 | LUMBER RIVER RPO | I-6055 | REGION E | REGION E | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2027 | 2028 | 1 YEAR DELAY | 2027 | 2028 | 1 YEAR DELAY | 2030 | 2031 | 1 YEAR DELAY
STANLY | STANLY COUNTY AIRPORT (VUJ) | ACQUIRE LAND FOR EXPANSION AND PERFORM ESA TO DETERMINE STATUS OF STRUCTURES ON PROPERTY. CLEAR AND GRUBB LAND REQUIRED FOR EXPANSION AND DEMOLISH HOUSES ON PROPERTY ACQUIRED. | AVIATION | 10 | ROCKY RIVER RPO | AV-5817 | DIVISION 10 | DIVISION 10 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2025 | 2025 | NO CHANGE | N/A | 2025 | PHASE ADDED | 2027 | 2027 | NO CHANGE
STANLY | ALBEMARLE | US 52, WEST MAIN STREET TO SNUGGES STREET. CONSTRUCT SIDEWALK ON EAST SIDE OF ROAD | BIKE/PED | 10 | ROCKY RIVER RPO | EB-5841 | DIVISION 10 | DIVISION 10 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2025 | 2025 | NO CHANGE | N/A | N/A | NO CHANGE | 2026 | 2026 | NO CHANGE
STANLY | NORTH SECOND AVENUE | PARK RIDGE TO SALISBURY AVENUE. CONSTRUCT SIDEWALKS, ADA RAMPS, AND CROSSWALKS. | BIKE/PED | 10 | ROCKY RIVER RPO | EB-5972 | DIVISION 10 | DIVISION 10 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2026 | 2026 | NO CHANGE | N/A | N/A | NO CHANGE | 2027 | 2027 | NO CHANGE
STANLY | SALISBURY AVENUE | US 52 TO NORTH SECOND STREET. CONSTRUCT BIKE LANES. | BIKE/PED | 10 | ROCKY RIVER RPO | EB-5973 | DIVISION 10 | DIVISION 10 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | N/A | N/A | NO CHANGE | N/A | N/A | NO CHANGE | 2025 | 2025 | NO CHANGE
STANLY | US 52 BUSINESS RAMP | NC 24/27 TO SECOND STREET. CONSTRUCT SIDEWALK ALONG US 52 BUSINESS RAMP | BIKE/PED | 10 | ROCKY RIVER RPO | EB-5974 | NOT FUNDED | NOT FUNDED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE
SURRY | MOUNT AIRY | S. SOUTH STREET, WORTH STREET TO ROCKFORD STREET. ROCKFORD STREET, PENN STREET TO US 52. WORTH STREET, SOUTH STREET TO US 52. CONSTRUCT SIDEWALK. | BIKE/PED | 11 | NORTHWEST PIEDMONT RPO | EB-5845 | DIVISION 11 | DIVISION 11 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2023 | 2023 | NO CHANGE | N/A | N/A | NO CHANGE | 2024 | 2024 | NO CHANGE
SURRY | US 21 BUSINESS (NORTH BRIDGE STREET) | NC 268 (CC CAMP ROAD) TO HIGHLAND AVENUE. CONSTRUCT SIDEWALK ON WEST SIDE OF ROADWAY. | BIKE/PED | 11 | NORTHWEST PIEDMONT RPO | EB-5961 | DIVISION 11 | DIVISION 11 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2023 | 2023 | NO CHANGE | N/A | N/A | NO CHANGE | 2024 | 2024 | NO CHANGE
SURRY | NC 103 (EAST PINE STREET) | SR 1742 (QUAKER ROAD) INTERSECTION. IMPROVE INTERSECTION. | HIGHWAY | 11 | NORTHWEST PIEDMONT RPO | R-5895 | NOT FUNDED | NOT FUNDED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE
SURRY | NC 89 (WEST PINE STREET) | SR 1397 (ROUND PEAK CHURCH ROAD) INTERSECTION. IMPROVE INTERSECTION. | HIGHWAY | 11 | NORTHWEST PIEDMONT RPO | R-5901 | NOT FUNDED | REGION F | WILL BE REPRIORITIZED | SCHEDULED FOR DELIVERY | NOT FUNDED | 2024 | PROJECT BECOMES COMMITTED | NOT FUNDED | 2024 | PROJECT BECOMES COMMITTED | NOT FUNDED | 2026 | PROJECT BECOMES COMMITTED |  | YES
SURRY | NC 89 (WEST PINE STREET) | SR 1387 (TOAST ROAD) TO SR 1396 (PINE RIDGE ROAD). MODERNIZE ROADWAY AND IMPROVE INTERSECTION AT SR 1396 (PINE RIDGE ROAD). | HIGHWAY | 11 | NORTHWEST PIEDMONT RPO | R-5905 | DIVISION 11 | DIVISION 11 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2026 | 2025 | 1 YEAR ACCELERATION | 2026 | 2025 | 1 YEAR ACCELERATION | 2028 | 2027 | 1 YEAR ACCELERATION
SURRY | US 601 | I-74 TO SR 1104 (CODY TRAIL). WIDEN TO 4-LANES. | HIGHWAY | 11 | NORTHWEST PIEDMONT RPO | R-5836 | DIVISION 11 | DIVISION 11 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2024 | 2024 | NO CHANGE | 2024 | 2024 | NO CHANGE | 2026 | 2026 | NO CHANGE
SWAIN | US 19 | SR 1152 (HUGHES BRANCH ROAD) IN BRYSON CITY TO SR 1195 (US 19A). MODERNIZE ROADWAY. | HIGHWAY | 14 | SOUTHWESTERN RPO | R-4751 | NOT FUNDED | NOT FUNDED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE
TRANSYLVANIA | BREVARD | CONSTRUCT BICYCLE AND PEDESTRIAN BRIDGE FROM CITY OF BREVARD EXISTING SHARED USE PATH ACROSS DAVIDSON RIVER. | BIKE/PED | 14 | LAND-OF-SKY RPO | EB-5858 | DIVISION 14 | DIVISION 14 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | UNDERWAY | UNDERWAY | NO CHANGE | UNDERWAY | UNDERWAY | NO CHANGE | 2024 | 2024 | NO CHANGE
TRANSYLVANIA | SR 1540 (WILSON ROAD) | SR 1504 (OLD US 64) TO US 276. UPGRADE ROADWAY. | HIGHWAY | 14 | LAND-OF-SKY RPO | R-5763 | DIVISION 14 | DIVISION 14 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2022 | 2022 | NO CHANGE | 2022 | 2022 | NO CHANGE | 2024 | 2025 | 1 YEAR DELAY | YES
TRANSYLVANIA | US 178 | SR 1156 (MAIN STREET) IN ROSMAN TO SR 1133 (MIDDLEFORK ROAD) MODERNIZE ROADWAY. | HIGHWAY | 14 | LAND-OF-SKY RPO | R-5919 | DIVISION 14 | DIVISION 14 | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE
TRANSYLVANIA | US 64 | US 276, NC 280 INTERSECTION. CONSTRUCT INTERSECTION IMPROVEMENTS. | HIGHWAY | 14 | LAND-OF-SKY RPO | R-5799 | REGION G | REGION G | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2022 | 2022 | NO CHANGE | 2022 | 2022 | NO CHANGE | 2024 | 2024 | NO CHANGE
TRANSYLVANIA | US 64 (SOUTH BROAD STREET) | US 64 BUSINESS (SOUTH CALDWELL STREET), SR 1116 (NORTH COUNTRY CLUB ROAD) INTERSECTION. IMPROVE INTERSECTION ALIGNMENT. | HIGHWAY | 14 | LAND-OF-SKY RPO | R-5882 | NOT FUNDED | NOT FUNDED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE
TRANSYLVANIA | US 64, US 276 | FORTUNE COVE ROAD TO US 64 BUSINESS (NORTH CALDWELL STREET). CONSTRUCT MEDIAN AND ACCESS CONTROL MEASURES. | HIGHWAY | 14 | LAND-OF-SKY RPO | R-5800 | REGION G | REGION G | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2023 | 2023 | NO CHANGE | 2023 | 2023 | NO CHANGE | 2025 | 2025 | NO CHANGE
TYRRELL | US 64 | COLUMBIA TO ALLIGATOR RIVER BRIDGE. MODERNIZE ROADWAY. | HIGHWAY | 1 | ALBEMARLE RPO | R-5940 | DIVISION 1 | DIVISION 1 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2028 | 2028 | NO CHANGE | 2028 | 2028 | NO CHANGE | 2030 | 2032 | 2 YEAR DELAY
UNION | CHARLOTTE-MONROE EXECUTIVE AIRPORT (EQY) | RELOCATE AND WIDEN THE EXISTING PARALLEL TAXIWAY SECTION BETWEEN THE EXISTING RAMP AND THE RUNWAY 5 TAXIWAY EXTENSION. | AVIATION | 10 | CHARLOTTE REGIONAL TPO | AV-5814 | DIVISION 10 | DIVISION 10 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | N/A | N/A | NO CHANGE | N/A | N/A | NO CHANGE | 2028 | 2028 | NO CHANGE
UNION | NC 16 (PROVIDENCE ROAD SOUTH) | SR 1316 (REA ROAD EXTENSION) TO SR 1307 (BONDS GROVE CHURCH RD). WIDEN TO MULTI-LANES. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-5769A | REGION E | REGION E | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2024 | 2024 | NO CHANGE | 2024 | 2024 | NO CHANGE | 2027 | 2027 | NO CHANGE
UNION | NC 16 (PROVIDENCE ROAD SOUTH) | SR 1307 (BONDS GROVE CHURCH RD) TO SR 3530 (WAXHAW PARKWAY) IN WAXHAW. WIDEN TO MULTI-LANES. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-5769B | REGION E | REGION E | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2024 | 2024 | NO CHANGE | 2024 | 2024 | NO CHANGE | 2027 | 2027 | NO CHANGE
UNION | NC 84 | NC 16 TO SR 1008 (WAXHAW-INDIAN TRAIL ROAD) IN WESLEY CHAPEL. CONSTRUCT FOUR LANE ROADWAY, PART ON NEW LOCATION. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-3467 | REGION E | REGION E | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2024 | 2024 | NO CHANGE | 2024 | 2024 | NO CHANGE | 2027 | 2027 | NO CHANGE
UNION | SR 1004 (LAWYERS ROAD) | I-485 TO SR 1524 (STEVENS MILL ROAD). WIDEN ROADWAY TO FOUR LANES. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-6170 | NOT FUNDED | DIVISION 10 | WILL BE REPRIORITIZED | SCHEDULED FOR DELIVERY | NOT FUNDED | 2027 | PROJECT BECOMES COMMITTED | NOT FUNDED | 2027 | PROJECT BECOMES COMMITTED | NOT FUNDED | 2029 | PROJECT BECOMES COMMITTED |  | YES
UNION | SR 1009 (CHARLOTTE AVENUE) | SEYMOUR STREET TO NC 200 (DICKERSON BOULEVARD). WIDEN TO FOUR-LANES DIVIDED. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-6031 | DIVISION 10 | DIVISION 10 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2028 | 2028 | NO CHANGE | 2028 | 2028 | NO CHANGE | 2030 | 2030 | NO CHANGE
UNION | SR 1009 (JOHN STREET-OLD MONROE ROAD) | WEST OF MORNINGSIDE MEADOW LANE TO EAST OF SR 1377 (WESLEY CHAPEL-STOUTS ROAD) | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-4714B | DIVISION 10 | DIVISION 10 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2021 | 2021 | NO CHANGE | 2021 | 2021 | NO CHANGE | 2024 | 2025 | 1 YEAR DELAY | YES
UNION | SR 1009 (OLD MONROE ROAD) | SR 1377 (WESLEY CHAPEL-STOUTS ROAD) TO SR 1349 (AIRPORT ROAD). | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-6169 | NOT FUNDED | NOT FUNDED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE
UNION | US 601 | EXISTING US 74 TO THE MONROE BYPASS. WIDEN TO MULTI-LANES. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-4024 | REGION E | REGION E | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2028 | 2028 | NO CHANGE | 2028 | 2028 | NO CHANGE | 2030 | 2030 | NO CHANGE
UNION | US 74 | US 601 INTERCHANGE. CONSTRUCT IMPROVEMENTS. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-5723 | STATEWIDE MOBILITY | STATEWIDE MOBILITY | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | UNDERWAY | UNDERWAY | NO CHANGE | UNDERWAY | UNDERWAY | NO CHANGE | 2025 | 2026 | 1 YEAR DELAY
UNION | US 74 | NC 200 (DICKERSON BOULEVARD) TO SR 1007 (ROCKY RIVER ROAD). WIDEN EXISTING ROADWAY. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-5764 | REGION E | REGION E | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2025 | 2025 | NO CHANGE | 2025 | 2025 | NO CHANGE | 2028 | 2028 | NO CHANGE
UNION | US 74 | INTERSECTION OF US 74 AND SECREST SHORTCUT ROAD. CONSTRUCT IMPROVEMENTS. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-5931 | STATEWIDE MOBILITY | STATEWIDE MOBILITY | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2025 | 2025 | NO CHANGE | 2025 | 2025 | NO CHANGE | 2028 | 2028 | NO CHANGE
UNION | US 74 (ROOSEVELT BLVD) | REALIGN JAMES HAMILTON ROAD TO INTERSECT WITH SR 1514 (ROCKY RIVER ROAD) AT MYERS ROAD. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-5703B | STATEWIDE MOBILITY | STATEWIDE MOBILITY | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | UNDERWAY | UNDERWAY | NO CHANGE | UNDERWAY | UNDERWAY | NO CHANGE | 2025 | 2026 | 1 YEAR DELAY
UNION | CSX SF LINE | SR 1377 (WESLEY CHAPEL STOUTS ROAD). CONSTRUCT GRADE SEPERATION. | RAIL | 10 | CHARLOTTE REGIONAL TPO | P-5744 | STATEWIDE MOBILITY | STATEWIDE MOBILITY | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2025 | 2025 | NO CHANGE | 2025 | 2025 | NO CHANGE | 2027 | 2027 | NO CHANGE
UNION, MECKLENBURG | IDLEWILD ROAD | SR 3175 (STALLINGS ROAD) TO SR 1524 (STEVENS MILL ROAD). WIDEN EXISTING ROADWAY. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-4913A | DIVISION 10 | DIVISION 10 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2026 | 2026 | NO CHANGE | 2026 | 2026 | NO CHANGE | 2028 | 2028 | NO CHANGE
UNION, MECKLENBURG | IDLEWILD ROAD | SR 3175 (STALLINGS ROAD) TO SR 1524 (STEVENS MILL ROAD). WIDEN EXISTING ROADWAY. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-4913B | DIVISION 10 | NOT FUNDED | SCHEDULED FOR DELIVERY | WILL BE REPRIORITIZED | 2026 | NOT FUNDED | PROJECT NO LONGER FUNDED | 2026 | NOT FUNDED | PROJECT NO LONGER FUNDED | 2028 | NOT FUNDED | PROJECT NO LONGER FUNDED |  | YES
UNION, MECKLENBURG | SR 1009 (JOHN STREET-OLD MONROE ROAD) | EAST OF I-485 TO WEST OF MORNINGSIDE MEADOW LANE | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-4714AC | DIVISION 10 | DIVISION 10 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2019 | 2019 | NO CHANGE | 2019 | 2019 | NO CHANGE | 2024 | 2025 | 1 YEAR DELAY | YES
VANCE | SR 1162 (DABNEY DRIVE) | COBLE BOULEVARD TO US 158 BUSINESS IN HENDERSON. CORRIDOR UPGRADE. | HIGHWAY | 5 | KERR-TAR RPO | U-5890 | DIVISION 5 | DIVISION 5 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2026 | 2026 | NO CHANGE | 2026 | 2026 | NO CHANGE | 2028 | 2028 | NO CHANGE
WAKE | SR 1012 (WESTERN BOULEVARD) | CONSTRUCT BICYCLE / PEDESTRIAN TUNNEL IMMEDIATELY WEST OF SR 1321 (AVENT FERRY ROAD) IN RALEIGH. | BIKE/PED | 5 | CAPITAL AREA MPO | EB-5718 | DIVISION 5 | DIVISION 5 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | N/A | N/A | NO CHANGE | N/A | N/A | NO CHANGE | 2025 | 2028 | 3 YEAR DELAY | YES
WAKE | SR 1637 (CHURCH STREET) | SR 3014 (MORRISVILLE-CARPENTER ROAD) TO DURHAM COUNTY LINE IN MORRISVILLE. CONSTRUCT SIDEWALKS TO FILL IN GAPS. | BIKE/PED | 5 | CAPITAL AREA MPO | EB-5838 | DIVISION 5 | DIVISION 5 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2023 | 2023 | NO CHANGE | N/A | N/A | NO CHANGE | 2024 | 2024 | NO CHANGE
WAKE | I-40 | I-440 / US 1 / US 64 INTERCHANGE IN RALEIGH. RECONSTRUCT INTERCHANGE. | HIGHWAY | 5 | CAPITAL AREA MPO | I-5703 | STATEWIDE MOBILITY | STATEWIDE MOBILITY | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2026 | 2027 | 1 YEAR DELAY | 2026 | 2027 | 1 YEAR DELAY | 2026 | 2027 | 1 YEAR DELAY
WAKE | I-40 | SR 1002 (AVIATION PARKWAY) TO SR 1652 (HARRISON AVENUE) IN CARY. CONSTRUCT AUXILIARY LANES IN BOTH DIRECTIONS. | HIGHWAY | 5 | CAPITAL AREA MPO | I-5966 | STATEWIDE MOBILITY | STATEWIDE MOBILITY | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2027 | 2028 | 1 YEAR DELAY | 2027 | 2028 | 1 YEAR DELAY | 2030 | 2031 | 1 YEAR DELAY
WAKE | I-40 / US 64 | I-440 / US 1 / US 64 TO SR 1370 (LAKE WHEELER ROAD) IN RALEIGH. ADD LANES. | HIGHWAY | 5 | CAPITAL AREA MPO | I-5701 | STATEWIDE MOBILITY | STATEWIDE MOBILITY | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2026 | 2027 | 1 YEAR DELAY | 2026 | 2027 | 1 YEAR DELAY | 2026 | 2027 | 1 YEAR DELAY
WAKE | I-440 / US 1 | SR 2000 (WAKE FOREST ROAD) IN RALEIGH. INTERCHANGE IMPROVEMENTS. | HIGHWAY | 5 | CAPITAL AREA MPO | I-5708 | STATEWIDE MOBILITY | STATEWIDE MOBILITY | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | UNDERWAY | UNDERWAY | NO CHANGE | UNDERWAY | UNDERWAY | NO CHANGE | 2025 | 2026 | 1 YEAR DELAY
WAKE | I-440 / US 1 | US 70 (GLENWOOD AVENUE) IN RALEIGH. CONSTRUCT INTERCHANGE IMPROVEMENTS, REVISE US 70 INTERSECTION WITH SR 1670 (BLUE RIDGE ROAD) / SR 1820 (LEAD MINE ROAD), AND REPLACE BRIDGE 910494 ON SR 1670. | HIGHWAY | 5 | CAPITAL AREA MPO | I-5870 | STATEWIDE MOBILITY | STATEWIDE MOBILITY | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE
WAKE | I-440 / US 1 | US 401 (CAPITAL BOULEVARD) IN RALEIGH. INTERCHANGE IMPROVEMENTS. | HIGHWAY | 5 | CAPITAL AREA MPO | I-5970 | STATEWIDE MOBILITY | STATEWIDE MOBILITY | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE
WAKE | I-540 | US 70 TO SR 1829 (LEESVILLE ROAD) IN RALEIGH. CONSTRUCT EASTBOUND AUXILIARY LANE. | HIGHWAY | 5 | CAPITAL AREA MPO | I-5968 | STATEWIDE MOBILITY | STATEWIDE MOBILITY | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2028 | 2028 | NO CHANGE | 2028 | 2028 | NO CHANGE | 2030 | 2030 | NO CHANGE
WAKE | I-87 / US 64 / US 264 | US 64 BUSINESS (WENDELL BOULEVARD) TO US 264. WIDEN TO 6 LANES. | HIGHWAY | 5 | CAPITAL AREA MPO | I-6005 | STATEWIDE MOBILITY | STATEWIDE MOBILITY | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE
WAKE | I-87 / US 64 / US 264 | SR 2233 (SMITHFIELD ROAD). CONVERT INTERCHANGE TO DIVERGING DIAMOND. | HIGHWAY | 5 | CAPITAL AREA MPO | I-6007 | STATEWIDE MOBILITY | STATEWIDE MOBILITY | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE
WAKE | NC 50 (CREEDMOOR ROAD) | I-540 TO NORTH OF NC 98. WIDEN TO MULTILANE DIVIDED ROADWAY. | HIGHWAY | 5 | CAPITAL AREA MPO | U-5891 | REGION C | REGION C | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE
WAKE | NC 55 (WILLIAMS STREET) | US 1 TO NORTH OF SR 1160 (OLIVE CHAPEL ROAD). CONVERT EXISTING MULTILANES TO MEDIAN DIVIDED SECTION AND WIDEN REMAINING 2-LANE SECTIONS TO MULTILANES. | HIGHWAY | 5 | CAPITAL AREA MPO | U-2901B | REGION C | REGION C | SCHEDULED FOR DELIVERY | WILL BE REPRIORITIZED | 2028 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | PROJECT UNCOMMITTED | 2028 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | PROJECT UNCOMMITTED | 2031 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | PROJECT UNCOMMITTED
WAKE | NEW ROUTE | SR 1613 (MCCRIMMON PARKWAY) TO NC 540 IN MORRISVILLE. CONSTRUCT MULTILANE FACILITY ON NEW LOCATION. | HIGHWAY | 5 | CAPITAL AREA MPO | U-5966 | REGION C | REGION C | SCHEDULED FOR DELIVERY | WILL BE REPRIORITIZED | 2028 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | PROJECT UNCOMMITTED | 2028 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | PROJECT UNCOMMITTED | 2030 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | PROJECT UNCOMMITTED |  | YES
WAKE | SR 1002 (AVIATION PARKWAY) | NC 54 TO I-40 IN MORRISVILLE. WIDEN TO MULTILANES WITH INTERCHANGE MODIFICATIONS AT I-40. | HIGHWAY | 5 | CAPITAL AREA MPO | U-5811 | DIVISION 5 | DIVISION 5 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2026 | 2026 | NO CHANGE | 2026 | 2026 | NO CHANGE | 2028 | 2028 | NO CHANGE
WAKE | SR 1010 (TEN-TEN ROAD) | APEX PEAKWAY IN APEX TO SR 1300 (KILDARE FARM ROAD) IN CARY. WIDEN TO MULTILANES. | HIGHWAY | 5 | CAPITAL AREA MPO | U-5825 | DIVISION 5 | DIVISION 5 | SCHEDULED FOR DELIVERY | WILL BE REPRIORITIZED | 2028 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | PROJECT UNCOMMITTED | 2028 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | PROJECT UNCOMMITTED | 2031 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | PROJECT UNCOMMITTED
WAKE | SR 1115 (AVENT FERRY ROAD) | SR 1116 (CASS HOLT ROAD) TO NC 55 BYPASS IN HOLLY SPRINGS. WIDEN TO MULTILANES, WITH INTERSECTION IMPROVEMENTS AT SR 1116 (CASS HOLT ROAD), SR 1101 (PINEY GROVE-WILBON ROAD) AND NC 55 BYPASS. | HIGHWAY | 5 | CAPITAL AREA MPO | U-5889 | DIVISION 5 | DIVISION 5 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2026 | 2026 | NO CHANGE | 2026 | 2026 | NO CHANGE | 2028 | 2028 | NO CHANGE
WAKE | SR 1152 (HOLLY SPRINGS ROAD) | SR 1010 (TEN-TEN ROAD) TO SR 3977 (CARY PARKWAY). IMPROVE INTERSECTIONS AT SR 1010, SR 1379 (PENNY ROAD), AND SR 3977. | HIGHWAY | 5 | CAPITAL AREA MPO | U-6217 | DIVISION 5 | DIVISION 5 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2028 | 2028 | NO CHANGE | 2028 | 2028 | NO CHANGE | 2031 | 2031 | NO CHANGE
WAKE | SR 1664 (DURALEIGH ROAD) | SR 3009 (EDWARDS MILL ROAD) IN RALEIGH. | HIGHWAY | 5 | CAPITAL AREA MPO | U-6193 | DIVISION 5 | NOT FUNDED | SCHEDULED FOR DELIVERY | WILL BE REPRIORITIZED | 2027 | NOT FUNDED | PROJECT NO LONGER FUNDED | 2027 | NOT FUNDED | PROJECT NO LONGER FUNDED | 2029 | NOT FUNDED | PROJECT NO LONGER FUNDED |  | YES
WAKE | SR 1728 (WADE AVENUE) | I-40 TO I-440 IN RALEIGH. ADD LANES. | HIGHWAY | 5 | CAPITAL AREA MPO | U-5936 | STATEWIDE MOBILITY | STATEWIDE MOBILITY | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE
WAKE | US 1 | I-540 TO NORTH OF SR 2006 (DURANT ROAD) IN RALEIGH. | HIGHWAY | 5 | CAPITAL AREA MPO | U-5307A | STATEWIDE MOBILITY | STATEWIDE MOBILITY | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2025 | 2026 | 1 YEAR DELAY | 2025 | 2026 | 1 YEAR DELAY | 2025 | 2026 | 1 YEAR DELAY
WAKE | US 1 | NORTH OF SR 2006 (DURANT ROAD) IN RALEIGH TO NORTH OF SR 2045 (BURLINGTON MILLS ROAD) IN WAKE FOREST. | HIGHWAY | 5 | CAPITAL AREA MPO | U-5307B | REGION C | REGION C | SCHEDULED FOR DELIVERY | WILL BE REPRIORITIZED | 2027 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | PROJECT UNCOMMITTED | 2027 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | PROJECT UNCOMMITTED | 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | PROJECT UNCOMMITTED
WAKE | US 1 | NORTH OF SR 2045 (BURLINGTON MILLS ROAD) TO SOUTH OF NC 98 BUSINESS IN WAKE FOREST. | HIGHWAY | 5 | CAPITAL AREA MPO | U-5307C | REGION C | REGION C | SCHEDULED FOR DELIVERY | WILL BE REPRIORITIZED | 2027 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | PROJECT UNCOMMITTED | 2027 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | PROJECT UNCOMMITTED | 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | PROJECT UNCOMMITTED
WAKE | US 1 | SOUTH OF NC 98 BUSINESS TO SR1909 (PURNELL ROAD) / SR 1931 (HARRIS ROAD) IN WAKE FOREST. | HIGHWAY | 5 | CAPITAL AREA MPO | U-5307D | REGION C | REGION C | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE
WAKE | US 1 | NC 55 IN APEX TO US 64 IN CARY. ADD LANES. | HIGHWAY | 5 | CAPITAL AREA MPO | U-6066 | STATEWIDE MOBILITY | STATEWIDE MOBILITY | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE
WAKE | US 401 | SR 1467 / SR 2839 (ALLEN STREET) TO SR 1010 (TEN-TEN ROAD). ADD LANES. | HIGHWAY | 5 | CAPITAL AREA MPO | U-5746 | REGION C | REGION C | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | UNDERWAY | UNDERWAY | NO CHANGE | UNDERWAY | UNDERWAY | NO CHANGE | 2024 | 2024 | NO CHANGE
WAKE | US 401 | NC 55 / NC 42 IN FUQUAY-VARINA. IMPROVE US 401 INTERSECTION WITH NC 55 / NC 42. PROJECT WILL INCLUDE IMPROVEMENTS TO NC 55 INTERSECTION WITH NC 42, AND CONSTRUCTION OF CONNECTOR FROM NC 55 TO SR 5056 (JUDD PARKWAY). | HIGHWAY | 5 | CAPITAL AREA MPO | U-5751 | REGION C | REGION C | WILL BE REPRIORITIZED | SCHEDULED FOR DELIVERY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2028 | PROJECT BECOMES COMMITTED | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2028 | PROJECT BECOMES COMMITTED | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2031 | PROJECT BECOMES COMMITTED |  | YES
WAKE | US 401 | SR 1010 (TEN-TEN ROAD). CONVERT EXISTING SIGNALIZED INTERSECTION TO SQUARE-LOOP INTERCHANGE. | HIGHWAY | 5 | CAPITAL AREA MPO | U-6112 | REGION C | REGION C | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE
WAKE | US 401 | SR 1375 (SIMPKINS ROAD) TO SR 2538 (MECHANICAL BOULEVARD) IN GARNER. WIDEN TO 6 LANES AND CONVERT TO SUPERSTREET. | HIGHWAY | 5 | CAPITAL AREA MPO | U-6116 | NOT FUNDED | NOT FUNDED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE
WAKE | US 64 | WEST OF SR 1308 (LAURA DUNCAN ROAD) TO US 1 IN APEX AND CARY. CORRIDOR UPGRADE AND IMPROVEMENTS. | HIGHWAY | 5 | CAPITAL AREA MPO | U-5301 | STATEWIDE MOBILITY | STATEWIDE MOBILITY | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2026 | 2027 | 1 YEAR DELAY | 2026 | 2027 | 1 YEAR DELAY | 2029 | 2030 | 1 YEAR DELAY
WAKE | US 70 | I-540 TO HILLBURN DRIVE IN RALEIGH. ADD LANES AND CONVERT TO SUPERSTREET. | HIGHWAY | 5 | CAPITAL AREA MPO | U-2823 | STATEWIDE MOBILITY | STATEWIDE MOBILITY | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE
WAKE | US 70 / NC 50 | SR 2026 (HAMMOND ROAD) / SR 2812 (TIMBER DRIVE) IN GARNER. CONVERT AT-GRADE INTERSECTION TO INTERCHANGE. | HIGHWAY | 5 | CAPITAL AREA MPO | U-5744 | REGION C | REGION C | SCHEDULED FOR DELIVERY | WILL BE REPRIORITIZED | 2028 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | PROJECT UNCOMMITTED | 2028 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | PROJECT UNCOMMITTED | 2030 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | PROJECT UNCOMMITTED
WAKE | VARIOUS | TOWN OF MORRISVILLE. CONSTRUCT TOWNWIDE ITS / SIGNAL SYSTEM. | HIGHWAY | 5 | CAPITAL AREA MPO | U-5967 | REGION C | REGION C | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | N/A | N/A | NO CHANGE | 2025 | 2028 | 3 YEAR DELAY | 2026 | 2029 | 3 YEAR DELAY
WAKE | VARIOUS | APEX TOWNWIDE SIGNAL SYSTEM. UPGRADE EXISTING INFRASTRUCTURE AND INSTALL NEW FIBER, CONTROLLERS, SIGNALS, AND OTHER EQUIPMENT AS NECESSARY. | HIGHWAY | 5 | CAPITAL AREA MPO | U-6117 | NOT FUNDED | DIVISION 5 | WILL BE REPRIORITIZED | SCHEDULED FOR DELIVERY | NOT FUNDED | 2027 | PROJECT BECOMES COMMITTED | NOT FUNDED | 2027 | PROJECT BECOMES COMMITTED | NOT FUNDED | 2028 | PROJECT BECOMES COMMITTED |  | YES
WAKE | VARIOUS | RALEIGH CITYWIDE SIGNAL SYSTEM. UPGRADE SOFTWARE FOR EXISTING ITS SYSTEM. | HIGHWAY | 5 | CAPITAL AREA MPO | U-6119 | REGION C | DIVISION 5 | WILL BE REPRIORITIZED | SCHEDULED FOR DELIVERY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2027 | PROJECT BECOMES COMMITTED | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2027 | PROJECT BECOMES COMMITTED | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2028 | PROJECT BECOMES COMMITTED |  | YES
WAKE | VARIOUS | GARNER CITYWIDE SIGNAL SYSTEM | HIGHWAY | 5 | CAPITAL AREA MPO | U-6194 | DIVISION 5 | DIVISION 5 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2027 | 2027 | NO CHANGE | 2027 | 2027 | NO CHANGE | 2028 | 2028 | NO CHANGE
WAKE | VARIOUS | TRIANGLE TOWN CENTER. CONSTRUCT TRANSIT CENTER AND PARK-AND-RIDE FACILITY. | PUBLIC TRANSIT | 5 | CAPITAL AREA MPO | TD-5307 | DIVISION 5 | DIVISION 5 | WILL BE REPRIORITIZED | SCHEDULED FOR DELIVERY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2027 | PROJECT BECOMES COMMITTED | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2027 | PROJECT BECOMES COMMITTED | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2028 | PROJECT BECOMES COMMITTED |  | YES
WAKE | VARIOUS | BUS RAPID TRANSIT SERVICE, MORRISVILLE TO CARY. CONSTRUCT INFRASTRUCTURE, PURCHASE VEHICLES, AND ESTABLISH SERVICE. | PUBLIC TRANSIT | 5 | CAPITAL AREA MPO | TO-6166A | REGION C | REGION C | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE
WAKE | CSX | CROSSING 643351A AT SR 1415 (NORTHEAST MAYNARD ROAD) IN CARY. CONSTRUCT GRADE SEPARATION. | RAIL | 5 | CAPITAL AREA MPO | P-5718 | REGION C | REGION C | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE
WAKE | CSX S LINE | CONSTRUCT GRADE SEPARATION AT SR 2052 (ROGERS ROAD EXTENSION) CROSSING (633905Y) IN WAKE FOREST. | RAIL | 5 | CAPITAL AREA MPO | P-5707 | REGION C | REGION C | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | N/A | N/A | NO CHANGE | N/A | N/A | NO CHANGE | 2024 | 2024 | NO CHANGE
WAKE | CSX S LINE | SR 2108 (MILLBROOK ROAD) IN RALEIGH. CONSTRUCT GRADE SEPARATION AND CLOSE CROSSING 630605A. | RAIL | 5 | CAPITAL AREA MPO | P-5737 | STATEWIDE MOBILITY | STATEWIDE MOBILITY | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | UNDERWAY | UNDERWAY | NO CHANGE | 2022 | 2022 | NO CHANGE | 2024 | 2025 | 1 YEAR DELAY | YES
WAKE | CSX S LINE | SR 1415 (WEST MAYNARD ROAD) IN CARY. CONSTRUCT GRADE SEPARATION AND CLOSE CROSSING 643400U. | RAIL | 5 | CAPITAL AREA MPO | P-5739 | NOT FUNDED | NOT FUNDED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE
WAKE | NORFOLK SOUTHERN H LINE | CONSTRUCT GRADE SEPARATION AT HARRISON AVENUE CROSSING (734755X) IN CARY. | RAIL | 5 | CAPITAL AREA MPO | P-5708 | REGION C | REGION C | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE
WAKE | NORTH CAROLINA RAILROAD / NORFOLK SOUTHERN H LINE | SR 2713 (VANDORA SPRINGS ROAD) IN GARNER. CONSTRUCT GRADE SEPARATION AND CLOSE CROSSING 735324J. | RAIL | 5 | CAPITAL AREA MPO | P-5738 | NOT FUNDED | NOT FUNDED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE
WAKE | NORTH CAROLINA RAILROAD / NORFOLK SOUTHERN H LINE | SR 1655 (TRINITY ROAD) IN CARY. CONSTRUCT GRADE SEPARATION AND CLOSE CROSSING 630657S. | RAIL | 5 | CAPITAL AREA MPO | P-5734 | STATEWIDE MOBILITY | STATEWIDE MOBILITY | WILL BE REPRIORITIZED | SCHEDULED FOR DELIVERY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2027 | PROJECT BECOMES COMMITTED | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2027 | PROJECT BECOMES COMMITTED | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2029 | PROJECT BECOMES COMMITTED |  | YES
WAKE | NORTH CAROLINA RAILROAD; NORFOLK SOUTHERN H LINE; | BERYL ROAD CROSSING IN RALEIGH. EXTEND BERYL ROAD TO ROYAL AVENUE, AND CLOSE CROSSING 630647L. | RAIL | 5 | CAPITAL AREA MPO | P-5736 | NOT FUNDED | STATEWIDE MOBILITY | WILL BE REPRIORITIZED | SCHEDULED FOR DELIVERY | NOT FUNDED | 2028 | PROJECT BECOMES COMMITTED | NOT FUNDED | 2028 | PROJECT BECOMES COMMITTED | NOT FUNDED | 2029 | PROJECT BECOMES COMMITTED |  | YES
WAKE, DURHAM | US 70 (GLENWOOD AVENUE) | WEST OF SR 3067 (T.W. ALEXANDER DRIVE) TO I-540 IN RALEIGH. UPGRADE ROADWAY TO IMPROVE CAPACITY, SAFETY AND TRAFFIC OPERATIONS INCLUDING INTERCHANGES AT VARIOUS LOCATIONS. | HIGHWAY | 5 | CAPITAL AREA MPO, DURHAM-CHAPEL HILL-CARRBORO MPO | U-5518 | STATEWIDE MOBILITY | STATEWIDE MOBILITY | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2025 | 2026 | 1 YEAR DELAY | 2025 | 2026 | 1 YEAR DELAY | 2025 | 2026 | 1 YEAR DELAY
WAKE, JOHNSTON | I-40; I-87; I-440; US 1 / US 64 | I-40 FROM SR 1728 (WADE AVENUE) TO NC 42, I-440, I-87 FROM I-40 TO I-540, US 1 FROM NC 540 TO I-40. CONVERT FACILITIES TO MANAGED FREEWAYS, TO INCLUDE RAMP METERING. | HIGHWAY | 4, 5 | CAPITAL AREA MPO | U-6101 | NOT FUNDED | NOT FUNDED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE
WAKE, JOHNSTON | NEW ROUTE (FUTURE NC 540) | EASTERN WAKE FREEWAY / TRIANGLE EXPRESSWAY SOUTHEAST EXTENSION (RALEIGH OUTER LOOP), I-40 TO US 64 / US 264 BYPASS. FREEWAY ON NEW LOCATION. | HIGHWAY | 4, 5 | CAPITAL AREA MPO | R-2829 | STATEWIDE MOBILITY | STATEWIDE MOBILITY | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2025 | 2023 | 2 YEAR ACCELERATION | 2025 | 2023 | 2 YEAR ACCELERATION | 2026 | 2023 | 3 YEAR ACCELERATION | YES
WASHINGTON | SR 1106 (MORATTOCK ROAD) | SR 1100 (LONG RIDGE ROAD) TO NC 32 SOUTH. MODERNIZE ROADWAY. | HIGHWAY | 1 | ALBEMARLE RPO | R-5937 | DIVISION 1 | DIVISION 1 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2028 | 2028 | NO CHANGE | 2028 | 2028 | NO CHANGE | 2030 | 2032 | 2 YEAR DELAY
WASHINGTON | SR 1126 (ROPER NEWLAND ROAD) | SR 1128 (A CANAL ROAD) TO SR 1183 (SHORE DRIVE). MODERNIZE ROADWAY. | HIGHWAY | 1 | ALBEMARLE RPO | R-5936 | DIVISION 1 | DIVISION 1 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2026 | 2026 | NO CHANGE | 2026 | 2026 | NO CHANGE | 2028 | 2028 | NO CHANGE
WATAUGA | US 421 (KING STREET) MULTI-USE PATH | GROVE STREET TO BROOKSHIRE ROAD. CONSTRUCT MULTI-USE PATH. | BIKE/PED | 11 | HIGH COUNTRY RPO | EB-5983 | DIVISION 11 | DIVISION 11 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2024 | 2024 | NO CHANGE | N/A | N/A | NO CHANGE | 2025 | 2025 | NO CHANGE
WATAUGA | NC 105 | SR 1136 (CLARKS CREEK ROAD) TO SR 1107 (NC 105 BYPASS) IN BOONE. | HIGHWAY | 11 | HIGH COUNTRY RPO | R-2566B | REGION F | REGION F | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2022 | 2022 | NO CHANGE | 2022 | 2022 | NO CHANGE | 2025 | 2025 | NO CHANGE
WATAUGA | SR 1514 (BAMBOO ROAD); SR 1523 (WILSON RIDGE) | US 421/US 221 TO SR 1522 (DEERFIELD ROAD). MODERNIZE ROADWAY. | HIGHWAY | 11 | HIGH COUNTRY RPO | U-5810 | DIVISION 11 | DIVISION 11 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2022 | 2022 | NO CHANGE | 2022 | 2022 | NO CHANGE | 2024 | 2024 | NO CHANGE
WATAUGA | SR 1522 (DEERFIELD ROAD) | STATE FARM ROAD TO SR 1523 (WILSON RIDGE ROAD). UPGRADE ROADWAY. | HIGHWAY | 11 | HIGH COUNTRY RPO | R-5830 | DIVISION 11 | DIVISION 11 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2024 | 2024 | NO CHANGE | 2024 | 2024 | NO CHANGE | 2025 | 2025 | NO CHANGE
WATAUGA | US 321 | DEERFIELD ROAD AND MEADOWVIEW ROAD. REALIGN OFFSET INTERSECTION. | HIGHWAY | 11 | HIGH COUNTRY RPO | R-5874 | NOT FUNDED | NOT FUNDED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE
WATAUGA | US 421 | SR 1180 (POPLAR GROVE CONNECTOR). CONSTRUCT ROUNDABOUT. | HIGHWAY | 11 | HIGH COUNTRY RPO | R-5872 | STATEWIDE MOBILITY | STATEWIDE MOBILITY | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE
WATAUGA | US 421 | TENNESSEE LINE TO US 321-US 421 JUNCTION NEAR VILAS. WIDEN TO MULTI-LANES. | HIGHWAY | 11 | HIGH COUNTRY RPO | R-5903 | NOT FUNDED | NOT FUNDED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE
WATAUGA | US 421 (DANIEL BOONE PARKWAY) | US 321/421 WEST OF BOONE TO NC 105 | HIGHWAY | 11 | HIGH COUNTRY RPO | R-5915A | NOT FUNDED | NOT FUNDED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE
WATAUGA | US 421 (DANIEL BOONE PARKWAY) | NC 105 TO US 221/321 SOUTH OF BOONE | HIGHWAY | 11 | HIGH COUNTRY RPO | R-5915B | DIVISION 11 | DIVISION 11 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2028 | 2028 | NO CHANGE | 2028 | 2028 | NO CHANGE | 2031 | 2031 | NO CHANGE
WATAUGA | US 421 (DANIEL BOONE PARKWAY) | US 221/321 TO US 221/421 EAST OF BOONE | HIGHWAY | 11 | HIGH COUNTRY RPO | R-5915C | NOT FUNDED | NOT FUNDED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE
WATAUGA | US 421/US 321 | US 321/US 421 JUNCTION NEAR VILAS TO SR 1107 (105 BYPASS) - TERMINI OF PROPOSED DANIEL BOONE PARKWAY (R-5915). WIDEN TO MULTI-LANES. | HIGHWAY | 11 | HIGH COUNTRY RPO | R-2615 | REGION F | REGION F | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2027 | 2027 | NO CHANGE | 2027 | 2027 | NO CHANGE | 2030 | 2030 | NO CHANGE
WAYNE | MOUNT OLIVE MUNICIPAL AIRPORT (W40) | EXTEND RUNWAY TO 5500 FEET. | AVIATION | 4 | EASTERN CAROLINA RPO | AV-5811 | DIVISION 4 | DIVISION 4 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | N/A | N/A | NO CHANGE | N/A | N/A | NO CHANGE | 2027 | 2027 | NO CHANGE
WAYNE | WAYNE EXECUTIVE JETPORT (GWW) | EXTEND RUNWAY. | AVIATION | 4 | GOLDSBORO URBAN AREA MPO | AV-5843 | DIVISION 4 | DIVISION 4 | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | N/A | N/A | NO CHANGE | N/A | N/A | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE
WAYNE | GOLDSBORO | BERKELEY BOULEVARD, US 70 BUSINESS (EAST ASH STREET) TO SR 1900 (ELM STREET) IN GOLDSBORO. CONSTRUCT SIDEWALK ON EAST SIDE. | BIKE/PED | 4 | GOLDSBORO URBAN AREA MPO | EB-5850 | DIVISION 4 | DIVISION 4 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | N/A | N/A | NO CHANGE | N/A | N/A | NO CHANGE | 2025 | 2025 | NO CHANGE
WAYNE | NC 581 (BILL LANE BOULEVARD) | ARRINGTON BRIDGE ROAD TO NC 111. MODERNIZE ROADWAY. | HIGHWAY | 4 | GOLDSBORO URBAN AREA MPO | U-6207 | DIVISION 4 | DIVISION 4 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2027 | 2027 | NO CHANGE | 2027 | 2027 | NO CHANGE | 2029 | 2029 | NO CHANGE
WAYNE | SR 1556 (WAYNE MEMORIAL DRIVE) | SR 1003 (NEW HOPE ROAD) TO PROPOSED US 70 BYPASS IN GOLDSBORO. WIDEN TO MULTI-LANES. | HIGHWAY | 4 | GOLDSBORO URBAN AREA MPO | U-4753 | DIVISION 4 | DIVISION 4 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2019 | 2019 | NO CHANGE | N/A | N/A | NO CHANGE | 2025 | 2025 | NO CHANGE
WAYNE | SR 1556 (WAYNE MEMORIAL DRIVE) | COUNTRY DAY ROAD TO NEW HOPE ROAD. ACCESS MANAGEMENT. | HIGHWAY | 4 | GOLDSBORO URBAN AREA MPO | U-6204 | DIVISION 4 | DIVISION 4 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2026 | 2025 | 1 YEAR ACCELERATION | 2026 | 2025 | 1 YEAR ACCELERATION | 2028 | 2028 | NO CHANGE
WAYNE | SR 1556 (WAYNE MEMORIAL DRIVE) | US 70 BYPASS TO SR 1572 (SAULSTON ROAD). WIDEN ROADWAY. | HIGHWAY | 4 | GOLDSBORO URBAN AREA MPO | U-6205 | DIVISION 4 | DIVISION 4 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2027 | 2027 | NO CHANGE | 2027 | 2027 | NO CHANGE | 2029 | 2029 | NO CHANGE
WAYNE | SR 1713 (MILLER'S CHAPEL ROAD) | US 70 TO SR 1712 (THOROUGHFARE ROAD). MODERNIZE ROADWAY. | HIGHWAY | 4 | GOLDSBORO URBAN AREA MPO | U-6206 | DIVISION 4 | DIVISION 4 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2027 | 2027 | NO CHANGE | 2027 | 2027 | NO CHANGE | 2029 | 2029 | NO CHANGE
WAYNE | US 117 (FUTURE I-795) | NORTH OF SR 1135 (COUNTRY CLUB ROAD) TO SOUTH OF SR 1129 (SOUTH LANDFILL ROAD). | HIGHWAY | 4 | GOLDSBORO URBAN AREA MPO, EASTERN CAROLINA RPO | U-3125C | REGION A | REGION A | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2026 | 2026 | NO CHANGE | 2026 | 2026 | NO CHANGE | 2028 | 2028 | NO CHANGE
WAYNE | US 117 (FUTURE I-795) | SOUTH OF SR 1129 (SOUTH LANDFILL ROAD) TO SOUTH OF SR 1927 (GENOA ROAD). | HIGHWAY | 4 | GOLDSBORO URBAN AREA MPO | U-3125D | REGION A | REGION A | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2027 | 2027 | NO CHANGE | 2027 | 2027 | NO CHANGE | 2029 | 2029 | NO CHANGE
WAYNE | US 117 (FUTURE I-795) | SOUTH OF SR 1927 (GENOA ROAD) TO NORTH OF NC 581 (ARRINGTON BRIDGE ROAD). | HIGHWAY | 4 | GOLDSBORO URBAN AREA MPO | U-3125E | NOT FUNDED | NOT FUNDED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE
WAYNE | US 117 (FUTURE I-795) | NORTH OF NC 581 (ARRINGTON BRIDGE ROAD) TO I-795. | HIGHWAY | 4 | GOLDSBORO URBAN AREA MPO | U-3125F | NOT FUNDED | NOT FUNDED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE
WAYNE | US 13 (BERKELEY BOULEVARD) | WIDEN TO MULTI-LANES FROM SR 1003 (NEW HOPE ROAD) TO US 70 BYPASS WITH INTERSECTION IMPROVEMENT AT SR1572 (SAULSTON ROAD) | HIGHWAY | 4 | GOLDSBORO URBAN AREA MPO | U-3609B | REGION A | REGION A | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2020 | 2020 | NO CHANGE | 2020 | 2020 | NO CHANGE | 2025 | 2025 | NO CHANGE
WAYNE | US 70 | SR 1711 (NORTH OAK FOREST ROAD). IMPROVE INTERSECTION. | HIGHWAY | 4 | GOLDSBORO URBAN AREA MPO | U-6110 | REGION A | REGION A | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2025 | 2025 | NO CHANGE | 2025 | 2025 | NO CHANGE | 2027 | 2027 | NO CHANGE
WAYNE | US 70 BUSINESS (EAST ASH STREET) | SR 1579 (BERKELEY BOULEVARD) EAST TO US 70 IN GOLDSBORO. WIDEN TO MULTI-LANES. | HIGHWAY | 4 | GOLDSBORO URBAN AREA MPO | U-4407 | REGION A | REGION A | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2026 | 2026 | NO CHANGE | 2026 | 2026 | NO CHANGE | 2028 | 2028 | NO CHANGE
WAYNE, GREENE | US 13 | SR 1572 (SAULSTON ROAD) TO SR 1700 (RODELL BARROW ROAD). MODERNIZE ROADWAY. | HIGHWAY | 2, 4 | GOLDSBORO URBAN AREA MPO, EASTERN CAROLINA RPO | R-5853 | DIVISION 2, 4 | DIVISION 2, 4 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2025 | 2025 | NO CHANGE | 2025 | 2025 | NO CHANGE | 2027 | 2027 | NO CHANGE
WAYNE, JOHNSTON | US 70 | US 70 BYPASS TO WEST OF SR 2372 (EDWARDS ROAD / NORTH PEARL STREET). UPGRADE TO FREEWAY STANDARDS. | HIGHWAY | 4 | EASTERN CAROLINA RPO, GOLDSBORO URBAN AREA MPO, UPPER COASTAL PLAIN RPO | R-5829A | STATEWIDE MOBILITY | STATEWIDE MOBILITY | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NO CHANGE
WILKES | WILKES COUNTY AIRPORT (UKF) | EXTEND RUNWAY TO 7,000 FEET. | AVIATION | 11 | HIGH COUNTRY RPO | AV-5894 | DIVISION 11 | DIVISION 11 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2023 | 2023 | NO CHANGE | N/A | N/A | NO CHANGE | 2024 | 2024 | NO CHANGE
WILKES | NC 115 | US 421 TO 2ND STREET. WIDEN ROADWAY. | HIGHWAY | 11 | HIGH COUNTRY RPO | R-5759 | DIVISION 11 | DIVISION 11 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2022 | 2022 | NO CHANGE | 2022 | 2022 | NO CHANGE | 2024 | 2024 | NO CHANGE
WILKES | NC 268 | SR 1966 TO FOUR LANES WEST OF SR 2026 (AUSTIN TRAPHILL ROAD). MODERNIZE ROADWAY. | HIGHWAY | 11 | HIGH COUNTRY RPO | R-5906 | DIVISION 11 | DIVISION 11 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2026 | 2028 | 2 YEAR DELAY | 2026 | 2028 | 2 YEAR DELAY | 2029 | 2031 | 2 YEAR DELAY
WILKES | NEW ROUTE | NC 268 CONNECTOR, NC 18 TO US 421. CONSTRUCT MULTI-LANE FACILITY, PART ON NEW LOCATION. | HIGHWAY | 11 | HIGH COUNTRY RPO | R-0616 | NOT FUNDED | NOT FUNDED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE
WILKES | SR 1001 (OAKWOODS ROAD) | US 421 TO FOREST HILLS DRIVE. UPGRADE ROADWAY. | HIGHWAY | 11 | HIGH COUNTRY RPO | R-5772 | DIVISION 11 | DIVISION 11 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2026 | 2025 | 1 YEAR ACCELERATION | 2026 | 2025 | 1 YEAR ACCELERATION | 2028 | 2027 | 1 YEAR ACCELERATION
WILSON | NC 58 (NASH STREET NW) | SR 1330 (AIRPORT ROAD)/SR 1332 (LAKE WILSON ROAD). IMPROVE INTERSECTION. | HIGHWAY | 4 | UPPER COASTAL PLAIN RPO | U-6111 | REGION A | REGION A | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2027 | 2027 | NO CHANGE | 2027 | 2027 | NO CHANGE | 2029 | 2029 | NO CHANGE
WILSON | SR 1309 (BLOOMERY ROAD) / SR 1382 (PACKHOUSE ROAD) | US 264 ALTERNATE TO NC 58. WIDEN AND UPGRADE FACILITY. | HIGHWAY | 4 | UPPER COASTAL PLAIN RPO | U-5794 | DIVISION 4 | NOT FUNDED | SCHEDULED FOR DELIVERY | WILL BE REPRIORITIZED | 2023 | NOT FUNDED | PROJECT NO LONGER FUNDED | 2023 | NOT FUNDED | PROJECT NO LONGER FUNDED | 2025 | NOT FUNDED | PROJECT NO LONGER FUNDED |  | YES
WILSON | US 264 ALTERNATE (RALEIGH ROAD PARKWAY) | SR 1320 (AIRPORT BOULEVARD) TO EAST OF SR 1165 (FOREST HILLS ROAD). SAFETY IMPROVEMENTS. | HIGHWAY | 4 | UPPER COASTAL PLAIN RPO | U-5941 | REGION A | REGION A | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2026 | 2026 | NO CHANGE | 2026 | 2026 | NO CHANGE | 2028 | 2028 | NO CHANGE
WILSON | WILSON | WILSON CITY SIGNAL SYSTEM. | HIGHWAY | 4 | UPPER COASTAL PLAIN RPO | U-5945 | NOT FUNDED | DIVISION 4 | WILL BE REPRIORITIZED | SCHEDULED FOR DELIVERY | N/A | N/A | NO CHANGE | NOT FUNDED | 2024 | PROJECT BECOMES COMMITTED | NOT FUNDED | 2025 | PROJECT BECOMES COMMITTED |  | YES
YADKIN | NC 67 | US 601 IN BOONVILLE TO WEST MAIN STREET IN EAST BEND. MODERNIZE ROADWAY WITH INTERSECTION IMPROVEMENTS AT NEBO ROAD. | HIGHWAY | 11 | NORTHWEST PIEDMONT RPO | R-5914 | DIVISION 11 | DIVISION 11 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2026 | 2026 | NO CHANGE | 2026 | 2026 | NO CHANGE | 2028 | 2028 | NO CHANGE
YADKIN | SR 1314 (EAST MAIN STREET) | US 601 TO SR 1765 (UNIFI INDUSTRIAL ROAD) IN YADKINVILLE. MODERNIZE ROADWAY, INCLUDING IMPROVEMENTS AT THE US 601 AND VAN BUREN STREET INTERSECTIONS. | HIGHWAY | 11 | NORTHWEST PIEDMONT RPO | R-5909 | DIVISION 11 | DIVISION 11 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2026 | 2026 | NO CHANGE | 2026 | 2026 | NO CHANGE | 2028 | 2028 | NO CHANGE
YADKIN | SR 1605 (OLD US 421) | SR 1600 (FALCON ROAD) INTERSECTION. CONSTRUCT ROUNDABOUT. | HIGHWAY | 11 | NORTHWEST PIEDMONT RPO | R-5912 | DIVISION 11 | DIVISION 11 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2023 | 2023 | NO CHANGE | 2023 | 2023 | NO CHANGE | 2024 | 2024 | NO CHANGE
YADKIN | US 601 | NC 67 TO (SR 1502/1503) COUNTRY CLUB ROAD. MODERNIZE ROADWAY AND IMPROVE SR 1134 (MACKIE ROAD) INTERSECTION. | HIGHWAY | 11 | NORTHWEST PIEDMONT RPO | R-5896 | NOT FUNDED | NOT FUNDED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE | NOT FUNDED | NOT FUNDED | NO CHANGE
YADKIN | US 601 (SOUTH STATE STREET) | US 421 EASTBOUND RAMPS. INSTALL ROUNDABOUT. | HIGHWAY | 11 | NORTHWEST PIEDMONT RPO | R-5894 | REGION F | NOT FUNDED | SCHEDULED FOR DELIVERY | WILL BE REPRIORITIZED | 2024 | NOT FUNDED | PROJECT NO LONGER FUNDED | 2024 | NOT FUNDED | PROJECT NO LONGER FUNDED | 2026 | NOT FUNDED | PROJECT NO LONGER FUNDED |  | YES
YADKIN | US 601 (STATE STREET) | US 421 TO SR 1146 (LEE AVENUE). CONSTRUCT MEDIAN AND ROUNDABOUTS. | HIGHWAY | 11 | NORTHWEST PIEDMONT RPO | U-5809 | DIVISION 11 | DIVISION 11 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | UNDERWAY | UNDERWAY | NO CHANGE | UNDERWAY | UNDERWAY | NO CHANGE | 2024 | 2024 | NO CHANGE
YADKIN, SURRY | NC 67, US 21 BUSINESS | COMMERCE STREET IN ELKIN TO NORTH BRIDGE STREET IN JONESVILLE. WIDEN ROADWAY, CONSTRUCT ROUNDABOUTS AT WEST MAIN STREET AND ELM STREET AND ELM STREET AND NORTH BRIDGE STREET, AND IMPROVE BICYCLE AND PEDESTRIAN CONNECTIONS. | HIGHWAY | 11 | NORTHWEST PIEDMONT RPO | R-5913A | DIVISION 11 | DIVISION 11 | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2023 | 2023 | NO CHANGE | 2023 | 2023 | NO CHANGE | 2025 | 2025 | NO CHANGE